## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | Augmentation of Ghoshpur Piped Water Supply Scheme under Khanakul-I Block | SM/15787 | Augmentation | Repairing of Concrete Roads damaged due to Laying of Augmentation work of GHOSHPUR Water Supply Scheme under KHANAKUL-II Block under Arambag Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000022/2023-2024 | 1102/HUG | 17/04/2023 | 17/05/2023 | ARATI ENGINEERING | 18.55 | 0 | 0 | 0
2 | HOOGHLY |  | Hooghly Division | Augmentation of Ghoshpur Piped Water Supply Scheme under Khanakul-I Block | SM/15787 | Augmentation | AUGMENTATION of GHOSHPUR Piped Water Supply Scheme with Extension of LDS, Rising Main, FHTC & construction of switch-room & boundary wall at Proposed TW site under Arambagh Sub-Division Of Hooghly Division P.H.E Dte. Block-KHANAKUL-I, District:- Hooghly. [AUGMENTATION SCHEME] | Assistant Engineer | Junior Engineer (Civill) | ORD/000324/2023-2024 | 2414/HUG | 11/08/2023 | 01/04/2025 | GHOSH BROTHERS | 333.22 | 233.14 | 69.97 | 80
3 | HOOGHLY |  | Hooghly Division | Augmentation of Ghoshpur Piped Water Supply Scheme under Khanakul-I Block | SM/15787 | Augmentation | Sinking of One No Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto150 Mtr at GHOSHPUR PWSS of ARAMBAGH Sub-Division under Hooghly Division, PHE Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000771/2022-2023 | 742/HUG | 15/03/2023 | 14/04/2023 | MAYA CONSTRUCTION | 11.32 | 11.32 | 100 | 100
4 | HOOGHLY |  | Hooghly Division | Augmentation of Ghoshpur Piped Water Supply Scheme under Khanakul-I Block | SM/15787 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000190/2023-2024 | 1385/61/Hug | 15/05/2023 | 15/05/2023 | Resource Division | 0.31 | 0 | 0 | 0
5 | HOOGHLY |  | Hooghly Division | Augmentation of Ghoshpur Piped Water Supply Scheme under Khanakul-I Block | SM/15787 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000099/2023-2024 | 1263/16/Hug | 03/05/2023 | 03/05/2023 | Resource Division | 61 | 0 | 0 | 0
6 | HOOGHLY |  | Electrical | Augmentation of Ghoshpur Piped Water Supply Scheme under Khanakul-I Block | SM/15787 | Augmentation | Quotation Bill for New Service Connection at Ghoshpur W/S. Sch.PH-V |  |  | BILL/04584/2023-2024 | 585 | 28/12/2023 | 28/12/2023 | WBSEDCL | 3.58 | 0 | 0 | 0
7 | HOOGHLY |  | Electrical | Augmentation of Ghoshpur Piped Water Supply Scheme under Khanakul-I Block | SM/15787 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Ghoshpur water supply scheme, T.W. No. I, Block: Khanakul-I, District: Hooghly under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/002474/2023-2024 | 335/ED | 21/02/2024 | 21/05/2024 | DEY ENTERPRISE | 10.43 | 0 | 0 | 0
8 | HOOGHLY |  | Electrical | Augmentation of Ghoshpur Piped Water Supply Scheme under Khanakul-I Block | SM/15787 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for ARUNDA PIPED W/S SCHEME, Zone - II, T.W. No. V, Block: Khanakul - I, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000208/2024-2025 | 1176/ED | 14/06/2024 | 12/09/2024 | P.K. ENTERPRISE | 10.72 | 0 | 0 | 0
9 | HOOGHLY |  | Hooghly Division | Augmentation of Ghoshpur Piped Water Supply Scheme under Khanakul-I Block | SM/15787 | Augmentation | Protection works and other allied works at Head Work Site of GHOSHPUR Water Supply Scheme under Arambagh Sub-Division of Hooghly Division P.H.E Dte |  |  | ORD/000480/2024-2025 | 4056/HUG | 19/12/2024 | 19/03/2025 | CITYCON UNEMPLOYED ENGINEERS CO-OP SOCIETY LTD | 23.74 | 0 | 0 | 0
10 | HOOGHLY |  | Hooghly Division | Augmentation of Ghoshpur Piped Water Supply Scheme under Khanakul-I Block | SM/15787 | Augmentation | Protection works and other allied works at 3Nos. Proposed TubeWell Sites of Ghoshpur Water Supply Scheme under Arambagh Sub-Division of Hooghly Division P.H.E Dte. |  |  | ORD/000474/2024-2025 | 4053/HUG | 19/12/2024 | 19/03/2025 | M/S KAUSAR CONSTRUCTION | 23.36 | 0 | 0 | 0
Total | [13 empty] | 496.22 | 244.46 | 49.27