## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Electrical | Augmentation of Chiladangi Piped Water Supply Scheme under Pursurah Block | SM/15788 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Chiladangi water supply scheme, T.W. No. I, Block: Pursura, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer1 | ORD/001146/2022-2023 | 1498/ED | 28/03/2023 | 26/06/2023 | DAS ENTERPRISE | 10.73 | 0 | 0 | 0
2 | HOOGHLY |  | Hooghly Division | Augmentation of Chiladangi Piped Water Supply Scheme under Pursurah Block | SM/15788 | Augmentation | AUGMENTATION of CHILADANGI Piped Water Supply Scheme with Extension of LDS, Rising Main, FHTC & construction of switch-room & boundary wall at Proposed TW site under Arambagh Sub-Division Of Hooghly Division P.H.E Dte. Block-PURSURAH, District:- Hooghly. [AUGMENTATION SCHEME] | Assistant Engineer | Junior Engineer (Civill) | ORD/000252/2023-2024 | 2147/HUG | 24/07/2023 | 22/10/2023 | GHOSH BROTHERS | 215.95 | 0 | 0 | 0
3 | HOOGHLY |  | Electrical | Augmentation of Chiladangi Piped Water Supply Scheme under Pursurah Block | SM/15788 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Chiladangi water supply scheme, T.W. No. II, Block: Pursura, District- Hooghly under Electrical Division, PHE Dte. |  |  | ORD/001531/2021-2022 | 3004_ED | 29/12/2021 | 29/03/2022 | A.G. ENTERPRISE | 10.52 | 0 | 0 | 0
4 | HOOGHLY |  | Hooghly Division | Augmentation of Chiladangi Piped Water Supply Scheme under Pursurah Block | SM/15788 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000144/2023-2024 | 1385/16/Hug | 15/05/2023 | 15/05/2023 | Resource Division | 0.31 | 0 | 0 | 0
5 | HOOGHLY |  | Hooghly Division | Augmentation of Chiladangi Piped Water Supply Scheme under Pursurah Block | SM/15788 | Augmentation | AUGMENTATION of CHILADANGI Piped Water Supply Scheme with Extension of LDS, Rising Main, FHTC & construction of switch-room & boundary wall at Proposed TW site under Arambagh Sub-Division Of Hooghly Division P.H.E Dte. Block-PURSURAH, District:- Hooghly[AUGMENTATION SCHEME] | Assistant Engineer | Junior Engineer (Civill) | ORD/000322/2023-2024 | 2413/HUG | 11/08/2023 | 01/04/2025 | GHOSH BROTHERS | 215.95 | 0 | 0 | 65
Total | [13 empty] | 453.47 | 0 | 0