## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Arambag | Hooghly Division | Bhalia (Zone-I) Piped Water Supply Scheme, Block-Arambagh, District-Hooghly | SM/15789 | New | Material Requisition To Resource Division |  |  | RTOR000178/2023-2024 | 1385/49/Hug | 15/05/2023 | 15/05/2023 | Resource Division | 13.46 | 0 | 0 | 0
2 | HOOGHLY | Arambag | Hooghly Division | Bhalia (Zone-I) Piped Water Supply Scheme, Block-Arambagh, District-Hooghly | SM/15789 | New | Material Requisition To Resource Division |  |  | RTOR000456/2023-2024 | 3057/22/Hug | 11/10/2023 | 11/10/2023 | Resource Division | 13.46 | 0 | 0 | 0
3 | HOOGHLY | Arambag | Hooghly Division | Bhalia (Zone-I) Piped Water Supply Scheme, Block-Arambagh, District-Hooghly | SM/15789 | New | Material Requisition To Resource Division |  |  | RTOR000031/2023-2024 | 1234/12/Hug | 28/04/2023 | 28/04/2023 | Resource Division | 43.14 | 0 | 0 | 0
4 | HOOGHLY | Arambag | Electrical | Bhalia (Zone-I) Piped Water Supply Scheme, Block-Arambagh, District-Hooghly | SM/15789 | New | Quotation Bill for New Service Connectio at Bhalia W/S. Sch. Z-I, TW-IV |  |  | BILL/04161/2023-2024 | 396 | 06/11/2023 | 06/11/2023 | WBSEDCL | 4.24 | 0 | 0 | 0
5 | HOOGHLY | Arambag | Electrical | Bhalia (Zone-I) Piped Water Supply Scheme, Block-Arambagh, District-Hooghly | SM/15789 | New | "Quotation Bill for New Service Connection at Bhalia W/S. Sch. Z-I" |  |  | BILL/04164/2023-2024 | 401 | 09/11/2023 | 09/11/2023 | WBSEDCL | 4.24 | 0 | 0 | 0
6 | HOOGHLY | Arambag | Electrical | Bhalia (Zone-I) Piped Water Supply Scheme, Block-Arambagh, District-Hooghly | SM/15789 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for BHALIA PIPED W/S SCHEME, Zone - I, T.W. No. III, Block: Arambag, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000188/2024-2025 | 1204/ED | 14/06/2024 | 12/09/2024 | C.M.S. ENGINEERING CONCERN | 10.95 | 0 | 0 | 0
7 | HOOGHLY | Arambag | Electrical | Bhalia (Zone-I) Piped Water Supply Scheme, Block-Arambagh, District-Hooghly | SM/15789 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Bhalia (Zone-I) water supply scheme, T.W. No. I & II, Block: Arambag, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 2 | Junior Engineer4 | ORD/000009/2023-2024 | 1625/ED | 11/04/2023 | 10/07/2023 | C.M.S. ENGINEERING CONCERN | 22.04 | 0 | 0 | 30
8 | HOOGHLY | Arambag | Hooghly Division | Bhalia (Zone-I) Piped Water Supply Scheme, Block-Arambagh, District-Hooghly | SM/15789 | New | BHALIA ZONE-I Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 300 cum capacity RCC OHR with 20.0 mtr. Staging height including soil investigation & construction of switch-room & boundary wall at Proposed TW site, under Arambagh Sub-Division of Hooghly Division P.H.E Dte. Block Arambagh, District:- Hooghly [NEW SCHEME] [2nd Call of WBPHE/EE/53/HUG/2022-23(Sl No. 2)] | Assistant Engineer | Junior Engineer (Civill) | ORD/000241/2023-2024 | 2079/HUG | 18/07/2023 | 01/01/2026 | PRASUN ENTERPRISE (PRASUN BISWAS) | 496.11 | 0 | 0 | 30
Total | [13 empty] | 607.64 | 0 | 0