## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Arambag | Hooghly Division | Bhalia (Zone-I) Piped Water Supply Scheme, Block-Arambagh, District-Hooghly | SM/15789 | New | Material Requisition To Resource Division |  |  | RTOR000178/2023-2024 | 1385/49/Hug | 15/05/2023 | 15/05/2023 | Resource Division | 13.46 | 0 | 0 | 0
2 | HOOGHLY | Arambag | Hooghly Division | Bhalia (Zone-I) Piped Water Supply Scheme, Block-Arambagh, District-Hooghly | SM/15789 | New | Material Requisition To Resource Division |  |  | RTOR000456/2023-2024 | 3057/22/Hug | 11/10/2023 | 11/10/2023 | Resource Division | 13.46 | 0 | 0 | 0
3 | HOOGHLY | Arambag | Hooghly Division | Bhalia (Zone-I) Piped Water Supply Scheme, Block-Arambagh, District-Hooghly | SM/15789 | New | Material Requisition To Resource Division |  |  | RTOR000031/2023-2024 | 1234/12/Hug | 28/04/2023 | 28/04/2023 | Resource Division | 43.14 | 0 | 0 | 0
4 | HOOGHLY | Arambag | Electrical | Bhalia (Zone-I) Piped Water Supply Scheme, Block-Arambagh, District-Hooghly | SM/15789 | New | Quotation Bill for New Service Connectio at Bhalia W/S. Sch. Z-I, TW-IV |  |  | BILL/04161/2023-2024 | 396 | 06/11/2023 | 06/11/2023 | WBSEDCL | 4.24 | 0 | 0 | 0
5 | HOOGHLY | Arambag | Electrical | Bhalia (Zone-I) Piped Water Supply Scheme, Block-Arambagh, District-Hooghly | SM/15789 | New | "Quotation Bill for New Service Connection at Bhalia W/S. Sch. Z-I" |  |  | BILL/04164/2023-2024 | 401 | 09/11/2023 | 09/11/2023 | WBSEDCL | 4.24 | 0 | 0 | 0
6 | HOOGHLY | Arambag | Electrical | Bhalia (Zone-I) Piped Water Supply Scheme, Block-Arambagh, District-Hooghly | SM/15789 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for BHALIA PIPED W/S SCHEME, Zone - I, T.W. No. III, Block: Arambag, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000188/2024-2025 | 1204/ED | 14/06/2024 | 12/09/2024 | C.M.S. ENGINEERING CONCERN | 10.95 | 0 | 0 | 0
7 | HOOGHLY | Arambag | Electrical | Bhalia (Zone-I) Piped Water Supply Scheme, Block-Arambagh, District-Hooghly | SM/15789 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Bhalia (Zone-I) water supply scheme, T.W. No. I & II, Block: Arambag, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 2 | Junior Engineer4 | ORD/000009/2023-2024 | 1625/ED | 11/04/2023 | 10/07/2023 | C.M.S. ENGINEERING CONCERN | 22.04 | 0 | 0 | 30
8 | HOOGHLY | Arambag | Hooghly Division | Bhalia (Zone-I) Piped Water Supply Scheme, Block-Arambagh, District-Hooghly | SM/15789 | New | BHALIA ZONE-I Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 300 cum capacity RCC OHR with 20.0 mtr. Staging height including soil investigation & construction of switch-room & boundary wall at Proposed TW site, under Arambagh Sub-Division of Hooghly Division P.H.E Dte. Block Arambagh, District:- Hooghly [NEW SCHEME] [2nd Call of WBPHE/EE/53/HUG/2022-23(Sl No. 2)] | Assistant Engineer | Junior Engineer (Civill) | ORD/000241/2023-2024 | 2079/HUG | 18/07/2023 | 01/01/2026 | PRASUN ENTERPRISE (PRASUN BISWAS) | 496.11 | 0 | 0 | 30
9 | HOOGHLY | Arambag | Hooghly Division | Bhalia (Zone-I) Piped Water Supply Scheme, Block-Arambagh, District-Hooghly | SM/15789 | New | Designing making and erection of Display Board using logo and tag line of LAND DEMARCATION OF P.H.E. Dte. to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under ARAMBAGH Sub Division under Hooghly Division PHE Dte. 1. HARISCHAK(Z-I)PWSS- 1 nos 2. HARISCHAK(Z-II)PWSS- 1nos 3. MAINAN PWSS - 2nos 4. PURBA THAKURANICHAK(Z-I)PWSS - 2nos 5. PURBA THAKURANICHAK(Z-II)PWSS- 2nos 6. GOURHATI PWSS - 2nos 7. KANPUR PWSS- 2nos 8. TANTISAL PWSS - 2nos | Assistant Engineer | Junior Engineer (Civill) | ORD/000533/2024-2025 | 820/Arg | 23/08/2024 | 22/09/2024 | M/S KHAMRUI CONSTRUCTION | 0.98 | 0 | 0 | 100
Total | [13 empty] | 608.62 | 0 | 0