## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Arambag | Electrical | GROUND WATER BASED MAYAPUR (ZONE-II) PIPED WATER SUPPLY SCHEME IN ARAMBAG BLOCK UNDER HOOGHLY DIVISION, HOOGHLY | SM/15790 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Mayapur (Zone-II) water supply scheme, T.W. No. I & II, Block: Arambag, District- Hooghly under Electrical Division, PHE Dte. |  |  | ORD/000025/2023-2024 | 1702/ED | 18/04/2023 | 17/07/2023 | NUPUR CHANDRA HALDER | 20.8 | 0 | 0 | 0
2 | HOOGHLY | Arambag | Hooghly Division | GROUND WATER BASED MAYAPUR (ZONE-II) PIPED WATER SUPPLY SCHEME IN ARAMBAG BLOCK UNDER HOOGHLY DIVISION, HOOGHLY | SM/15790 | New | Material Requisition To Resource Division |  |  | RTOR000472/2023-2024 | 3057/12/Hug | 11/10/2023 | 11/10/2023 | Resource Division | 6.12 | 0 | 0 | 0
3 | HOOGHLY | Arambag | Hooghly Division | GROUND WATER BASED MAYAPUR (ZONE-II) PIPED WATER SUPPLY SCHEME IN ARAMBAG BLOCK UNDER HOOGHLY DIVISION, HOOGHLY | SM/15790 | New | Material Requisition To Resource Division |  |  | RTOR000186/2023-2024 | 1385/57/Hug | 15/05/2023 | 15/05/2023 | Resource Division | 2.68 | 0 | 0 | 0
4 | HOOGHLY | Arambag | Hooghly Division | GROUND WATER BASED MAYAPUR (ZONE-II) PIPED WATER SUPPLY SCHEME IN ARAMBAG BLOCK UNDER HOOGHLY DIVISION, HOOGHLY | SM/15790 | New | Material Requisition To Resource Division |  |  | RTOR000041/2023-2024 | 1234/14/Hug | 28/04/2023 | 28/04/2023 | Resource Division | 25.34 | 0 | 0 | 0
5 | HOOGHLY | Arambag | Hooghly Division | GROUND WATER BASED MAYAPUR (ZONE-II) PIPED WATER SUPPLY SCHEME IN ARAMBAG BLOCK UNDER HOOGHLY DIVISION, HOOGHLY | SM/15790 | New | MAYAPUR ZONE-II Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 150 cum capacity RCC OHR with 20.0 mtr. Staging height including soil investigation & construction of switch-room & boundary wall at Proposed TW site under Arambagh Sub-Division of Hooghly Division P.H.E Dte. Block Arambagh, District:- Hooghly [NEW SCHEME] | Assistant Engineer | Junior Engineer (Civill) | ORD/000179/2023-2024 | 1618/hug | 02/06/2023 | 27/02/2024 | M/S RAJKUMAR KHAN | 246.71 | 56.24 | 22.8 | 20
6 | HOOGHLY | Arambag | Hooghly Division | GROUND WATER BASED MAYAPUR (ZONE-II) PIPED WATER SUPPLY SCHEME IN ARAMBAG BLOCK UNDER HOOGHLY DIVISION, HOOGHLY | SM/15790 | New | Sinking of 3 nos 300 X200 mm dia Tube Well, 210 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at Proposed Tube Well Site of KRISHNANAGAR Zone-II , MAYAPUR , TIROL Zone-I W/S Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. |  |  | ORD/000257/2024-2025 | 3530/HUG | 22/10/2024 | 06/12/2024 | PADMA ENGINEERING CO. | 47.5 | 0 | 0 | 0
7 | HOOGHLY | Arambag | Hooghly Division | GROUND WATER BASED MAYAPUR (ZONE-II) PIPED WATER SUPPLY SCHEME IN ARAMBAG BLOCK UNDER HOOGHLY DIVISION, HOOGHLY | SM/15790 | New | Laying of Additional Pipeline for MAYAPUR Piped Water Supply Scheme under ARAMBAGH SUB DIVISION Block Arambagh. |  |  | ORD/000230/2024-2025 | 3439/HUG | 03/10/2024 | 02/11/2024 | DILIP KUMAR GHOSH | 54.57 | 0 | 0 | 0
8 | HOOGHLY | Arambag | Hooghly Division | GROUND WATER BASED MAYAPUR (ZONE-II) PIPED WATER SUPPLY SCHEME IN ARAMBAG BLOCK UNDER HOOGHLY DIVISION, HOOGHLY | SM/15790 | New | MAYAPUR ZONE-II Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 150 cum capacity RCC OHR with 20.0 mtr. Staging height including soil investigation & construction of switch-room & boundary wall at Proposed TW site under Arambagh Sub-Division of Hooghly Division P.H.E Dte. Block Arambagh, District:- Hooghly [NEW SCHEME] | Assistant Engineer |  | ORD/000164/2023-2024 | 1618/Hug | 02/06/2023 | 27/02/2024 | M/S RAJKUMAR KHAN | 246.71 | 13.25 | 5.37 | 15
9 | HOOGHLY | Arambag | Electrical | GROUND WATER BASED MAYAPUR (ZONE-II) PIPED WATER SUPPLY SCHEME IN ARAMBAG BLOCK UNDER HOOGHLY DIVISION, HOOGHLY | SM/15790 | New | Quotation for New Service Connection at Mayapur W/S. Sch. Z=II |  |  | BILL/04611/2023-2024 | 610 | 04/01/2024 | 04/01/2024 | WBSEDCL | 6.44 | 0 | 0 | 0
Total | [13 empty] | 656.85 | 69.5 | 10.58