## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Arambag | Electrical | GROUND WATER BASED MAYAPUR (ZONE-I) PIPED WATER SUPPLY SCHEME IN ARAMBAG BLOCK UNDER HOOGHLY DIVISION, HOOGHLY | SM/15791 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Mayapur (Zone-I) water supply scheme, T.W. No. I, II, III & IV, Block: Arambag, District- Hooghly under Electrical Division, PHE Dte. |  |  | ORD/000034/2023-2024 | 1711/ED | 18/04/2023 | 17/07/2023 | D. K. ELECTRIC | 40.97 | 0 | 0 | 0
2 | HOOGHLY | Arambag | Hooghly Division | GROUND WATER BASED MAYAPUR (ZONE-I) PIPED WATER SUPPLY SCHEME IN ARAMBAG BLOCK UNDER HOOGHLY DIVISION, HOOGHLY | SM/15791 | New | Material Requisition To Resource Division |  |  | RTOR000187/2023-2024 | 1385/58/Hug | 15/05/2023 |  | Resource Division | 10.29 | 0 | 0 | 0
3 | HOOGHLY | Arambag | Electrical | GROUND WATER BASED MAYAPUR (ZONE-I) PIPED WATER SUPPLY SCHEME IN ARAMBAG BLOCK UNDER HOOGHLY DIVISION, HOOGHLY | SM/15791 | New | Adhoc Payment to WBSEDCL against service connection |  |  | BILL/01120/2023-2024 | null | 27/06/2023 |  | WBSEDCL | 104.27 | 0 | 0 | 0
4 | HOOGHLY | Arambag | Hooghly Division | GROUND WATER BASED MAYAPUR (ZONE-I) PIPED WATER SUPPLY SCHEME IN ARAMBAG BLOCK UNDER HOOGHLY DIVISION, HOOGHLY | SM/15791 | New | Material Requisition To Resource Division |  |  | RTOR000474/2023-2024 | 3057/11/Hug | 11/10/2023 |  | Resource Division | 10.29 | 0 | 0 | 0
5 | HOOGHLY | Arambag | Electrical | GROUND WATER BASED MAYAPUR (ZONE-I) PIPED WATER SUPPLY SCHEME IN ARAMBAG BLOCK UNDER HOOGHLY DIVISION, HOOGHLY | SM/15791 | New | Quotation for new service connection charge at Mayapur PWSS, Zone-I, TW - I |  |  | BILL/04372/2023-2024 | 462 | 01/12/2023 |  | WBSEDCL | 4.9 | 0 | 0 | 0
6 | HOOGHLY | Arambag | Electrical | GROUND WATER BASED MAYAPUR (ZONE-I) PIPED WATER SUPPLY SCHEME IN ARAMBAG BLOCK UNDER HOOGHLY DIVISION, HOOGHLY | SM/15791 | New | Quotation for new service connection charge at Mayapur PWSS, Zone-I, TW - I |  |  | BILL/04372/2023-2024 | 462 | 01/12/2023 |  | WBSEDCL | 4.9 | 0 | 0 | 0
7 | HOOGHLY | Arambag | Electrical | GROUND WATER BASED MAYAPUR (ZONE-I) PIPED WATER SUPPLY SCHEME IN ARAMBAG BLOCK UNDER HOOGHLY DIVISION, HOOGHLY | SM/15791 | New | Quotation for New Service Connection at Mayapur W/S. Sch. Z=I |  |  | BILL/04612/2023-2024 | 611 | 04/01/2024 |  | WBSEDCL | 5.8 | 0 | 0 | 0
8 | HOOGHLY | Arambag | Electrical | GROUND WATER BASED MAYAPUR (ZONE-I) PIPED WATER SUPPLY SCHEME IN ARAMBAG BLOCK UNDER HOOGHLY DIVISION, HOOGHLY | SM/15791 | New | Quotation for New Service Connection at Mayapur W/S. Sch. Z=I |  |  | BILL/04612/2023-2024 | 611 | 04/01/2024 |  | WBSEDCL | 5.8 | 0 | 0 | 0
9 | HOOGHLY | Arambag | Hooghly Division | GROUND WATER BASED MAYAPUR (ZONE-I) PIPED WATER SUPPLY SCHEME IN ARAMBAG BLOCK UNDER HOOGHLY DIVISION, HOOGHLY | SM/15791 | New | MAYAPUR ZONE-I Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 250 cum capacity RCC OHR with 20.0 mtr. Staging height including soil investigation & construction of switch-room & boundary wall at Proposed TW site, under Arambagh Sub-Division of Hooghly Division P.H.E Dte. Block Arambagh, District:- Hooghly [NEW SCHEME] | Assistant Engineer | Junior Engineer (Civill) | ORD/000073/2023-2024 | 1300 | 08/05/2023 | 02/02/2024 | MS PRADIP KUMAR PAL | 360.88 | 98.51 | 27.3 | 15
10 | HOOGHLY | Arambag | Hooghly Division | GROUND WATER BASED MAYAPUR (ZONE-I) PIPED WATER SUPPLY SCHEME IN ARAMBAG BLOCK UNDER HOOGHLY DIVISION, HOOGHLY | SM/15791 | New | Sinking of 3rd tube-well by D.R. Rig method ,Construction of 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement, Construction of Boundary Wall, Laying rising main pipe for inter connection between Proposed T.W & Distribution of MAYAPUR (ZONE-I) Piped Water Supply Scheme under ARAMBAGH Sub-Division of Hooghly Division P.HE Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000758/2023-2024 | 448/HUG | 15/02/2024 | 15/04/2024 | MS PRADIP KUMAR PAL | 29.69 | 12.09 | 40.73 | 40
11 | HOOGHLY | Arambag | Electrical | GROUND WATER BASED MAYAPUR (ZONE-I) PIPED WATER SUPPLY SCHEME IN ARAMBAG BLOCK UNDER HOOGHLY DIVISION, HOOGHLY | SM/15791 | New | Quotaion of New Service Connection for Mayapur w/s Scheme,Zone-I,PH No-II Block-Arambag Dist-Hooghly under Electrical Division,PHE Dte.(SM/15791) Application No-5004314243 Reference Id-503702554 |  |  | BILL/01355/2024-2025 | 334 | 30/07/2024 |  | WBSEDCL | 7.67 | 0 | 0 | null
Total | [13 empty] | 585.46 | 110.6 | 18.89