## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Khanakul-I | Electrical | GROUND WATER BASED ARUNDA (ZONE-II) PIPED WATER SUPPLY SCHEME IN KHANAKUL-I BLOCK UNDER HOOGHLY DIVISION, DISTRICT HOOGHLY | SM/15792 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Arunda (Zone-II) water supply scheme, T.W. No. I & II, Block: Khanakul-I, District- Hooghly under Electrical Division, PHE Dte. |  |  | ORD/001143/2022-2023 | 1495/ED | 28/03/2023 | 26/06/2023 | BARISAL TRADING CO. | 21.49 | 0 | 0 | 0
2 | HOOGHLY | Khanakul-I | Hooghly Division | GROUND WATER BASED ARUNDA (ZONE-II) PIPED WATER SUPPLY SCHEME IN KHANAKUL-I BLOCK UNDER HOOGHLY DIVISION, DISTRICT HOOGHLY | SM/15792 | New | Material Requisition To Resource Division |  |  | RTOR000132/2023-2024 | 1385/3/Hug | 15/05/2023 | 15/05/2023 | Resource Division | 12.79 | 0 | 0 | 0
3 | HOOGHLY | Khanakul-I | Hooghly Division | GROUND WATER BASED ARUNDA (ZONE-II) PIPED WATER SUPPLY SCHEME IN KHANAKUL-I BLOCK UNDER HOOGHLY DIVISION, DISTRICT HOOGHLY | SM/15792 | New | Material Requisition To Resource Division |  |  | RTOR000387/2023-2024 | 3057/58/Hug | 11/10/2023 | 11/10/2023 | Resource Division | 11.7 | 0 | 0 | 0
4 | HOOGHLY | Khanakul-I | Hooghly Division | GROUND WATER BASED ARUNDA (ZONE-II) PIPED WATER SUPPLY SCHEME IN KHANAKUL-I BLOCK UNDER HOOGHLY DIVISION, DISTRICT HOOGHLY | SM/15792 | New | Material Requisition To Resource Division |  |  | RTOR000066/2023-2024 | 1234/33/Hug | 28/04/2023 | 28/04/2023 | Resource Division | 25.46 | 0 | 0 | 0
5 | HOOGHLY | Khanakul-I | Electrical | GROUND WATER BASED ARUNDA (ZONE-II) PIPED WATER SUPPLY SCHEME IN KHANAKUL-I BLOCK UNDER HOOGHLY DIVISION, DISTRICT HOOGHLY | SM/15792 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for ARUNDA PIPED W/S SCHEME, Zone - II, T.W. No. V, Block: Khanakul - I, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000208/2024-2025 | 1176/ED | 14/06/2024 | 12/09/2024 | P.K. ENTERPRISE | 10.72 | 0 | 0 | 0
6 | HOOGHLY | Khanakul-I | Electrical | GROUND WATER BASED ARUNDA (ZONE-II) PIPED WATER SUPPLY SCHEME IN KHANAKUL-I BLOCK UNDER HOOGHLY DIVISION, DISTRICT HOOGHLY | SM/15792 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for ARUNDA PIPED W/S SCHEME, Zone - II, T.W. No. III, Block: Khanakul - I, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000151/2024-2025 | 1174/ED | 14/06/2024 | 12/09/2024 | BARISAL TRADING CO. | 10.74 | 0 | 0 | 0
7 | HOOGHLY | Khanakul-I | Electrical | GROUND WATER BASED ARUNDA (ZONE-II) PIPED WATER SUPPLY SCHEME IN KHANAKUL-I BLOCK UNDER HOOGHLY DIVISION, DISTRICT HOOGHLY | SM/15792 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for ARUNDA PIPED W/S SCHEME, Zone - II, T.W. No. IV, Block: Khanakul - I, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000152/2024-2025 | 1175/ED | 14/06/2024 | 12/09/2024 | S.M. ELECTRICALS | 10.74 | 0 | 0 | 0
8 | HOOGHLY | Khanakul-I | Electrical | GROUND WATER BASED ARUNDA (ZONE-II) PIPED WATER SUPPLY SCHEME IN KHANAKUL-I BLOCK UNDER HOOGHLY DIVISION, DISTRICT HOOGHLY | SM/15792 | New | Quotation of New Service Connection for Arunda w/s Scheme,Zone-II, PH No-I Block-Khanakul-I Dist-Hooghly under Electrical Division,PHE Dte.(SM/15792) Application No-5004460466 Reference Id-503787366 |  |  | BILL/02592/2024-2025 | 628 | 18/12/2024 | 18/12/2024 | WBSEDCL | 5.68 | 0 | 0 | 0
9 | HOOGHLY | Khanakul-I | Electrical | GROUND WATER BASED ARUNDA (ZONE-II) PIPED WATER SUPPLY SCHEME IN KHANAKUL-I BLOCK UNDER HOOGHLY DIVISION, DISTRICT HOOGHLY | SM/15792 | New | Quotation of New Service Connection for Arunda w/s Scheme,Zone-II, PH No-III Block-Khanakul-I Dist-Hooghly under Electrical Division,PHE Dte.(SM/15792) Application No-5004460458 Reference Id-503787369 |  |  | BILL/02276/2024-2025 | BP-24-25-579 | 19/11/2024 | 19/11/2024 | WBSEDCL | 4.06 | 0 | 0 | 0
10 | HOOGHLY | Khanakul-I | Hooghly Division | GROUND WATER BASED ARUNDA (ZONE-II) PIPED WATER SUPPLY SCHEME IN KHANAKUL-I BLOCK UNDER HOOGHLY DIVISION, DISTRICT HOOGHLY | SM/15792 | New | Designing making and erection of Display Board using logo and tag line of LAND DEMARCATION OF P.H.E. Dte. to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under ARAMBAGH Sub Division under Hooghly Division PHE Dte. (1) KHANAKUL PWSS (Z-I)- 1 no?s (2) PURBATHAKURANICHAK PWSS (Z-I)-2 no?s (3) ARUNDA PWSS (Z-I)- 4 no?s (4) ARUNDA PWSS (Z-II)- 5 no?s (5) POL PWSS ? 2no?s | Assistant Engineer | Junior Engineer (Civill) | ORD/002744/2024-2025 | 1152/Arg | 10/12/2024 | 10/01/2025 | HAZRA CONSTRUCTION | 0.98 | 0 | 0 | 0
11 | HOOGHLY | Khanakul-I | Hooghly Division | GROUND WATER BASED ARUNDA (ZONE-II) PIPED WATER SUPPLY SCHEME IN KHANAKUL-I BLOCK UNDER HOOGHLY DIVISION, DISTRICT HOOGHLY | SM/15792 | New | ARUNDA ZONE-II Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 300 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under KHANAKUL-I Block of Arambag Sub-Division under Hooghly Division, PHE Dte. [NEW SCHEME] | Assistant Engineer | Junior Engineer (Civill) | ORD/000269/2023-2024 | 2280/HUG | 03/08/2023 | 29/04/2024 | M/S. NANDY ENTERPRISE | 501.51 | 0 | 0 | 25
12 | HOOGHLY | Khanakul-I | Hooghly Division | GROUND WATER BASED ARUNDA (ZONE-II) PIPED WATER SUPPLY SCHEME IN KHANAKUL-I BLOCK UNDER HOOGHLY DIVISION, DISTRICT HOOGHLY | SM/15792 | New | Sinking of 4 (Four) Nos tube well (250 mm X 150 mm) with supply of PVC Pipe and strainer and having depth upto 180 M at CHINRA Z-II and ARUNDA Z-II W/S Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000849/2023-2024 | 726/HUG | 05/03/2024 | 06/03/2025 | GARHBETA - I UNEMPLOYED YOUTH ENGINEERS CO OPERATIVE | 39.06 | 9.57 | 24.51 | 75
Total | [13 empty] | 654.92 | 9.57 | 1.46