## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | Source Augmentation of Santoshpur Piped Water Supply scheme, Block- Tarakeswar, District-Hooghly | SM/15793 | Augmentation | Sinking of One No Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto180 Mtr at SANTOSHPUR PWSS of CHANDANNAGAR Sub-Division under Hooghly Division, PHE Dte. | Assistant Engineer (Civil) |  | ORD/000768/2022-2023 | 751/HUG | 15/03/2023 | 14/04/2023 | PAUL CONSTRUCTION (RANJIT KUMAR PAUL) | 12.44 | 0 | 0 | 0
2 | HOOGHLY |  | Electrical | Source Augmentation of Santoshpur Piped Water Supply scheme, Block- Tarakeswar, District-Hooghly | SM/15793 | Augmentation | Quotation money deposition for new service connection at Santoshpur w/s scheme, P.H. No.-3, Dist.-Hooghly under PHE Dte. Application No- 5004085290 Reference ID- 503609191 SM Code- 15793 |  |  | BILL/00439/2024-2025 | 129 | 17/05/2024 | 17/05/2024 | WBSEDCL | 6.12 | 0 | 0 | 0
3 | HOOGHLY |  | Electrical | Source Augmentation of Santoshpur Piped Water Supply scheme, Block- Tarakeswar, District-Hooghly | SM/15793 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Santoshpur water supply scheme, T.W. No. I, Block: Tarakeswar, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 2 | Junior Engineer2 | ORD/000007/2023-2024 | 1623/ED | 11/04/2023 | 31/03/2025 | UNIVERSAL ENTERPRISES | 10.75 | 0 | 0 | 100
Total | [13 empty] | 29.31 | 0 | 0