## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Electrical | Source Augmentation of Santoshpur Piped Water Supply scheme, Block- Tarakeswar, District-Hooghly | SM/15793 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Santoshpur water supply scheme, T.W. No. I, Block: Tarakeswar, District- Hooghly under Electrical Division, PHE Dte. |  |  | ORD/000007/2023-2024 | 1623/ED | 11/04/2023 | 10/07/2023 | UNIVERSAL ENTERPRISES | 10.75 | 0 | 0 | 0
2 | HOOGHLY |  | Hooghly Division | Source Augmentation of Santoshpur Piped Water Supply scheme, Block- Tarakeswar, District-Hooghly | SM/15793 | Augmentation | Construction of 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement, Boundary Wall in Proposed T.W Site, Laying rising main pipe for inter connection between T.W & Distribution For Source Augmentation of Santoshpur Piped Water Supply Scheme under Chandannagar Sub-Division of Hooghly Division P.HE Dte. within Tarakeswar Block. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000078/2023-2024 | 1312/HUG | 10/05/2023 | 09/06/2023 | SRI KRISHNA ENTERPRISE | 11.78 | 0 | 0 | 0
3 | HOOGHLY |  | Hooghly Division | Source Augmentation of Santoshpur Piped Water Supply scheme, Block- Tarakeswar, District-Hooghly | SM/15793 | Augmentation | Sinking of One No Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto180 Mtr at SANTOSHPUR PWSS of CHANDANNAGAR Sub-Division under Hooghly Division, PHE Dte. | Assistant Engineer (Civil) |  | ORD/000768/2022-2023 | 751/HUG | 15/03/2023 | 14/04/2023 | PAUL CONSTRUCTION (RANJIT KUMAR PAUL) | 12.44 | 0 | 0 | 0
4 | HOOGHLY |  | Electrical | Source Augmentation of Santoshpur Piped Water Supply scheme, Block- Tarakeswar, District-Hooghly | SM/15793 | Augmentation | Adhoc payment to WBSEDCL against Service Connection |  |  | BILL/01125/2023-2024 | null | 28/06/2023 |  | WBSEDCL | 71.17 | 0 | 0 | 0
5 | HOOGHLY |  | Electrical | Source Augmentation of Santoshpur Piped Water Supply scheme, Block- Tarakeswar, District-Hooghly | SM/15793 | Augmentation | Quotation money deposition for new service connection at Santoshpur w/s scheme, P.H. No.-3, Dist.-Hooghly under PHE Dte. Application No- 5004085290 Reference ID- 503609191 SM Code- 15793 |  |  | BILL/00439/2024-2025 | 129 | 17/05/2024 |  | WBSEDCL | 6.12 | 0 | 0 | null
Total | [13 empty] | 112.25 | 0 | 0