## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Electrical | Source Augmentation of Bamonjol PWSS | SM/15794 | Augmentation | Quotation of New Service Connection of Bamonjol W/S Scheme(Aug) TW No-3 District-Hooghly under Electrical Division, PHE Dte |  |  | BILL/01998/2023-2024 | 113 | 19/07/2023 | 19/07/2023 | WBSEDCL | 0.79 | 0 | 0 | 0
2 | HOOGHLY |  | Electrical | Source Augmentation of Bamonjol PWSS | SM/15794 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Bamonjol water supply scheme, T.W. No. I, Block: Haripal, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 2 | Junior Engineer4 | ORD/000013/2023-2024 | 1629/ED | 11/04/2023 | 10/07/2023 | ANIK & CO. | 11.41 | 11.05 | 96.91 | 40
3 | HOOGHLY |  | Hooghly Division | Source Augmentation of Bamonjol PWSS | SM/15794 | Augmentation | Construction of 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement, Boundary Wall in Proposed T.W Site, Laying rising main pipe for inter connection between T.W & Distribution For Source Augmentation of BAMONJOL Piped Water Supply Scheme under Chandannagar Sub-Division of Hooghly Division P.HE Dte. within HARIPAL Block. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000129/2023-2024 | 1472/HUG | 19/05/2023 | 18/06/2023 | GOURI ENTERPRISE | 11.8 | 11.12 | 94.21 | 100
4 | HOOGHLY |  | Hooghly Division | Source Augmentation of Bamonjol PWSS | SM/15794 | Augmentation | Repair and Renovation Works of R.C.C. Elevated Reservoir of BAMONJALPWSS under ChandannagarSub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000477/2024-2025 | 4072/HUG | 19/12/2024 | 19/03/2025 | SWARNA ENTERPRISE | 9.28 | 0 | 0 | 100
Total | [13 empty] | 33.27 | 22.17 | 66.63