## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | Source Augmentation of Paschim Joykrishnapur PWSS | SM/15795 | Augmentation | Sinking of One No Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto180 Mtr at PASCHIM JOYKRISHNAPUR PWSS of CHANDANNAGAR Sub-Division under Hooghly Division, PHE Dte. [2nd Call of WBPHE/EE/45/HUG/2022-23, Sl No-18] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000051/2023-2024 | 1203/HUG | 26/04/2023 | 26/05/2023 | GARHBETA - I UNEMPLOYED YOUTH ENGINEERS CO OPERATIVE | 12.43 | 12.09 | 97.26 | 0
2 | HOOGHLY |  | Electrical | Source Augmentation of Paschim Joykrishnapur PWSS | SM/15795 | Augmentation | Adhoc payment to WBSEDCL against Service Connection |  |  | BILL/01125/2023-2024 | null | 28/06/2023 |  | WBSEDCL | 71.17 | 0 | 0 | 0
3 | HOOGHLY |  | Electrical | Source Augmentation of Paschim Joykrishnapur PWSS | SM/15795 | Augmentation | Quotation for new service Connection of Paschim Joykrishnapur w/s scheme,Zone-2,PH No-3 Distric- Hooghly under Electrical Division PHE Dte |  |  | BILL/02004/2023-2024 | 105 | 19/07/2023 |  | WBSEDCL | 3.19 | 0 | 0 | 0
4 | HOOGHLY |  | Electrical | Source Augmentation of Paschim Joykrishnapur PWSS | SM/15795 | Augmentation | Supply, delivery and installation of voltage correcting device and other allied works for Joykrishnapur w/s scheme, P.H No.- I, Dist- Hooghly under Electrical Division, PHE Dte. |  |  | ORD/001128/2022-2023 | 727/HMSD | 24/03/2023 | 23/04/2023 | KUNAL ENTERPRISE | 3.01 | 0 | 0 | 0
5 | HOOGHLY |  | Electrical | Source Augmentation of Paschim Joykrishnapur PWSS | SM/15795 | Augmentation | Quotation of New Service Connection for Paschim Joykrishnapur W/S Scheme,Zone-I,TW No-III Block-Haripal Dist-hooghly under ED,PHE Dte. |  |  | BILL/03853/2023-2024 | 304 | 26/09/2023 |  | WBSEDCL | 10.44 | 0 | 0 | 0
6 | HOOGHLY |  | Hooghly Division | Source Augmentation of Paschim Joykrishnapur PWSS | SM/15795 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000462/2023-2024 | 3058/22/Hug | 11/10/2023 |  | Resource Division | 26.06 | 0 | 0 | 0
7 | HOOGHLY |  | Electrical | Source Augmentation of Paschim Joykrishnapur PWSS | SM/15795 | Augmentation | Car Hire Charges Bill for official use office of the Executive Engineer Howrah Mechanical Sub-Division PHED |  |  | ORD/000985/2023-2024 | 959/HMSD | 20/04/2023 | 19/04/2024 | SANJIB PRADHAN | 5 | 1.16 | 23.23 | 1
8 | HOOGHLY |  | Electrical | Source Augmentation of Paschim Joykrishnapur PWSS | SM/15795 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Paschim Joykrishnapur water supply scheme, Zone-I, T.W. No. I & Zone-II, T.W. No. I, Block: Haripal, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 2 | Junior Engineer4 | ORD/000003/2023-2024 | 1619/ED | 11/04/2023 | 10/07/2023 | STANDARD ELECTRICALS | 21.81 | 14.47 | 66.36 | 40
9 | HOOGHLY |  | Electrical | Source Augmentation of Paschim Joykrishnapur PWSS | SM/15795 | Augmentation | Hiring of 1 (one) no. Diesel luxury Taxi on contract carriage for the Office of the Assistant Engineer, Howrah Mechanical Sub Division, PHE Dte (JJM Work for Howrah District). | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer5 | ORD/001901/2023-2024 | 3112/HMSD | 22/11/2023 | 05/06/2024 | SIDDHARTHA CHATTERJEE. | 0.93 | 0 | 0 | 60
10 | HOOGHLY |  | Electrical | Source Augmentation of Paschim Joykrishnapur PWSS | SM/15795 | Augmentation | Hiring of 1 (one) no. Diesel luxury Taxi on contract carriage for the Office of the Assistant Engineer, Howrah Mechanical Sub Division, PHE Dte (JJM Work for Hooghly District). | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/001104/2023-2024 | 2830/HMSD | 30/10/2023 | 29/04/2024 | SANJIB PRADHAN | 0.86 | 0 | 0 | 42
11 | HOOGHLY |  | Hooghly Division | Source Augmentation of Paschim Joykrishnapur PWSS | SM/15795 | Augmentation | Sinking of 5 nos. 300 X200 mm dia Tube Well 210 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) For AUGMENTATION Of Olipur,Kulteghori,Paschim Jaykrishnapur & Barakamalpur W/S Scheme under Chandannagar Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000213/2023-2024 | 1839/HUG | 26/06/2023 | 10/08/2023 | GARHBETA - I UNEMPLOYED YOUTH ENGINEERS CO OPERATIVE | 80.45 | 14.39 | 17.89 | 100
Total | [13 empty] | 235.35 | 42.12 | 17.9