## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | Source Augmentation of Malia PWSS | SM/15796 | Augmentation | Sinking of One No Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto180 Mtr at MALIA PWSS of CHANDANNAGAR Sub-Division under Hooghly Division, PHE Dte. [2nd Call of WBPHE/EE/45/HUG/2022-23, Sl No-17] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000050/2023-2024 | 1202/HUG | 26/04/2023 | 26/05/2023 | GARHBETA - I UNEMPLOYED YOUTH ENGINEERS CO OPERATIVE | 12.43 | 11.93 | 96.02 | 0
2 | HOOGHLY |  | Electrical | Source Augmentation of Malia PWSS | SM/15796 | Augmentation | Supply & Delivery of S/P/M for Malia W/S. Sch. PH-III, Hooghly | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/001224/2021-2022 | 863/HMSD | 13/05/2021 | 11/08/2021 | DEY ENTERPRISE | 0.51 | 0.51 | 100 | 0
3 | HOOGHLY |  | Electrical | Source Augmentation of Malia PWSS | SM/15796 | Augmentation | Supply, Delivery & Installation of automatic chlorinator for Malia W/S. Sch. PH-III | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/001227/2021-2022 | 862/HMSD | 13/05/2021 | 11/08/2021 | DEY ENTERPRISE | 0.71 | 0.71 | 100 | 0
4 | HOOGHLY |  | Electrical | Source Augmentation of Malia PWSS | SM/15796 | Augmentation | Internal Electrification & allied works at Malia W/S. Sch. PH-III Hooghly | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/001228/2021-2022 | 861/HMSD | 13/05/2021 | 11/08/2021 | DEY ENTERPRISE | 0.59 | 0.59 | 100 | 0
5 | HOOGHLY |  | Electrical | Source Augmentation of Malia PWSS | SM/15796 | Augmentation | Supply, Installation of MCC panel & allied works at Malia W/S. Sch. PH-III Hooghly | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000187/2020-2021 | 503/HMSD | 12/03/2021 | 10/06/2021 | DEY ENTERPRISE | 2.7 | 2.7 | 100 | 0
6 | HOOGHLY |  | Electrical | Source Augmentation of Malia PWSS | SM/15796 | Augmentation | Supply, Delivery & Installation of actuor operated butterfly valve for Malia W/S. Sch. PH-III | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/001226/2021-2022 | 865/HMSD | 13/05/2021 | 11/08/2021 | DEY ENTERPRISE | 1 | 1 | 100 | 0
7 | HOOGHLY |  | Electrical | Source Augmentation of Malia PWSS | SM/15796 | Augmentation | Supply, Delivery & Installation of voltage correcting device & other allied works for Malia W/S. Sch. PH-III | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000188/2020-2021 | 322/HMSD | 15/02/2021 | 16/05/2021 | DEY ENTERPRISE | 1.7 | 1.7 | 100 | 0
8 | HOOGHLY |  | Electrical | Source Augmentation of Malia PWSS | SM/15796 | Augmentation | Supply & Delivery of electro-mechanical equipments & Installation of S/P/M & other allied works for Malia W/S. Sch. PH-III, Hooghly | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/001225/2021-2022 | 864/HMSD | 13/05/2021 | 11/08/2021 | DEY ENTERPRISE | 0.72 | 0.72 | 100 | 0
9 | HOOGHLY |  | Hooghly Division | Source Augmentation of Malia PWSS | SM/15796 | Augmentation | Construction of 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement, Boundary Wall in Proposed T.W Site, Laying rising main pipe for inter connection between T.W & Distribution For Source Augmentation of MALIA Piped Water Supply Scheme under Chandannagar Sub-Division of Hooghly Division P.HE Dte. within HARIPAL Block. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000130/2023-2024 | 1473/HUG | 19/05/2023 | 18/06/2023 | SUDIPTA SINHA | 11.92 | 10.71 | 89.89 | 98
10 | HOOGHLY |  | Electrical | Source Augmentation of Malia PWSS | SM/15796 | Augmentation | Supply ,delivery & installation of Voltage correcting device and other allied works for Malia water supply scheme, P.H. No.- III, District - Hooghly under Electrical Division, PHE Dte. |  |  | BILL/00879/2022-2023 |  | 28/02/2023 | 28/02/2023 | DEY ENTERPRISE | 1.7 | 0 | 0 | 0
11 | HOOGHLY |  | Electrical | Source Augmentation of Malia PWSS | SM/15796 | Augmentation | Supply & delivery of submersible pumping machinery for Malia water supply scheme, P.H. No.- III, District - Hooghly under Electrical Division, PHE Dte. |  |  | BILL/00873/2022-2023 |  | 28/02/2023 | 28/02/2023 | DEY ENTERPRISE | 0.51 | 0 | 0 | 0
12 | HOOGHLY |  | Electrical | Source Augmentation of Malia PWSS | SM/15796 | Augmentation | Supply ,delivery & installation of Actuator operated butterfly valve for for Malia water supply scheme, P.H. No.- III, District - Hooghly under Electrical Division, PHE Dte. |  |  | BILL/00878/2022-2023 |  | 28/02/2023 | 28/02/2023 | DEY ENTERPRISE | 1 | 0 | 0 | 0
13 | HOOGHLY |  | Electrical | Source Augmentation of Malia PWSS | SM/15796 | Augmentation | Internal electrification and works at Malia water supply scheme, P.H. No.- III, District - Hooghly under Electrical Division, PHE Dte. |  |  | BILL/00881/2022-2023 |  | 28/02/2023 | 28/02/2023 | DEY ENTERPRISE | 0.59 | 0 | 0 | 0
14 | HOOGHLY |  | Electrical | Source Augmentation of Malia PWSS | SM/15796 | Augmentation | Supply & Delivery of S/P/M for Malia W/S. Sch. PH-III |  |  | BILL/00870/2022-2023 |  | 28/02/2023 | 28/02/2023 | DEY ENTERPRISE | 0.51 | 0 | 0 | 0
15 | HOOGHLY |  | Electrical | Source Augmentation of Malia PWSS | SM/15796 | Augmentation | Supply & installation of MCC Panel & allied works at Malia water supply scheme, P.H. No.- III, District - Hooghly under Electrical Division, PHE Dte. |  |  | BILL/00875/2022-2023 |  | 28/02/2023 | 28/02/2023 | DEY ENTERPRISE | 2.7 | 0 | 0 | 0
16 | HOOGHLY |  | Electrical | Source Augmentation of Malia PWSS | SM/15796 | Augmentation | Supply & installation of Automatic Chlorinator at Malia water supply scheme, P.H. No.- III, District - Hooghly under Electrical Division, PHE Dte. |  |  | BILL/00880/2022-2023 |  | 28/02/2023 | 28/02/2023 | DEY ENTERPRISE | 0.71 | 0 | 0 | 0
17 | HOOGHLY |  | Electrical | Source Augmentation of Malia PWSS | SM/15796 | Augmentation | Supply & delivery of electro-mechanical equipments and installation of submersible pumping machinery & other allied works for Malia water supply scheme, P.H. No.- III, District - Hooghly under Electrical Division, PHE Dte. |  |  | BILL/00877/2022-2023 |  | 28/02/2023 | 28/02/2023 | DEY ENTERPRISE | 0.72 | 0 | 0 | 0
18 | HOOGHLY |  | Electrical | Source Augmentation of Malia PWSS | SM/15796 | Augmentation | Quotation of New Service Connection of Malia W/S Scheme(Aug) T.W No-4 District-Hooghly under Electrical Division PHE Dte |  |  | BILL/01997/2023-2024 | 114 | 19/07/2023 | 19/07/2023 | WBSEDCL | 2.28 | 0 | 0 | 0
19 | HOOGHLY |  | Electrical | Source Augmentation of Malia PWSS | SM/15796 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Malia water supply scheme, T.W. No. I, Block: Haripal, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 2 | Junior Engineer4 | ORD/000002/2023-2024 | 1618/ED | 11/04/2023 | 10/07/2023 | A.S. ENTERPRISE | 10.71 | 10.69 | 99.83 | 50
Total | [13 empty] | 53.7 | 41.26 | 76.84