## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF SANKHANAGAR CHAKBASNBERIA W/S SCHEME UNDER CHINSURAH MAGRA BLOCK | SM/15797 | Augmentation | Construction of 2 Nos. 3.6 m X 3.0 m Switch Room with Additional Plinth Height, with Sanitary and Water Supply arrangement, Laying of C.I/D.I pipes & specials for connection of Proposed 2 nos. T.W with distribution system, FHTC of SHANKHANAGAR CHAK BANSBERIA W/S Scheme under Chinsurah Sub - Division P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000185/2023-2024 | 1772/HUG | 15/06/2023 | 30/07/2023 | SURAJIT SINGHA RAY | 40.36 | 9.51 | 23.56 | 45
2 | HOOGHLY |  | Electrical | SOURCE AUGMENTATION OF SANKHANAGAR CHAKBASNBERIA W/S SCHEME UNDER CHINSURAH MAGRA BLOCK | SM/15797 | Augmentation | Supply, delivery and installation of voltage correcting device and other allied works for Sankhanagar Chawk Bansberia w/s scheme, P.H No.- II, Dist- Hooghly under Electrical Division, PHE Dte. |  |  | ORD/000315/2022-2023 | 491/HMSD | 02/03/2023 | 01/04/2023 | S.B.ENTERPRISE | 2.49 | 2.49 | 100 | 1
3 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF SANKHANAGAR CHAKBASNBERIA W/S SCHEME UNDER CHINSURAH MAGRA BLOCK | SM/15797 | Augmentation | Emmergency Reparing work of Different Dia Ditribution Pipeline under Chakbasberia water supply scheme under Chinsurah Sub Divusion undre Hooghly Division PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000525/2023-2024 | 822/CH | 31/08/2023 | 15/09/2023 | MAA BUNAMATA ENTERPRISE | 0.63 | 0.63 | 99.82 | 95
4 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF SANKHANAGAR CHAKBASNBERIA W/S SCHEME UNDER CHINSURAH MAGRA BLOCK | SM/15797 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000545/2023-2024 | 3059/24/Hug | 11/10/2023 | 11/10/2023 | Resource Division | 1.85 | 0 | 0 | 0
5 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF SANKHANAGAR CHAKBASNBERIA W/S SCHEME UNDER CHINSURAH MAGRA BLOCK | SM/15797 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000355/2023-2024 | 3004/8/Hug | 05/10/2023 | 05/10/2023 | Resource Division | 37.77 | 0 | 0 | 0
6 | HOOGHLY |  | Electrical | SOURCE AUGMENTATION OF SANKHANAGAR CHAKBASNBERIA W/S SCHEME UNDER CHINSURAH MAGRA BLOCK | SM/15797 | Augmentation | Quotation Bill for New Service Connection at Sankhanagar Chak Bansberia W/S. Sch. TW-I |  |  | BILL/04090/2023-2024 | 355 | 12/10/2023 | 12/10/2023 | WBSEDCL | 6.63 | 0 | 0 | 0
7 | HOOGHLY |  | Electrical | SOURCE AUGMENTATION OF SANKHANAGAR CHAKBASNBERIA W/S SCHEME UNDER CHINSURAH MAGRA BLOCK | SM/15797 | Augmentation | Quotation for new service connection at Sankhanagar Chakbansberia W/S Sch. , T/W No. - I(Aug.), Block - Chinsurah- Mogra, Dist. - Hooghly |  |  | BILL/04082/2023-2024 |  | 10/10/2023 | 10/10/2023 | WBSEDCL | 6.63 | 0 | 0 | 0
8 | HOOGHLY |  | Electrical | SOURCE AUGMENTATION OF SANKHANAGAR CHAKBASNBERIA W/S SCHEME UNDER CHINSURAH MAGRA BLOCK | SM/15797 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Sankhanagar & Chakbasnberia water supply scheme, T.W. No. I, Block: Chinsurah-Magra, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 2 | Junior Engineer4 | ORD/000022/2023-2024 | 1699/ED | 18/04/2023 | 17/07/2023 | EMCON | 11.4 | 11.4 | 99.96 | 80
9 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF SANKHANAGAR CHAKBASNBERIA W/S SCHEME UNDER CHINSURAH MAGRA BLOCK | SM/15797 | Augmentation | Sinking of Six Nos. Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto180 Mtr at SHIBRAI(2NOS.), SHANKHANAGAR CHAK BANSBERIA(2NOS.), BAKULIA ZONE-I(2NOS.) PWSS of CHINSURAH Sub-Division under Hooghly Division, PHE Dte. [3rd Call of WBPHE/EE/77/HUG/2022-23, Sl No-2] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000160/2023-2024 | 1618/HUG | 02/06/2023 | 17/07/2023 | GARHBETA - I UNEMPLOYED YOUTH ENGINEERS CO OPERATIVE | 72.85 | 23.77 | 32.63 | 65
10 | HOOGHLY |  | Electrical | SOURCE AUGMENTATION OF SANKHANAGAR CHAKBASNBERIA W/S SCHEME UNDER CHINSURAH MAGRA BLOCK | SM/15797 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Sankhanagar Chakbansberia (Replacement) water supply scheme, T.W. No. I, Block: Chinsura-Mogra, District - Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 2 | Junior Engineer4 | ORD/001388/2023-2024 | 4738/ED | 15/12/2023 | 14/03/2024 | S. DUTTA | 10.74 | 10.46 | 97.4 | 90
11 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF SANKHANAGAR CHAKBASNBERIA W/S SCHEME UNDER CHINSURAH MAGRA BLOCK | SM/15797 | Augmentation | Laying HDPE Pipeline From existing existing Distribution System for providing FHTC of Chakbansberia W/S Scheme under Chinsurah Sub - Division under Hooghly Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000735/2023-2024 | 27/CH | 05/01/2024 | 20/01/2024 | SURAJIT SINGHA RAY | 4.8 | 1.27 | 26.48 | 60
Total | [13 empty] | 196.16 | 59.53 | 30.35