## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF GURAP W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/15798 | Augmentation | Laying Rising main with necessary interconnection with T.W., OHR & Distribution System & Repairing works of 1st Pump House, Boundary Wall & Go-down Room for Gurap Water Supply Scheme Under Chinsurah Sub-Division. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000025/2023-2024 | 1108/HUG | 17/04/2023 | 17/05/2023 | GOBINDA MAITY | 16.16 | 0 | 0 | 100
2 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF GURAP W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/15798 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000357/2023-2024 | 3004/18/Hug | 05/10/2023 | 05/10/2023 | Resource Division | 37.77 | 0 | 0 | 0
3 | HOOGHLY |  | Electrical | SOURCE AUGMENTATION OF GURAP W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/15798 | Augmentation | New Service connection quotation charges for ph-4 Gurap pwss |  |  | BILL/04473/2023-2024 | 523 | 12/12/2023 | 12/12/2023 | WBSEDCL | 10.02 | 0 | 0 | 0
4 | HOOGHLY |  | Electrical | SOURCE AUGMENTATION OF GURAP W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/15798 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Gurap water supply scheme, T.W. No. I, Block: Dhaniakhali, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer1 | ORD/000017/2023-2024 | 1633/ED | 11/04/2023 | 10/07/2023 | DITHI ENTERPRISE | 11.4 | 0 | 0 | 70
5 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF GURAP W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/15798 | Augmentation | Sinking of Six Nos. Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto180 Mtr at DHARAMPUR, BADINAN, BHASTARA, KOLA, PATNABHAIRABPUR, GURAP PWSS of CHINSURAH Sub-Division under Hooghly Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000787/2022-2023 | 882/HUG | 27/03/2023 | 11/05/2023 | AUXILIARY TUBEWELL DRILLERS | 75.1 | 0 | 0 | 65
6 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF GURAP W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/15798 | Augmentation | Laying UPVC Pipeline for Proper Drainage of Washout / Overflow Water to Nearby Pond & Replacement Of Damaged Sluice Valve At Head Works Site For Gurap Piped Water Supply Scheme Under Dhaniakhali Block Of Chinsurah Sub-Division Under Hooghly Division, Phe Dte. | Assistant Engineer (Civil) |  | ORD/002523/2024-2025 | 314/CH | 21/02/2025 | 08/03/2025 | ARUN SEAL AND CO. | 3.13 | 0 | 0 | 0
7 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF GURAP W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/15798 | Augmentation | REPAIRING & RENOVATION OF SWITCH ROOM INCLUDING BOUNDARY WALL AT HEAD WORKS SITE OF GURAP WATER SUPPLY SCHEME UNDER DHANIAKHALI BLOCK OF CHINSURAH SUB-DIVISION UNDER HOOGHLY DIVISION, PHE DTE. | Assistant Engineer (Civil) |  | ORD/001466/2024-2025 | 130/CH | 29/01/2025 | 08/02/2025 | ARUN SEAL AND CO. | 4.83 | 0 | 0 | 0
Total | [13 empty] | 158.41 | 0 | 0