## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Electrical | SOURCE AUGMENTATION OF BADINAN PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK | SM/15799 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Badinan water supply scheme, T.W. No. II, Block: Polba-Dadpur, District- Hooghly under Electrical Division, PHE Dte. |  |  | ORD/000864/2023-2024 | 3436/ED | 11/08/2023 | 09/11/2023 | BIDYUT KUMAR MUKHERJEE | 11.41 | 0 | 0 | 0
2 | HOOGHLY |  | Electrical | SOURCE AUGMENTATION OF BADINAN PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK | SM/15799 | Augmentation | Additional Quotation for new service connection at Badinan w/s sch. , P.H. No. III, Dist -Hooghly |  |  | BILL/00750/2023-2024 | 37 | 15/05/2023 | 15/05/2023 | WBSEDCL | 0.48 | 0 | 0 | 0
3 | HOOGHLY |  | Electrical | SOURCE AUGMENTATION OF BADINAN PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK | SM/15799 | Augmentation | Quatation bill for New service connection at Aug. of Badinan w/s scheme, P.H No.-3 |  |  | BILL/00871/2022-2023 | 176 | 02/03/2023 | 02/03/2023 | WBSEDCL | 4.74 | 0 | 0 | 0
4 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF BADINAN PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK | SM/15799 | Augmentation | Preparation of DPR for Augmentation Hanral Z-I Piped Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. [Block-POLBA DADPUR]. | Assistant Engineer (Civil) |  | ORD/000075/2024-2025 | 690/CH | 09/08/2024 | 16/08/2024 | APEX ENGINEERING | 3.88 | 0 | 0 | 0
5 | HOOGHLY |  | Electrical | SOURCE AUGMENTATION OF BADINAN PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK | SM/15799 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Badinan water supply scheme, T.W. No. III, Block: Polba-Dadpur, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 2 | Junior Engineer4 | ORD/000124/2022-2023 | 3480/ED | 30/12/2022 | 30/03/2023 | INDIA ENTERPRISE | 10.64 | 10.3 | 96.79 | 90
6 | HOOGHLY |  | Electrical | SOURCE AUGMENTATION OF BADINAN PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK | SM/15799 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Badinan water supply scheme, T.W. No. I, Block: Polba-Dadpur, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 2 | Junior Engineer4 | ORD/000012/2023-2024 | 1628/ED | 11/04/2023 | 10/07/2023 | BIDYUT KUMAR MUKHERJEE | 11.41 | 11.4 | 99.88 | 99
7 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF BADINAN PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK | SM/15799 | Augmentation | Construction of 2 Nos. 3.6 m X 3.0 m Switch Room with Additional Plinth Height, with Sanitary and Water Supply arrangement, Laying of C.I/D.I pipes & specials for connection of Proposed 2 nos.T.W with distribution system, FHTC of BADINAN W/S Scheme under Chinsurah Sub - Division P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000082/2023-2024 | 1337/HUG | 11/05/2023 | 25/06/2023 | BAKSHI ENTERPRISE | 40.42 | 35.48 | 87.77 | 45
8 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF BADINAN PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK | SM/15799 | Augmentation | Sinking of 1 (One) No Big dia tube well (300 mm x200mm) with supply of PVC Pipe and strainer and having depth upto 180 Mtr at BADINAN W/S Scheme under Chinsurah Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000603/2023-2024 | 3318/HUG | 10/11/2023 | 10/12/2023 | AUXILIARY TUBEWELL DRILLERS | 14.88 | 13.06 | 87.79 | 100
9 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF BADINAN PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK | SM/15799 | Augmentation | Providing FHTC at the left out portions of Priyanagar for proiving FHTC in Badinan Piped Water Supply Scheme under Polba Dapur Block of Chinsurah Sub-Division under Hooghly Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000037/2024-2025 | 539/CH | 14/06/2024 | 21/06/2024 | BIMAL KUMAR HALDER | 4.84 | 4.84 | 99.94 | 85
10 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF BADINAN PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK | SM/15799 | Augmentation | Providing FHTC at the left out portions of Payan majipara for proiving FHTC in Badinan Piped Water Supply Scheme under Polba Dapur Block of Chinsurah Sub-Division under Hooghly Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000036/2024-2025 | 538/CH | 14/06/2024 | 21/06/2024 | BIMAL KUMAR HALDER | 4.84 | 4.84 | 99.91 | 100
11 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF BADINAN PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK | SM/15799 | Augmentation | Providing FHTC at the left out portions at Itkhola for proiving FHTC in Badinan Piped Water Supply Scheme under Polba Dapur Block of Chinsurah Sub-Division under Hooghly Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000035/2024-2025 | 537/CH | 14/06/2024 | 21/06/2024 | BIMAL KUMAR HALDER | 2.81 | 2.81 | 99.95 | 100
12 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF BADINAN PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK | SM/15799 | Augmentation | Repairing Of Switch Room, Boundary wall for Badinan W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte., Dist. Hooghly. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000061/2024-2025 | 2408/HUG | 26/06/2024 | 26/07/2024 | GHOSH CONSTRUCTION | 7.86 | 7.83 | 99.62 | 100
13 | HOOGHLY |  | Electrical | SOURCE AUGMENTATION OF BADINAN PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK | SM/15799 | Augmentation | Quotation Bill for New Service Connection at Badinan W/S. Sch. TW-I |  |  | BILL/04640/2023-2024 | 632 | 08/01/2024 | 08/01/2024 | WBSEDCL | 5.16 | 0 | 0 | 0
14 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF BADINAN PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK | SM/15799 | Augmentation | Sinking of Six Nos. Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto180 Mtr at DHARAMPUR, BADINAN, BHASTARA, KOLA, PATNABHAIRABPUR, GURAP PWSS of CHINSURAH Sub-Division under Hooghly Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000787/2022-2023 | 882/HUG | 27/03/2023 | 11/05/2023 | AUXILIARY TUBEWELL DRILLERS | 75.1 | 0 | 0 | 65
15 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF BADINAN PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK | SM/15799 | Augmentation | Laying C.I/D.I pipes & specials for rising main pipe line in between T.W No.- 4 of Badinan W/S under Chinsurah Sub - Division P.H.E. Dte. | Assistant Engineer (Civil) |  | ORD/000739/2024-2025 | 65/CH | 10/01/2025 | 15/01/2025 | BIMAL KUMAR HALDER | 0.97 | 0 | 0 | 0
Total | [13 empty] | 199.44 | 90.56 | 45.41