## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF BHASTARA PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/15800 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000358/2023-2024 | 3004/17/Hug | 05/10/2023 | 05/10/2023 | Resource Division | 35.98 | 0 | 0 | 0
2 | HOOGHLY |  | Electrical | SOURCE AUGMENTATION OF BHASTARA PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/15800 | Augmentation | New Service connection quotation charges for ph-3 Bhastara pwss |  |  | BILL/04472/2023-2024 | 521 | 12/12/2023 | 12/12/2023 | WBSEDCL | 3.8 | 0 | 0 | 0
3 | HOOGHLY |  | Electrical | SOURCE AUGMENTATION OF BHASTARA PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/15800 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Dhaniakhali water supply scheme, T.W. No.- I & II, Block: Dhaniakhali, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer1 | ORD/000206/2022-2023 | 833/ED | 14/02/2023 | 15/05/2023 | A.G. ENTERPRISE | 21.49 | 2.48 | 11.55 | 59
4 | HOOGHLY |  | Electrical | SOURCE AUGMENTATION OF BHASTARA PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/15800 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Bhastara water supply scheme, T.W. No. I & II, Block: Dhaniakhali, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 2 | Junior Engineer1 | ORD/000014/2023-2024 | 1630/ED | 11/04/2023 | 10/07/2023 | M.S ENTERPRISE | 22.83 | 11.11 | 48.69 | 50
5 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF BHASTARA PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/15800 | Augmentation | Preparation of DPR for BHASTARA Piped Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. [Block-DHANIAKHALI]. | Assistant Engineer (Civil) |  | ORD/000077/2024-2025 | 692/CH | 09/08/2024 | 16/08/2024 | APEX ENGINEERING | 4.5 | 0 | 0 | 0
6 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF BHASTARA PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/15800 | Augmentation | Construction of 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement and Boundary Wall for Augmentation of BHASTARA Piped Water Supply Scheme under Chinsurah Sub-Division of Hooghly Division P.HE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000601/2023-2024 | 3316/HUG | 10/11/2023 | 25/12/2023 | SUDIPTA DAS | 8.59 | 7.11 | 82.8 | 95
7 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF BHASTARA PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/15800 | Augmentation | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under Chinsurah Sub Division under Hooghly Division PHE Dte 1. Digra Arsenic PWSS 2. Charsundalpur Arsenic PWSS 3. Asanpur Arsenic PWSS 4. Polba (Retrofit) PWSS 5. Baastara PWSS 6. Bakulia PWSS | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000833/2023-2024 | 211/CH | 29/02/2024 | 07/03/2024 | MAA BUNAMATA ENTERPRISE | 0.95 | 0.95 | 100 | 45
8 | HOOGHLY |  | Electrical | SOURCE AUGMENTATION OF BHASTARA PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/15800 | Augmentation | New Service connection quotation charges for ph-4 Bhastara pwss |  |  | BILL/04471/2023-2024 | 522 | 12/12/2023 | 12/12/2023 | WBSEDCL | 3.73 | 0 | 0 | 0
9 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF BHASTARA PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/15800 | Augmentation | Sinking of Six Nos. Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto180 Mtr at DHARAMPUR, BADINAN, BHASTARA, KOLA, PATNABHAIRABPUR, GURAP PWSS of CHINSURAH Sub-Division under Hooghly Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000787/2022-2023 | 882/HUG | 27/03/2023 | 11/05/2023 | AUXILIARY TUBEWELL DRILLERS | 75.1 | 13.09 | 17.43 | 65
10 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF BHASTARA PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/15800 | Augmentation | Restoration & repairing of village road damaged due to laying of pipeline of piped water supply schemes under JJM in BHASTARA GP of DHANIAKHALI Block under Chinsurah Sub-Division of Hooghly Division PHE Dte. (Phase-II) | Assistant Engineer (Civil) |  | ORD/002018/2024-2025 | 315/CH | 21/02/2025 | 08/03/2025 | JOY GURU ENTERPRISE | 3.4 | 0 | 0 | 0
11 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF BHASTARA PIPED W/S SCHEME UNDER DHANIAKHALI BLOCK | SM/15800 | Augmentation | REPAIRING & RENOVATION OF SWITCH ROOM INCLUDING BOUNDARY WALL AT 2ND TW SITE OF BHASTARA WATER SUPPLY SCHEME UNDER DHANIAKHALI BLOCK OF CHINSURAH SUB-DIVISION UNDER HOOGHLY DIVISION, PHE DTE. | Assistant Engineer (Civil) |  | ORD/001464/2024-2025 | 128/CH | 29/01/2025 | 08/02/2025 | M/S B N ENTERPRISE | 4.12 | 0 | 0 | 0
Total | [13 empty] | 184.49 | 34.75 | 18.84