## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Electrical | Source Augmentation of KISHORPUR Piped Water Supply Scheme under Khanakul-I Block | SM/15802 | Augmentation | Emergency replacement of burnt submersible pump-motor set by newly supplied pump-motor set, rewinding of the burnt submersible motor, replacement of voltage corrector and related works at Kishorpur w/s scheme, P.H No-I, Dist- Hooghly. |  |  | ORD/000319/2022-2023 | 495/HMSD | 02/03/2023 | 01/04/2023 | SOMNATH ENTERPRISE | 3.58 | 3.32 | 92.75 | 100
2 | HOOGHLY |  | Electrical | Source Augmentation of KISHORPUR Piped Water Supply Scheme under Khanakul-I Block | SM/15802 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Kishorpur water supply scheme, T.W. No. I, Block: Khanakul-I, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 2 ,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000001/2023-2024 | 1617/ED | 11/04/2023 | 01/05/2025 | M/S G P ENTERPRISE | 10.74 | 7.95 | 74.04 | 20
3 | HOOGHLY |  | Hooghly Division | Source Augmentation of KISHORPUR Piped Water Supply Scheme under Khanakul-I Block | SM/15802 | Augmentation | Sinking of One No Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto150 Mtr at KISHORPUR PWSS of ARAMBAGH Sub-Division under Hooghly Division, PHE Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000108/2023-2024 | 1428/HUG | 17/05/2023 | 16/06/2023 | GARHBETA - I UNEMPLOYED YOUTH ENGINEERS CO OPERATIVE | 11.53 | 11.28 | 97.77 | 99
4 | HOOGHLY |  | Hooghly Division | Source Augmentation of KISHORPUR Piped Water Supply Scheme under Khanakul-I Block | SM/15802 | Augmentation | Construction of 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement , Boundary Wall in Proposed T.W Site,Laying rising main pipe for inter connection between T.W & Distribution For Source Augmentation of Kishorpur Piped Water Supply Scheme under Arambagh Sub-Division of Hooghly Division P.HE Dte. within KHANAKUL-I Block. | Assistant Engineer | Junior Engineer (Civill) | ORD/000143/2023-2024 | 1496/HUG | 22/05/2023 | 03/06/2025 | SUDIPTA DAS | 11.83 | 4.84 | 40.94 | 100
5 | HOOGHLY |  | Hooghly Division | Source Augmentation of KISHORPUR Piped Water Supply Scheme under Khanakul-I Block | SM/15802 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000094/2023-2024 | 1263/9/Hug | 03/05/2023 | 03/05/2023 | Resource Division | 5.69 | 0 | 0 | 0
6 | HOOGHLY |  | Hooghly Division | Source Augmentation of KISHORPUR Piped Water Supply Scheme under Khanakul-I Block | SM/15802 | Augmentation | Repair and Renovation Works of R.C.C. Elevated Reservoir, Boundary Wall, Switch Room of KISHORPUR PWSS under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. |  |  | ORD/000488/2024-2025 | 4152/HUG | 26/12/2024 | 26/03/2025 | MS PRADIP KUMAR PAL | 17.87 | 0 | 0 | 0
7 | HOOGHLY |  | Electrical | Source Augmentation of KISHORPUR Piped Water Supply Scheme under Khanakul-I Block | SM/15802 | Augmentation | Quotation Bill for New Service Connection at Kishorepur W/S. Sch. PH-III |  |  | BILL/04922/2023-2024 | 675 | 18/01/2024 | 18/01/2024 | WBSEDCL | 4.48 | 0 | 0 | 0
Total | [13 empty] | 65.72 | 27.39 | 41.67