## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | Source Augmentation of BALI Piped Water Supply Scheme under Goghat-I Block | SM/15803 | Augmentation | Sinking of One No Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto150 Mtr at BALI PWSS of ARAMBAGH Sub-Division under Hooghly Division, PHE Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000772/2022-2023 | 743/HUG | 15/03/2023 | 14/04/2023 | MAYA CONSTRUCTION | 11.32 | 0 | 0 | 100
2 | HOOGHLY |  | Electrical | Source Augmentation of BALI Piped Water Supply Scheme under Goghat-I Block | SM/15803 | Augmentation | Quotation of New Service Connection for Bali w/s Scheme, PH No-3 Block-Goghat-I,Dist-Hooghly under Electrical Division,PHE Dte.(SM/15803) Application No-5004191492 Reference Id-503647819. |  |  | BILL/00537/2024-2025 |  | 29/05/2024 | 29/05/2024 | WBSEDCL | 7.09 | 0 | 0 | 0
3 | HOOGHLY |  | Hooghly Division | Source Augmentation of BALI Piped Water Supply Scheme under Goghat-I Block | SM/15803 | Augmentation | Construction of 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement , Boundary Wall in Proposed T.W Site,Laying rising main pipe for inter connection between T.W & Distribution For Source Augmentation of BALI Piped Water Supply Scheme under Arambagh Sub-Division of Hooghly Division P.HE Dte. within Goghat-I Block. | Assistant Engineer | Junior Engineer (Civill) | ORD/000139/2023-2024 | 1492/HUG | 22/05/2023 | 11/04/2025 | P.K. GHOSH & CO. | 11.81 | 0 | 0 | 90
4 | HOOGHLY |  | Electrical | Source Augmentation of BALI Piped Water Supply Scheme under Goghat-I Block | SM/15803 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Bali water supply scheme, T.W. No. I, Block: Goghat-I, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 2 | Junior Engineer4 | ORD/001144/2022-2023 | 1496/ED | 28/03/2023 | 31/05/2025 | RUBY ENTERPRISE. | 10.75 | 0 | 0 | 30
Total | [13 empty] | 40.98 | 0 | 0