## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Electrical | Source Augmentation of PATUL Piped Water Supply Scheme under Khanakul-I Block | SM/15804 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Patul water supply scheme, T.W. No. I, Block: Khanakul-I, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 2 | Junior Engineer4 | ORD/000004/2023-2024 | 1620/ED | 11/04/2023 | 31/03/2025 | NITESH MANAGEMENT | 10.74 | 0 | 0 | 50
2 | HOOGHLY |  | Hooghly Division | Source Augmentation of PATUL Piped Water Supply Scheme under Khanakul-I Block | SM/15804 | Augmentation | Sinking of One No Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto150 Mtr at PATUL PWSS of ARAMBAGH Sub-Division under Hooghly Division, PHE Dte.. | Assistant Engineer |  | ORD/000744/2022-2023 | 655/HUG | 09/03/2023 | 08/04/2023 | R CONSTRUCTION | 11.31 | 9.95 | 87.99 | 100
3 | HOOGHLY |  | Hooghly Division | Source Augmentation of PATUL Piped Water Supply Scheme under Khanakul-I Block | SM/15804 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000100/2023-2024 | 1263/15/Hug | 03/05/2023 | 03/05/2023 | Resource Division | 5.69 | 0 | 0 | 0
4 | HOOGHLY |  | Electrical | Source Augmentation of PATUL Piped Water Supply Scheme under Khanakul-I Block | SM/15804 | Augmentation | Quotation Bill for New Service Connection at Patul W/S. Sch. Z-II, TW-I |  |  | BILL/04593/2023-2024 | 594 | 29/12/2023 | 29/12/2023 | WBSEDCL | 3.55 | 0 | 0 | 0
5 | HOOGHLY |  | Hooghly Division | Source Augmentation of PATUL Piped Water Supply Scheme under Khanakul-I Block | SM/15804 | Augmentation | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under ARAMBAGH Sub-Division under Hooghly Division PHE Dte. (i) PATUL PWSS (ii) GHOSHPUR PWSS (iii) UDNA PWSS (iv) POLE PWSS (v) GOBINDAPUR PWSS (vi) THAKURANICHAK PWSS | Assistant Engineer | Junior Engineer (Civill) | ORD/000436/2024-2025 | 800/Arg | 23/08/2024 | 30/08/2024 | LIMRA SOCIAL WELFARE SOCIETY | 0.95 | 0 | 0 | 100
Total | [13 empty] | 32.25 | 9.95 | 30.87