## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | Source Augmentation of PATUL Piped Water Supply Scheme under Khanakul-I Block | SM/15804 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000100/2023-2024 | 1263/15/Hug | 03/05/2023 | 03/05/2023 | Resource Division | 5.69 | 0 | 0 | 0
2 | HOOGHLY |  | Hooghly Division | Source Augmentation of PATUL Piped Water Supply Scheme under Khanakul-I Block | SM/15804 | Augmentation | Sinking of One No Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto150 Mtr at PATUL PWSS of ARAMBAGH Sub-Division under Hooghly Division, PHE Dte.. | Assistant Engineer |  | ORD/000744/2022-2023 | 655/HUG | 09/03/2023 | 08/04/2023 | R CONSTRUCTION | 11.31 | 0 | 0 | 100
3 | HOOGHLY |  | Electrical | Source Augmentation of PATUL Piped Water Supply Scheme under Khanakul-I Block | SM/15804 | Augmentation | Quotation Bill for New Service Connection at Patul W/S. Sch. Z-II, TW-I |  |  | BILL/04593/2023-2024 | 594 | 29/12/2023 | 29/12/2023 | WBSEDCL | 3.55 | 0 | 0 | 0
4 | HOOGHLY |  | Electrical | Source Augmentation of PATUL Piped Water Supply Scheme under Khanakul-I Block | SM/15804 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Patul water supply scheme, T.W. No. I, Block: Khanakul-I, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 2 | Junior Engineer4 | ORD/000004/2023-2024 | 1620/ED | 11/04/2023 | 31/03/2025 | NITESH MANAGEMENT | 10.74 | 0 | 0 | 50
Total | [13 empty] | 31.3 | 0 | 0