## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | Source Augmentation of RADHABALLABHPUR Piped Water Supply Scheme Under Goghat-I Block | SM/15805 | Augmentation | Sinking of One No Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto150 Mtr at RADHABALLAVPUR PWSS of ARAMBAGH Sub-Division under Hooghly Division, PHE Dte. | Assistant Engineer |  | ORD/000763/2022-2023 | 747/HUG | 15/03/2023 | 14/04/2023 | GARHBETA - I UNEMPLOYED YOUTH ENGINEERS CO OPERATIVE | 11.32 | 10.28 | 90.77 | 0
2 | HOOGHLY |  | Electrical | Source Augmentation of RADHABALLABHPUR Piped Water Supply Scheme Under Goghat-I Block | SM/15805 | Augmentation | Quotation of New Service Connection for Radhaballavpur w/s Scheme, TW No-3 Dist- Hooghly under ED,PHE Dte |  |  | BILL/02131/2023-2024 | 117 | 20/07/2023 | 20/07/2023 | WBSEDCL | 2.82 | 0 | 0 | 0
3 | HOOGHLY |  | Electrical | Source Augmentation of RADHABALLABHPUR Piped Water Supply Scheme Under Goghat-I Block | SM/15805 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Radhaballabpur water supply scheme, T.W. No. I, Block: Goghat-I, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 2 | Junior Engineer4 | ORD/000006/2023-2024 | 1622/ED | 11/04/2023 | 10/07/2023 | M/S, GHOSH ENTERPRISE | 10.74 | 10.66 | 99.22 | 40
4 | HOOGHLY |  | Hooghly Division | Source Augmentation of RADHABALLABHPUR Piped Water Supply Scheme Under Goghat-I Block | SM/15805 | Augmentation | Designing making and erection of Display Board using logo and tag line of LAND DEMARCATION OF P.H.E. Dte. to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under ARAMBAGH Sub Division under Hooghly Division PHE Dte. (1) GANESHBATI PWSS-3nos (2) AMDOBA PWSS-2nos (3) BALI PWSS- 3nos (4) RADHABALLAVPUR PWSS- 3nos (5) RAMNAGAR PWSS-3 nos | Assistant Engineer | Junior Engineer (Civill) | ORD/000418/2024-2025 | 818/Arg | 23/08/2024 | 31/12/2024 | DHIRENDRA ENGINEERING & CONSTRUCTION | 0.98 | 0.21 | 21.43 | 100
5 | HOOGHLY |  | Hooghly Division | Source Augmentation of RADHABALLABHPUR Piped Water Supply Scheme Under Goghat-I Block | SM/15805 | Augmentation | Construction of 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement , Boundary Wall in Proposed T.W Site,Laying rising main pipe for inter connection between T.W & Distribution For Source Augmentation of RADHABALLAVPUR Piped Water Supply Scheme under Arambagh Sub-Division of Hooghly Division P.HE Dte. within Goghat-I Block. | Assistant Engineer | Junior Engineer (Civill) | ORD/000145/2023-2024 | 1498/HUG | 22/05/2023 | 11/04/2025 | P.K. GHOSH & CO. | 11.83 | 7.91 | 66.9 | 85
Total | [13 empty] | 37.7 | 29.06 | 77.09