## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Electrical | Source Augmentation of PRATAPNAGAR Piped Water Supply Scheme under Arambag Block | SM/15807 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Pratapnagar water supply scheme, T.W. No. I & II, Block: Arambag, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 2 | Junior Engineer4 | ORD/000021/2023-2024 | 1698/ED | 18/04/2023 | 01/01/2026 | GOENKA ENTERPRISE | 20.5 | 15.17 | 74 | 10
2 | HOOGHLY |  | Hooghly Division | Source Augmentation of PRATAPNAGAR Piped Water Supply Scheme under Arambag Block | SM/15807 | Augmentation | Construction of 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement, Boundary Wall in Proposed T.W Site, Laying rising main pipe for inter connection between T.W & Distribution For Source Augmentation of PRATAPNAGAR Piped Water Supply Scheme under Arambagh Sub-Division of Hooghly Division P.HE Dte. within Arambagh Block. | Assistant Engineer | Junior Engineer (Civill) | ORD/000128/2023-2024 | 1471/HUG | 19/05/2023 | 08/06/2025 | S.B. ASSOCIATES | 11.81 | 0 | 0 | 0
3 | HOOGHLY |  | Hooghly Division | Source Augmentation of PRATAPNAGAR Piped Water Supply Scheme under Arambag Block | SM/15807 | Augmentation | Sinking of Two Nos. Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto150 Mtr at PRATAPNAGAR PWSS of ARAMBAGH Sub-Division under Hooghly Division, PHE Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000502/2023-2024 | 2862/HUG | 20/09/2023 | 14/09/2024 | B.R SUPPLIERS | 22.63 | 11.04 | 48.77 | 60
4 | HOOGHLY |  | Hooghly Division | Source Augmentation of PRATAPNAGAR Piped Water Supply Scheme under Arambag Block | SM/15807 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000247/2022-2023 | 127/19/Hug | 13/01/2023 | 13/01/2023 | Resource Division | 11.5 | 0 | 0 | 0
5 | HOOGHLY |  | Hooghly Division | Source Augmentation of PRATAPNAGAR Piped Water Supply Scheme under Arambag Block | SM/15807 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000095/2023-2024 | 1263/10/Hug | 03/05/2023 | 03/05/2023 | Resource Division | 11.38 | 0 | 0 | 0
6 | HOOGHLY |  | Electrical | Source Augmentation of PRATAPNAGAR Piped Water Supply Scheme under Arambag Block | SM/15807 | Augmentation | Quotation of New Service Connection for Pratapnagar w/s Scheme,PH No-3, Block-Arambag, Dist-Hooghly under Electrical division,PHE Dte.(SM/15807) Application No-5004254598 Reference Id-503673919 |  |  | BILL/00850/2024-2025 | 248 | 24/06/2024 | 24/06/2024 | WBSEDCL | 7.9 | 0 | 0 | 0
Total | [13 empty] | 85.71 | 26.21 | 30.58