## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Electrical | Source Augmentation of JAYKRISHNAPUR Piped Water Supply Scheme under Goghat-I Block | SM/15808 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Jaykrishnapur water supply scheme, T.W. No. I, Block: Goghat-I, District- Hooghly under Electrical Division, PHE Dte. |  |  | ORD/001150/2022-2023 | 1502/ED | 28/03/2023 | 26/06/2023 | M/S DILIP MITRA | 10.75 | 0 | 0 | 0
2 | HOOGHLY |  | Hooghly Division | Source Augmentation of JAYKRISHNAPUR Piped Water Supply Scheme under Goghat-I Block | SM/15808 | Augmentation | Laying of pipe line for left out portion within command area of Jaykrishnapur Water Supply Scheme to facilate the FHTC Under Arambagh Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000041/2023-2024 | 1170/HUG | 20/04/2023 | 20/05/2023 | SADHUKHAN ENTERPRISE | 4.76 | 0 | 0 | 0
3 | HOOGHLY |  | Hooghly Division | Source Augmentation of JAYKRISHNAPUR Piped Water Supply Scheme under Goghat-I Block | SM/15808 | Augmentation | Construction of 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement , Boundary Wall in Proposed T.W Site,Laying rising main pipe for inter connection between T.W & Distribution For Source Augmentation of Jaykrishnapur Piped Water Supply Scheme under Arambagh Sub-Division of Hooghly Division P.HE Dte. within Goghat-I Block. | Assistant Engineer | Junior Engineer (Civill) | ORD/000141/2023-2024 | 1494/HUG | 22/05/2023 | 21/06/2023 | A.R. CONSTRUCTION | 11.83 | 0 | 0 | 0
4 | HOOGHLY |  | Hooghly Division | Source Augmentation of JAYKRISHNAPUR Piped Water Supply Scheme under Goghat-I Block | SM/15808 | Augmentation | Sinking of One No Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto150 Mtr at JAYKRISHNAPUR PWSS of ARAMBAGH Sub-Division under Hooghly Division, PHE Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000774/2022-2023 | 746/hug | 15/03/2023 | 14/04/2023 | MAYA CONSTRUCTION | 11.32 | 10.58 | 93.45 | 100
5 | HOOGHLY |  | Hooghly Division | Source Augmentation of JAYKRISHNAPUR Piped Water Supply Scheme under Goghat-I Block | SM/15808 | Augmentation | Designing making and erection of Display Board using logo and tag line of LAND DEMARCATION OF P.H.E. Dte. to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under ARAMBAGH Sub Division under Hooghly Division PHE Dte. (1) ANANDAPUR PWSS-4nos (2) BHADUR(BHAGARBAND) PWSS-6nos (3) GOGHAT PWSS-2nos (4) JOYKRISHNAPUR PWSS-2nos | Assistant Engineer | Junior Engineer (Civill) | ORD/000417/2024-2025 | 816/Arg | 23/08/2024 | 31/12/2024 | DHIRENDRA ENGINEERING & CONSTRUCTION | 0.98 | 0.14 | 14.29 | 100
6 | HOOGHLY |  | Electrical | Source Augmentation of JAYKRISHNAPUR Piped Water Supply Scheme under Goghat-I Block | SM/15808 | Augmentation | Quotation of New Service Connection for Jaykrishnapur w/s Scheme,TW no-3 Block-Goghat-I Dist-Hooghly under ED,PHE Dte(SM/15808) Application No-5004009573 Reference Id-503561825 |  |  | BILL/06051/2023-2024 | 748 | 16/02/2024 | 16/02/2024 | WBSEDCL | 3.95 | 0 | 0 | 0
7 | HOOGHLY |  | Hooghly Division | Source Augmentation of JAYKRISHNAPUR Piped Water Supply Scheme under Goghat-I Block | SM/15808 | Augmentation | Repair and Renovation Works of R.C.C. Elevated Reservoir, Boundary Wall, Switch Room of JAYKRISHNAPUR PWSS under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. |  |  | ORD/000489/2024-2025 | 4153/HUG | 26/12/2024 | 26/03/2025 | BOSE ENTERPRISE (RATUL BOSE) | 11.84 | 0 | 0 | 0
8 | HOOGHLY |  | Hooghly Division | Source Augmentation of JAYKRISHNAPUR Piped Water Supply Scheme under Goghat-I Block | SM/15808 | Augmentation | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under ARAMBAGH Sub-Division under Hooghly Division PHE Dte. (i) BACHANARI PWSS (ii) KAPSIT PWSS (iii) JOY KRISHNAPUR PWSS (iv) BALI PWSS (v) LAKSHMIPUR PWSS (vi) RADHABALLAVPUR PWSS | Assistant Engineer | Junior Engineer (Civill) | ORD/000431/2024-2025 | 798/Arg | 23/08/2024 | 30/08/2024 | LIMRA SOCIAL WELFARE SOCIETY | 0.95 | 0 | 0 | 100
Total | [13 empty] | 56.39 | 10.72 | 19.01