## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | Source Augmentation of GANESHBATI Piped Water Supply Scheme under Goghat-I Block | SM/15809 | Augmentation | Sinking of Two Nos. Big Dia Tube Well (300 mm X 200 mm) with supply of UPVC pipes & Strainer having depth upto150 Mtr at GANESHBATI PWSS of ARAMBAGH Sub-Division under Hooghly Division, PHE Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000745/2022-2023 | 656/HUG | 09/03/2023 | 23/04/2023 | R CONSTRUCTION | 22.63 | 13.05 | 57.69 | 0
2 | HOOGHLY |  | Electrical | Source Augmentation of GANESHBATI Piped Water Supply Scheme under Goghat-I Block | SM/15809 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Ganeshbati water supply scheme, T.W. No. I & II, Block: Goghat-I, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 2 | Junior Engineer4 | ORD/001148/2022-2023 | 1500/ED | 28/03/2023 | 01/07/2025 | ASHUTOSH DAS & CO. | 21.49 | 0 | 0 | 30
3 | HOOGHLY |  | Hooghly Division | Source Augmentation of GANESHBATI Piped Water Supply Scheme under Goghat-I Block | SM/15809 | Augmentation | Construction of 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangment , Boundary Wall in Proposed T.W Site,Laying rising main pipe for inter connection between T.W & Distribution For Source Augmentation of GANESHBATI Piped Water Supply Scheme under Arambagh Sub-Division of Hooghly Division P.HE Dte. within Goghat-I Block. | Assistant Engineer |  | ORD/000194/2023-2024 | 1779/HUG | 15/06/2023 | 15/07/2023 | ROY ENTERPRISE | 12.01 | 0 | 0 | 0
4 | HOOGHLY |  | Hooghly Division | Source Augmentation of GANESHBATI Piped Water Supply Scheme under Goghat-I Block | SM/15809 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000249/2022-2023 | 1263/14/Hug | 03/05/2023 | 03/05/2023 | Resource Division | 11.5 | 0 | 0 | 0
5 | HOOGHLY |  | Electrical | Source Augmentation of GANESHBATI Piped Water Supply Scheme under Goghat-I Block | SM/15809 | Augmentation | Quotation for New Service Connection of Ganeshbati W/S Scheme(Aug) TW No-4 District-Hooghly under Electrical Division PHE Dte. |  |  | BILL/00754/2023-2024 | 42 | 17/05/2023 | 17/05/2023 | WBSEDCL | 3.31 | 0 | 0 | 0
6 | HOOGHLY |  | Hooghly Division | Source Augmentation of GANESHBATI Piped Water Supply Scheme under Goghat-I Block | SM/15809 | Augmentation | Repair and Renovation Works of R.C.C. Elevated Reservoir of GANESHBATI PWSS Under Arambagh Sub-Division Hooghly Division, P.H.E. Dte. |  |  | ORD/000293/2024-2025 | 3672/HUG | 13/11/2024 | 23/12/2024 | TAPAS ADHYA | 12.36 | 0 | 0 | 0
7 | HOOGHLY |  | Hooghly Division | Source Augmentation of GANESHBATI Piped Water Supply Scheme under Goghat-I Block | SM/15809 | Augmentation | Designing making and erection of Display Board using logo and tag line of LAND DEMARCATION OF P.H.E. Dte. to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under ARAMBAGH Sub Division under Hooghly Division PHE Dte. (1) GANESHBATI PWSS-3nos (2) AMDOBA PWSS-2nos (3) BALI PWSS- 3nos (4) RADHABALLAVPUR PWSS- 3nos (5) RAMNAGAR PWSS-3 nos | Assistant Engineer | Junior Engineer (Civill) | ORD/000418/2024-2025 | 818/Arg | 23/08/2024 | 31/12/2024 | DHIRENDRA ENGINEERING & CONSTRUCTION | 0.98 | 0.21 | 21.43 | 100
8 | HOOGHLY |  | Electrical | Source Augmentation of GANESHBATI Piped Water Supply Scheme under Goghat-I Block | SM/15809 | Augmentation | Quotation of New Service Connection for Ganeshbati w/s Scheme,PH No-III,Block-Goghat-I,Dist-Hooghly under Electrical Division,PHE Dte.(SM/15809) Application No-5004967642 Reference Id-504132130 |  |  | BILL/04643/2025-2026 |  | 01/12/2025 | 01/12/2025 | WBSEDCL | 12.17 | 0 | 0 | 0
Total | [13 empty] | 96.44 | 13.26 | 13.75