## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | Source Augmentation of SHYAMBALLAVPUR Piped Water Supply Scheme Under Goghat-I Block | SM/15810 | Augmentation | Sinking of One No Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto150 Mtr at SHYAMBALLAVPUR PWSS of ARAMBAGH Sub-Division under Hooghly Division, PHE Dte. | Assistant Engineer |  | ORD/000743/2022-2023 | 654/HUG | 09/03/2023 | 08/04/2023 | GARHBETA - I UNEMPLOYED YOUTH ENGINEERS CO OPERATIVE | 11.32 | 9.65 | 85.23 | 0
2 | HOOGHLY |  | Hooghly Division | Source Augmentation of SHYAMBALLAVPUR Piped Water Supply Scheme Under Goghat-I Block | SM/15810 | Augmentation | Construction of Boundary wall, land development, Internal Pathway at Head Work site of Shyamballavpur W/S Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. |  |  | ORD/000294/2019-2020 | 208/HUG | 04/02/2020 | 05/03/2020 | MOHANLAL CHATTERJEE | 15.28 | 0 | 0 | 0
3 | HOOGHLY |  | Electrical | Source Augmentation of SHYAMBALLAVPUR Piped Water Supply Scheme Under Goghat-I Block | SM/15810 | Augmentation | Adhoc payment to WBSEDCL against Service Connection |  |  | BILL/01125/2023-2024 | null | 28/06/2023 |  | WBSEDCL | 71.17 | 0 | 0 | 0
4 | HOOGHLY |  | Electrical | Source Augmentation of SHYAMBALLAVPUR Piped Water Supply Scheme Under Goghat-I Block | SM/15810 | Augmentation | Quotation of New Service Connection for Shyamballavpur w/s Scheme,TW No-3,Dist-Hooghly under ED,PHE Dte |  |  | BILL/02132/2023-2024 | 122 | 20/07/2023 |  | WBSEDCL | 4.38 | 0 | 0 | 0
5 | HOOGHLY |  | Hooghly Division | Source Augmentation of SHYAMBALLAVPUR Piped Water Supply Scheme Under Goghat-I Block | SM/15810 | Augmentation | Construction of 450 m3 capacity R.C.C. OHR with 20 m staging height including RCC Pile foundation as per departmental type drawing, design & specification, pipeline connection and cost of pipes, specials alongwith Laying Distribution System & Construction of Switch Room 5.40M x 3.65M with additional plinth height, sanitary & water supply arrangement at Head works site for SHYAMBALLAVPUR and adjoining mouzas W/S Scheme under Arambagh Sub-Division. P.H.E. Dte., Dist. Hooghly. |  |  | ORD/000293/2019-2020 | 1018/Hug | 11/06/2019 | 07/03/2020 | MOHANLAL CHATTERJEE | 255 | 9.21 | 3.61 | 95
6 | HOOGHLY |  | Electrical | Source Augmentation of SHYAMBALLAVPUR Piped Water Supply Scheme Under Goghat-I Block | SM/15810 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Shyamballavpur water supply scheme, T.W. No. I, Block: Goghat-I, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 2 | Junior Engineer4 | ORD/000008/2023-2024 | 1624/ED | 11/04/2023 | 10/07/2023 | S.G.-ENTERPRISE | 10.73 | 5.32 | 49.58 | 40
7 | HOOGHLY |  | Hooghly Division | Source Augmentation of SHYAMBALLAVPUR Piped Water Supply Scheme Under Goghat-I Block | SM/15810 | Augmentation | Construction of 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement, Boundary Wall in Proposed T.W Site, Laying rising main pipe for inter connection between T.W & Distribution For Source Augmentation of SHYAMBALLAVPUR Piped Water Supply Scheme under Arambagh Sub-Division of Hooghly Division P.HE Dte. within Goghat-I Block. | Assistant Engineer | Junior Engineer (Civill) | ORD/000077/2023-2024 | 1311/HUG | 10/05/2023 | 01/10/2024 | MUNSHI TAJUDDIN | 11.82 | 1.99 | 16.87 | 90
Total | [13 empty] | 379.71 | 26.17 | 6.89