## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Electrical | Source Augmentation of KANPUR Piped Water Supply Scheme under Arambag Block | SM/15811 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Kanpur water supply scheme, T.W. No. I, Block: Arambag, District- Hooghly under Electrical Division, PHE Dte. |  |  | ORD/001151/2022-2023 | 1503/ED | 28/03/2023 | 26/06/2023 | BISALAXMI ENTERPRISE | 10.73 | 0 | 0 | 0
2 | HOOGHLY |  | Hooghly Division | Source Augmentation of KANPUR Piped Water Supply Scheme under Arambag Block | SM/15811 | Augmentation | Construction of 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement , Boundary Wall in Proposed T.W Site,Laying rising main pipe for inter connection between T.W & Distribution For Source Augmentation of Kanpur Piped Water Supply Scheme under Arambagh Sub-Division of Hooghly Division P.HE Dte. within Arambagh Block. | Assistant Engineer | Junior Engineer (Civill) | ORD/000142/2023-2024 | 1495/HUG | 22/05/2023 | 21/06/2023 | SONAR BANGLA ENTERPRISE | 11.78 | 0 | 0 | 0
3 | HOOGHLY |  | Hooghly Division | Source Augmentation of KANPUR Piped Water Supply Scheme under Arambag Block | SM/15811 | Augmentation | Sinking of One No Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto150 Mtr at KANPUR PWSS of ARAMBAGH Sub-Division under Hooghly Division, PHE Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000107/2023-2024 | 1427/HUG | 17/05/2023 | 16/06/2023 | GARHBETA - I UNEMPLOYED YOUTH ENGINEERS CO OPERATIVE | 11.53 | 0 | 0 | 0
4 | HOOGHLY |  | Hooghly Division | Source Augmentation of KANPUR Piped Water Supply Scheme under Arambag Block | SM/15811 | Augmentation | Repair and Renovation Works of R.C.C. Elevated Reservoir for KANPUR PWSS Under Arambagh Sub Division Hooghly Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/002980/2024-2025 | 3778HUG | 25/11/2024 | 04/01/2025 | MAA JAGADHATRI CONSTRUCTION | 10.4 | 0 | 0 | 0
Total | [13 empty] | 44.45 | 0 | 0