## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | Source Augmentation of DAKSHIN RASULPUR Piped Water Supply Scheme under Arambag Block | SM/15812 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000242/2022-2023 | 127/07/Hug | 13/01/2023 |  | Resource Division | 11.35 | 0 | 0 | 0
2 | HOOGHLY |  | Electrical | Source Augmentation of DAKSHIN RASULPUR Piped Water Supply Scheme under Arambag Block | SM/15812 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Dakshin Rasulpur water supply scheme, T.W. No. I, Block: Arambag, District- Hooghly under Electrical Division, PHE Dte. |  |  | ORD/001147/2022-2023 | 1499/ED | 28/03/2023 | 26/06/2023 | KARUNAMOY ENGINEERING | 10.74 | 0 | 0 | 0
3 | HOOGHLY |  | Hooghly Division | Source Augmentation of DAKSHIN RASULPUR Piped Water Supply Scheme under Arambag Block | SM/15812 | Augmentation | Construction of 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement , Boundary Wall in Proposed T.W Site,Laying rising main pipe for inter connection between T.W & Distribution For Source Augmentation of DAKSHIN RASULPUR Piped Water Supply Scheme under Arambagh Sub-Division of Hooghly Division P.HE Dte. within Arambagh Block. | Assistant Engineer | Junior Engineer (Civill) | ORD/000140/2023-2024 | 1493/HUG | 22/05/2023 | 21/06/2023 | SHREEOM ENTERPRISE | 12.1 | 0 | 0 | 0
4 | HOOGHLY |  | Electrical | Source Augmentation of DAKSHIN RASULPUR Piped Water Supply Scheme under Arambag Block | SM/15812 | Augmentation | Adhoc Payment to WBSEDCL against Service Connection |  |  | BILL/01124/2023-2024 | null | 28/06/2023 |  | WBSEDCL | 89.37 | 0 | 0 | 0
Total | [13 empty] | 123.56 | 0 | 0