## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Electrical | Source Augmentation of DAKSHIN RASULPUR Piped Water Supply Scheme under Arambag Block | SM/15812 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Dakshin Rasulpur water supply scheme, T.W. No. I, Block: Arambag, District- Hooghly under Electrical Division, PHE Dte. |  |  | ORD/001147/2022-2023 | 1499/ED | 28/03/2023 | 26/06/2023 | KARUNAMOY ENGINEERING | 10.74 | 0 | 0 | 0
2 | HOOGHLY |  | Hooghly Division | Source Augmentation of DAKSHIN RASULPUR Piped Water Supply Scheme under Arambag Block | SM/15812 | Augmentation | Construction of 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement , Boundary Wall in Proposed T.W Site,Laying rising main pipe for inter connection between T.W & Distribution For Source Augmentation of DAKSHIN RASULPUR Piped Water Supply Scheme under Arambagh Sub-Division of Hooghly Division P.HE Dte. within Arambagh Block. | Assistant Engineer | Junior Engineer (Civill) | ORD/000140/2023-2024 | 1493/HUG | 22/05/2023 | 21/06/2023 | SHREEOM ENTERPRISE | 12.1 | 0 | 0 | 0
3 | HOOGHLY |  | Hooghly Division | Source Augmentation of DAKSHIN RASULPUR Piped Water Supply Scheme under Arambag Block | SM/15812 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000242/2022-2023 | 127/07/Hug | 13/01/2023 | 13/01/2023 | Resource Division | 11.35 | 0 | 0 | 0
4 | HOOGHLY |  | Hooghly Division | Source Augmentation of DAKSHIN RASULPUR Piped Water Supply Scheme under Arambag Block | SM/15812 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000091/2023-2024 | 1263/6/Hug | 03/05/2023 | 03/05/2023 | Resource Division | 9.76 | 0 | 0 | 0
5 | HOOGHLY |  | Hooghly Division | Source Augmentation of DAKSHIN RASULPUR Piped Water Supply Scheme under Arambag Block | SM/15812 | Augmentation | Designing making and erection of Display Board using logo and tag line of LAND DEMARCATION OF P.H.E. Dte. to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under ARAMBAGH Sub Division under Hooghly Division PHE Dte. (1) BALIPUR PWSS (ZONE- II )-2nos (2) BATANAL PWSS( Zone - I)-2nos (3) BATANAL PWSS( Zone - II)-2nos (4) DAKSHIN RASULPUR PWSS- 2 nos (5) HAZIPUR PWSS- 3nos (6) KAMARPUKUR PWSS- 3nos | Assistant Engineer | Junior Engineer (Civill) | ORD/002645/2024-2025 | 809/Arg | 23/08/2024 | 22/09/2024 | TITAS CONSTRUCTION | 0.98 | 0 | 0 | 100
6 | HOOGHLY |  | Hooghly Division | Source Augmentation of DAKSHIN RASULPUR Piped Water Supply Scheme under Arambag Block | SM/15812 | Augmentation | Route Survey for Augmentation of Dakshin Rasulpur Piped Water Supply Scheme under Arambagh Sub - Division of Hooghly Division, P.H.E. Dte. (Part-C) | Assistant Engineer |  | ORD/001214/2025-2026 | 650/Arg | 31/07/2025 | 31/08/2025 | APEX ENGINEERING | 0.68 | 0 | 0 | 0
7 | HOOGHLY |  | Hooghly Division | Source Augmentation of DAKSHIN RASULPUR Piped Water Supply Scheme under Arambag Block | SM/15812 | Augmentation | Prepatration of CAD-GIS Drawing and Pipe Network Design for Augmentation of Dakshin Rasulpur Piped Water Supply Scheme under Arambagh Sub - Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer |  | ORD/001208/2025-2026 | 646/Arg | 31/07/2025 | 31/08/2025 | APEX ENGINEERING | 0.84 | 0 | 0 | 0
8 | HOOGHLY |  | Hooghly Division | Source Augmentation of DAKSHIN RASULPUR Piped Water Supply Scheme under Arambag Block | SM/15812 | Augmentation | Preparation of DPR for Augmentation of Dakshin Rasulpur Piped Water Supply Scheme under Arambagh Sub - Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer |  | ORD/001209/2025-2026 | 647/Arg | 31/07/2025 | 31/08/2025 | APEX ENGINEERING | 0.78 | 0 | 0 | 0
9 | HOOGHLY |  | Hooghly Division | Source Augmentation of DAKSHIN RASULPUR Piped Water Supply Scheme under Arambag Block | SM/15812 | Augmentation | Route Survey for Augmentation of Dakshin Rasulpur Piped Water Supply Scheme under Arambagh Sub - Division of Hooghly Division, P.H.E. Dte. (Part - A) | Assistant Engineer |  | ORD/001212/2025-2026 | 648/Arg | 31/07/2025 | 31/08/2025 | APEX ENGINEERING | 0.73 | 0 | 0 | 0
10 | HOOGHLY |  | Hooghly Division | Source Augmentation of DAKSHIN RASULPUR Piped Water Supply Scheme under Arambag Block | SM/15812 | Augmentation | Route Survey for Augmentation of Dakshin Rasulpur Piped Water Supply Scheme under Arambagh Sub - Division of Hooghly Division, P.H.E. Dte. (Part-B) | Assistant Engineer |  | ORD/001213/2025-2026 | 649/Arg | 31/07/2025 | 31/08/2025 | APEX ENGINEERING | 0.95 | 0 | 0 | 0
Total | [13 empty] | 48.9 | 0 | 0