## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Electrical | Source Augmentation of BHANGAMORA Piped Water Supply Scheme under Pursurah Block | SM/15813 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Bhangamora water supply scheme, T.W. No. I, Block: Pursurah, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer1 | ORD/001145/2022-2023 | 1497/ED | 28/03/2023 | 26/06/2023 | KAMAKHYA ENTERPRISE | 10.69 | 0 | 0 | 0
2 | HOOGHLY |  | Hooghly Division | Source Augmentation of BHANGAMORA Piped Water Supply Scheme under Pursurah Block | SM/15813 | Augmentation | Construction of 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement , Boundary Wall in Proposed T.W Site,Laying rising main pipe for inter connection between T.W & Distribution For Source Augmentation of BHANGAMORA Piped Water Supply Scheme under Arambagh Sub-Division of Hooghly Division P.HE Dte. within Pursurah Block. | Assistant Engineer | Junior Engineer (Civill) | ORD/000119/2023-2024 | 1461/HUG | 18/05/2023 | 17/06/2023 | S. B. CONSTRUCTION | 11.97 | 0 | 0 | 0
3 | HOOGHLY |  | Electrical | Source Augmentation of BHANGAMORA Piped Water Supply Scheme under Pursurah Block | SM/15813 | Augmentation | Quotation Bill for New Service Connection at Bhangamora W/S. Sch. TW-III |  |  | BILL/03828/2023-2024 | 391 | 03/11/2023 | 03/11/2023 | WBSEDCL | 7.9 | 0 | 0 | 0
4 | HOOGHLY |  | Hooghly Division | Source Augmentation of BHANGAMORA Piped Water Supply Scheme under Pursurah Block | SM/15813 | Augmentation | Repair and Renovation Works of R.C.C. Elevated Reservoir, Boundary Wall, Switch Room of BHANGAMORA, SAOTA, PWSS under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. |  |  | ORD/000450/2024-2025 | 4081/HUG | 19/12/2024 | 19/03/2025 | R.K. TRADERS | 20.96 | 0 | 0 | 0
5 | HOOGHLY |  | Hooghly Division | Source Augmentation of BHANGAMORA Piped Water Supply Scheme under Pursurah Block | SM/15813 | Augmentation | Sinking of One No Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto150 Mtr at BHANGAMORA PWSS of ARAMBAGH Sub-Division under Hooghly Division, PHE Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000773/2022-2023 | 744/HUG | 15/03/2023 | 14/04/2023 | MAYA CONSTRUCTION | 11.32 | 0 | 0 | 100
6 | HOOGHLY |  | Hooghly Division | Source Augmentation of BHANGAMORA Piped Water Supply Scheme under Pursurah Block | SM/15813 | Augmentation | Supply of 200 mm dia CD pipe for Sinking of Tubewell at Bhangamora W/S Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/001050/2023-2024 | 471/Arg | 05/07/2023 | 20/07/2023 | MAYA CONSTRUCTION | 0.97 | 0 | 0 | 100
Total | [13 empty] | 63.81 | 0 | 0