## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Electrical | Source Augmentation of BHANGAMORA Piped Water Supply Scheme under Pursurah Block | SM/15813 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Bhangamora water supply scheme, T.W. No. I, Block: Pursurah, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer1 | ORD/001145/2022-2023 | 1497/ED | 28/03/2023 | 26/06/2023 | KAMAKHYA ENTERPRISE | 10.69 | 0 | 0 | 0
2 | HOOGHLY |  | Hooghly Division | Source Augmentation of BHANGAMORA Piped Water Supply Scheme under Pursurah Block | SM/15813 | Augmentation | Construction of 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement , Boundary Wall in Proposed T.W Site,Laying rising main pipe for inter connection between T.W & Distribution For Source Augmentation of BHANGAMORA Piped Water Supply Scheme under Arambagh Sub-Division of Hooghly Division P.HE Dte. within Pursurah Block. | Assistant Engineer | Junior Engineer (Civill) | ORD/000119/2023-2024 | 1461/HUG | 18/05/2023 | 17/06/2023 | S. B. CONSTRUCTION | 11.97 | 0 | 0 | 0
3 | HOOGHLY |  | Electrical | Source Augmentation of BHANGAMORA Piped Water Supply Scheme under Pursurah Block | SM/15813 | Augmentation | Quotation Bill for New Service Connection at Bhangamora W/S. Sch. TW-III |  |  | BILL/03828/2023-2024 | 391 | 03/11/2023 | 03/11/2023 | WBSEDCL | 7.9 | 0 | 0 | 0
4 | HOOGHLY |  | Hooghly Division | Source Augmentation of BHANGAMORA Piped Water Supply Scheme under Pursurah Block | SM/15813 | Augmentation | Repair and Renovation Works of R.C.C. Elevated Reservoir, Boundary Wall, Switch Room of BHANGAMORA, SAOTA, PWSS under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. |  |  | ORD/000450/2024-2025 | 4081/HUG | 19/12/2024 | 19/03/2025 | R.K. TRADERS | 20.96 | 0 | 0 | 0
5 | HOOGHLY |  | Hooghly Division | Source Augmentation of BHANGAMORA Piped Water Supply Scheme under Pursurah Block | SM/15813 | Augmentation | Sinking of One No Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto150 Mtr at BHANGAMORA PWSS of ARAMBAGH Sub-Division under Hooghly Division, PHE Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000773/2022-2023 | 744/HUG | 15/03/2023 | 14/04/2023 | MAYA CONSTRUCTION | 11.32 | 11.36 | 100.35 | 100
6 | HOOGHLY |  | Hooghly Division | Source Augmentation of BHANGAMORA Piped Water Supply Scheme under Pursurah Block | SM/15813 | Augmentation | Supply of 200 mm dia CD pipe for Sinking of Tubewell at Bhangamora W/S Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/001050/2023-2024 | 471/Arg | 05/07/2023 | 20/07/2023 | MAYA CONSTRUCTION | 0.97 | 0.97 | 100 | 100
7 | HOOGHLY |  | Hooghly Division | Source Augmentation of BHANGAMORA Piped Water Supply Scheme under Pursurah Block | SM/15813 | Augmentation | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under ARAMBAGH Sub-Division under Hooghly Division PHE Dte. (i) BAIKUNTHAPUR PWSS (ii) BHANGAMORA PWSS (iii) CHILADANGI PWSS (iv) SAOTA PWSS (v) SHYAMPUR PWSS (vi) MAHISGHOT-(ZONE-I) PWSS | Assistant Engineer | Junior Engineer (Civill) | ORD/000440/2024-2025 | 801/Arg | 23/08/2024 | 30/08/2024 | LIMRA SOCIAL WELFARE SOCIETY | 0.95 | 0 | 0 | 100
8 | HOOGHLY |  | Hooghly Division | Source Augmentation of BHANGAMORA Piped Water Supply Scheme under Pursurah Block | SM/15813 | Augmentation | Designing making and erection of Display Board using logo and tag line of LAND DEMARCATION OF P.H.E. Dte. to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under ARAMBAGH Sub Division under Hooghly Division PHE Dte. (1) GHOSHPUR PWSS-5nos (2) GHORADAHA PWSS-4nos (3) KAKNAN PWSS-3nos (4) BHANGAMORA PWSS-2nos | Assistant Engineer | Junior Engineer (Civill) | ORD/002650/2024-2025 | 817/Arg | 23/08/2024 | 22/09/2024 | TITAS CONSTRUCTION | 0.98 | 0 | 0 | 100
Total | [13 empty] | 65.74 | 12.33 | 18.75