## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | Source Augmentation of KAPSIT Piped Water Supply Scheme under Arambag Block | SM/15814 | Augmentation | Construction of 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement, Boundary Wall in Proposed T.W Site, Laying rising main pipe for inter connection between T.W & Distribution For Source Augmentation of KAPSIT Piped Water Supply Scheme under Arambagh Sub-Division of Hooghly Division P.HE Dte. within Arambagh Block. | Assistant Engineer | Junior Engineer (Civill) | ORD/000101/2023-2024 | 1420/HUG | 17/05/2023 | 16/06/2023 | SB ASSOCIATES | 11.82 | 0 | 0 | 0
2 | HOOGHLY |  | Hooghly Division | Source Augmentation of KAPSIT Piped Water Supply Scheme under Arambag Block | SM/15814 | Augmentation | Sinking of Two Nos. Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto150 Mtr at KAPSIT PWSS of ARAMBAGH Sub-Division under Hooghly Division, PHE Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000501/2023-2024 | 2861/HUG | 20/09/2023 | 14/09/2024 | SUBHAJIT BISWAS | 22.56 | 11.07 | 49.08 | 50
3 | HOOGHLY |  | Electrical | Source Augmentation of KAPSIT Piped Water Supply Scheme under Arambag Block | SM/15814 | Augmentation | Quotation of New Service Connection for Kapsit w/s Scheme, PH No-3 Block-Arambag Dist-Hooghly under Electrical Division,PHE Dte.(SM/15814) Application No-5004276344 Reference Id-503683335. |  |  | BILL/01142/2024-2025 | 264 | 03/07/2024 | 03/07/2024 | WBSEDCL | 3.77 | 0 | 0 | 0
4 | HOOGHLY |  | Electrical | Source Augmentation of KAPSIT Piped Water Supply Scheme under Arambag Block | SM/15814 | Augmentation | Quotation of New Service Connection for Kapsit w/s Scheme,PH No-IV Block-Arambag Dist-Hooghly under Electrical Division,PHE Dte.(SM/15814) Application No-5004320167 Reference Id- 503705436 |  |  | BILL/01375/2024-2025 | 335 | 30/07/2024 | 30/07/2024 | WBSEDCL | 11.46 | 0 | 0 | 0
5 | HOOGHLY |  | Electrical | Source Augmentation of KAPSIT Piped Water Supply Scheme under Arambag Block | SM/15814 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Kapsit water supply scheme, T.W. No. I & II, Block: Arambag, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 2 ,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/001152/2022-2023 | 1504/ED | 28/03/2023 | 01/09/2025 | A.K. ENTERPRISE | 21.93 | 8.12 | 37.05 | 100
Total | [13 empty] | 71.54 | 19.2 | 26.83