## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | Source Augmentation of KAPSIT Piped Water Supply Scheme under Arambag Block | SM/15814 | Augmentation | Construction of 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement, Boundary Wall in Proposed T.W Site, Laying rising main pipe for inter connection between T.W & Distribution For Source Augmentation of KAPSIT Piped Water Supply Scheme under Arambagh Sub-Division of Hooghly Division P.HE Dte. within Arambagh Block. | Assistant Engineer | Junior Engineer (Civill) | ORD/000101/2023-2024 | 1420/HUG | 17/05/2023 | 16/06/2023 | SB ASSOCIATES | 11.82 | 0 | 0 | 0
2 | HOOGHLY |  | Hooghly Division | Source Augmentation of KAPSIT Piped Water Supply Scheme under Arambag Block | SM/15814 | Augmentation | Sinking of Two Nos. Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto150 Mtr at KAPSIT PWSS of ARAMBAGH Sub-Division under Hooghly Division, PHE Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000501/2023-2024 | 2861/HUG | 20/09/2023 | 14/09/2024 | SUBHAJIT BISWAS | 22.56 | 11.07 | 49.08 | 50
3 | HOOGHLY |  | Electrical | Source Augmentation of KAPSIT Piped Water Supply Scheme under Arambag Block | SM/15814 | Augmentation | Quotation of New Service Connection for Kapsit w/s Scheme, PH No-3 Block-Arambag Dist-Hooghly under Electrical Division,PHE Dte.(SM/15814) Application No-5004276344 Reference Id-503683335. |  |  | BILL/01142/2024-2025 | 264 | 03/07/2024 | 03/07/2024 | WBSEDCL | 3.77 | 0 | 0 | 0
4 | HOOGHLY |  | Electrical | Source Augmentation of KAPSIT Piped Water Supply Scheme under Arambag Block | SM/15814 | Augmentation | Quotation of New Service Connection for Kapsit w/s Scheme,PH No-IV Block-Arambag Dist-Hooghly under Electrical Division,PHE Dte.(SM/15814) Application No-5004320167 Reference Id- 503705436 |  |  | BILL/01375/2024-2025 | 335 | 30/07/2024 | 30/07/2024 | WBSEDCL | 11.46 | 0 | 0 | 0
5 | HOOGHLY |  | Electrical | Source Augmentation of KAPSIT Piped Water Supply Scheme under Arambag Block | SM/15814 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Kapsit water supply scheme, T.W. No. I & II, Block: Arambag, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 2 ,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/001152/2022-2023 | 1504/ED | 28/03/2023 | 01/09/2025 | A.K. ENTERPRISE | 21.93 | 8.12 | 37.05 | 100
6 | HOOGHLY |  | Hooghly Division | Source Augmentation of KAPSIT Piped Water Supply Scheme under Arambag Block | SM/15814 | Augmentation | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under ARAMBAGH Sub-Division under Hooghly Division PHE Dte. (i) BACHANARI PWSS (ii) KAPSIT PWSS (iii) JOY KRISHNAPUR PWSS (iv) BALI PWSS (v) LAKSHMIPUR PWSS (vi) RADHABALLAVPUR PWSS | Assistant Engineer | Junior Engineer (Civill) | ORD/000431/2024-2025 | 798/Arg | 23/08/2024 | 30/08/2024 | LIMRA SOCIAL WELFARE SOCIETY | 0.95 | 0 | 0 | 100
Total | [13 empty] | 72.49 | 19.2 | 26.48