## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Electrical | Source Augmentation of Hazipur Piped Water Supply Scheme under Goghat-II Block | SM/15815 | Augmentation | Supply, Delivery & Installation of submersible Pumping Machinery & other allied electrical/mechanical equipments etc. incliding allied works for Hazipur W/S. Sch. | Assistant Engineer 2 | Junior Engineer4 | ORD/000522/2021-2022 | 555/ED | 23/03/2022 | 21/06/2022 | GLACIER ENGINEERING CO. | 6.62 | 0 | 0 | 60
2 | HOOGHLY |  | Hooghly Division | Source Augmentation of Hazipur Piped Water Supply Scheme under Goghat-II Block | SM/15815 | Augmentation | Repair and Renovation Works of R.C.C. Elevated Reservoir, Boundary Wall, Switch Room & Construction of boundary wall at 3rd Tube well Site of HAZIPUR PWSS under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. |  |  | ORD/000449/2024-2025 | 4082/HUG | 19/12/2024 | 19/03/2025 | DAS TRADING | 21.34 | 0 | 0 | 0
3 | HOOGHLY |  | Hooghly Division | Source Augmentation of Hazipur Piped Water Supply Scheme under Goghat-II Block | SM/15815 | Augmentation | Construction of 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement, Boundary Wall in Proposed T.W Site, Laying rising main pipe for inter connection between T.W & Distribution For Source Augmentation of HAZIPUR Piped Water Supply Scheme under Arambagh Sub-Division of Hooghly Division P.HE Dte. within Goghat-II Block. | Assistant Engineer | Junior Engineer (Civill) | ORD/000007/2023-2024 | 1013/Hug | 06/04/2023 | 25/01/2025 | RITAM ENTERPRISE | 11.79 | 5.06 | 42.94 | 100
4 | HOOGHLY |  | Hooghly Division | Source Augmentation of Hazipur Piped Water Supply Scheme under Goghat-II Block | SM/15815 | Augmentation | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under ARAMBAGH Sub-Division under Hooghly Division PHE Dte. (i) AMDOBA PWSS (ii) BADANGANJ PWSS (iii) HAZIPUR PWSS (iv) ARANDI PWSS (v) MAYAPUR PWSS (vi) BULUNDI PWSS | Assistant Engineer | Junior Engineer (Civill) | ORD/000432/2024-2025 | 799/Arg | 23/08/2024 | 30/08/2024 | LIMRA SOCIAL WELFARE SOCIETY | 0.95 | 0 | 0 | 100
Total | [13 empty] | 40.71 | 5.06 | 12.44