## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Electrical | Source Augmentation of Hazipur Piped Water Supply Scheme under Goghat-II Block | SM/15815 | Augmentation | Supply, Delivery & Installation of submersible Pumping Machinery & other allied electrical/mechanical equipments etc. incliding allied works for Hazipur W/S. Sch. | Assistant Engineer 2 | Junior Engineer4 | ORD/000522/2021-2022 | 555/ED | 23/03/2022 | 21/06/2022 | GLACIER ENGINEERING CO. | 6.62 | 0 | 0 | 60
2 | HOOGHLY |  | Hooghly Division | Source Augmentation of Hazipur Piped Water Supply Scheme under Goghat-II Block | SM/15815 | Augmentation | Repair and Renovation Works of R.C.C. Elevated Reservoir, Boundary Wall, Switch Room & Construction of boundary wall at 3rd Tube well Site of HAZIPUR PWSS under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. |  |  | ORD/000449/2024-2025 | 4082/HUG | 19/12/2024 | 19/03/2025 | DAS TRADING | 21.34 | 0 | 0 | 0
3 | HOOGHLY |  | Hooghly Division | Source Augmentation of Hazipur Piped Water Supply Scheme under Goghat-II Block | SM/15815 | Augmentation | Construction of 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement, Boundary Wall in Proposed T.W Site, Laying rising main pipe for inter connection between T.W & Distribution For Source Augmentation of HAZIPUR Piped Water Supply Scheme under Arambagh Sub-Division of Hooghly Division P.HE Dte. within Goghat-II Block. | Assistant Engineer | Junior Engineer (Civill) | ORD/000007/2023-2024 | 1013/Hug | 06/04/2023 | 25/01/2025 | RITAM ENTERPRISE | 11.79 | 0 | 0 | 100
Total | [13 empty] | 39.76 | 0 | 0