## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Arambag | Hooghly Division | GROUND WATER BASED TIROL (ZONE-II) PIPED W/S SCHEME UNDER ARAMBAGH BLOCK | SM/15886 | New | Material Requisition To Resource Division |  |  | RTOR000162/2023-2024 | 1385/33/Hug | 15/05/2023 | 15/05/2023 | Resource Division | 9.36 | 0 | 0 | 0
2 | HOOGHLY | Arambag | Hooghly Division | GROUND WATER BASED TIROL (ZONE-II) PIPED W/S SCHEME UNDER ARAMBAGH BLOCK | SM/15886 | New | Material Requisition To Resource Division |  |  | RTOR000420/2023-2024 | 3057/40/Hug | 11/10/2023 | 11/10/2023 | Resource Division | 9.36 | 0 | 0 | 0
3 | HOOGHLY | Arambag | Hooghly Division | GROUND WATER BASED TIROL (ZONE-II) PIPED W/S SCHEME UNDER ARAMBAGH BLOCK | SM/15886 | New | Material Requisition To Resource Division |  |  | RTOR000030/2023-2024 | 1234/11/Hug | 28/04/2023 | 28/04/2023 | Resource Division | 25 | 0 | 0 | 0
4 | HOOGHLY | Arambag | Electrical | GROUND WATER BASED TIROL (ZONE-II) PIPED W/S SCHEME UNDER ARAMBAGH BLOCK | SM/15886 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Tirol (Zone-II) water supply scheme, T.W. No. I & II, Block: Arambag, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 2 ,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000031/2023-2024 | 1708/ED | 18/04/2023 | 17/07/2023 | HINDUSTAN ENGINEERING CORPORATION (E&M) | 22.05 | 5.59 | 25.37 | 40
5 | HOOGHLY | Arambag | Hooghly Division | GROUND WATER BASED TIROL (ZONE-II) PIPED W/S SCHEME UNDER ARAMBAGH BLOCK | SM/15886 | New | Construction of 3 nos.5.4 m X 3.6 m Switch Room with Sanitary and Water Supply arrangement , Boundary Wall ,Laying rising main pipe for inter connection between Proposed T.W & Distribution at Proposed Tube Well Site of KRISHNANAGAR ZONE-II,MAYAPUR,TIROL ZONE-II W/S Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. |  |  | ORD/000407/2024-2025 | 3783/HUG | 25/11/2024 | 24/01/2025 | DAS CONSTRUCTION | 55.5 | 0 | 0 | 0
6 | HOOGHLY | Arambag | Electrical | GROUND WATER BASED TIROL (ZONE-II) PIPED W/S SCHEME UNDER ARAMBAGH BLOCK | SM/15886 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for TIROL PIPED W/S SCHEME, Zone - II, T.W. No. III, Block: Arambag, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer 2 ,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000166/2024-2025 | 1189/ED | 14/06/2024 | 12/03/2025 | HINDUSTAN ENGINEERING CORPORATION (E&M) | 10.73 | 0 | 0 | 0
7 | HOOGHLY | Arambag | Hooghly Division | GROUND WATER BASED TIROL (ZONE-II) PIPED W/S SCHEME UNDER ARAMBAGH BLOCK | SM/15886 | New | Construction of Approach Road at Tirol Zone-I Piped Water Supply Scheme under Arambagh Sub-Division Of Hooghly Division P.H.E Dte. |  |  | ORD/000231/2024-2025 | 3467/HUG | 04/10/2024 | 19/10/2024 | MINTU CHAKRABORTY | 3.45 | 0 | 0 | 0
8 | HOOGHLY | Arambag | Electrical | GROUND WATER BASED TIROL (ZONE-II) PIPED W/S SCHEME UNDER ARAMBAGH BLOCK | SM/15886 | New | Quotation money deposition for new service connection at Tirol w/s scheme , Zone -II, T.W. No- II, Dist.- Hooghly, under Electrical Division, PHE Dte. Application No.- 5004038623 Ref. ID- 503577402 SM Code- 15886 |  |  | BILL/06230/2023-2024 | 831 | 04/03/2024 | 04/03/2024 | WBSEDCL | 4.13 | 0 | 0 | 0
9 | HOOGHLY | Arambag | Electrical | GROUND WATER BASED TIROL (ZONE-II) PIPED W/S SCHEME UNDER ARAMBAGH BLOCK | SM/15886 | New | Quotation of New Service Connection for Tirol w/s Scheme, Zone-I,PH No-I Block-Arambag Dist-Hooghly under Electrical Division,PHE Dte.( SM/158668) Application No-5004061104 Reference Id-503590562 |  |  | BILL/06457/2023-2024 | 886 | 15/03/2024 | 15/03/2024 | WBSEDCL | 4.62 | 0 | 0 | 0
10 | HOOGHLY | Arambag | Electrical | GROUND WATER BASED TIROL (ZONE-II) PIPED W/S SCHEME UNDER ARAMBAGH BLOCK | SM/15886 | New | Quotation money deposition for new service connection at Tirol w/s scheme , Zone -II, T.W. No- I, Dist.- Hooghly, under Electrical Division, PHE Dte. Application No.- 5004038621 Ref. ID- 503577388 SM Code- 15886 |  |  | BILL/06231/2023-2024 | 832 | 04/03/2024 | 04/03/2024 | WBSEDCL | 6 | 0 | 0 | 0
11 | HOOGHLY | Arambag | Hooghly Division | GROUND WATER BASED TIROL (ZONE-II) PIPED W/S SCHEME UNDER ARAMBAGH BLOCK | SM/15886 | New | TIROL ZONE-II Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 200 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site, under ARAMBAGH Block, District:- Hooghly [NEW SCHEME] | Assistant Engineer | Junior Engineer (Civill) | ORD/000268/2023-2024 | 2279/HUG | 03/08/2023 | 16/03/2025 | UNIQUE AGENCY | 361.39 | 332.79 | 92.09 | 70
12 | HOOGHLY | Arambag | Hooghly Division | GROUND WATER BASED TIROL (ZONE-II) PIPED W/S SCHEME UNDER ARAMBAGH BLOCK | SM/15886 | New | Laying rising main pipe for inter connection between Proposed T.W & Distribution including Protection work of TIROL Z-II Piped Water Supply Scheme under ARAMBAGH Sub-Division of Hooghly Division P.H.E. Dte. |  |  | ORD/002257/2024-2025 | 572/HUG | 04/03/2025 | 03/05/2025 | UNIQUE AGENCY | 16.09 | 0 | 0 | 0
Total | [13 empty] | 527.69 | 338.38 | 64.12