## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Goghat-II | Hooghly Division | GROUND WATER BASED GARMANDARAN (Z-2) PIPED WATER SUPPLY SCHEME IN GOGHAT-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/15887 | New | Material Requisition To Resource Division |  |  | RTOR000064/2023-2024 | 1234/31/Hug | 28/04/2023 | 28/04/2023 | Resource Division | 56.14 | 0 | 0 | 0
2 | HOOGHLY | Goghat-II | Hooghly Division | GROUND WATER BASED GARMANDARAN (Z-2) PIPED WATER SUPPLY SCHEME IN GOGHAT-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/15887 | New | Material Requisition To Resource Division |  |  | RTOR000473/2023-2024 | 3057/61/Hug | 11/10/2023 | 11/10/2023 | Resource Division | 14.12 | 0 | 0 | 0
3 | HOOGHLY | Goghat-II | Electrical | GROUND WATER BASED GARMANDARAN (Z-2) PIPED WATER SUPPLY SCHEME IN GOGHAT-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/15887 | New | Quotation of New Service Connection Charge for Garmandaran w/s Scheme,Zone-II,PH No-I,Block-Goghat-I Dist-Hooghly under ED,PHE Dte |  |  | BILL/03700/2023-2024 | 241 | 01/09/2023 | 01/09/2023 | WBSEDCL | 4.17 | 0 | 0 | 0
4 | HOOGHLY | Goghat-II | Electrical | GROUND WATER BASED GARMANDARAN (Z-2) PIPED WATER SUPPLY SCHEME IN GOGHAT-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/15887 | New | Quotation of New Service Connection Charge for Garmandaran w/s Scheme,Zone-II,PH No-II Block-Goghat-II, Dist-Hooghly under Electrical Division ,PHE Dte |  |  | BILL/03701/2023-2024 | 242 | 01/09/2023 | 01/09/2023 | WBSEDCL | 5.35 | 0 | 0 | 0
5 | HOOGHLY | Goghat-II | Hooghly Division | GROUND WATER BASED GARMANDARAN (Z-2) PIPED WATER SUPPLY SCHEME IN GOGHAT-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/15887 | New | Construction of Boundary Wall, Laying rising main pipe for inter connection between Proposed T.W & Distribution of GARMANDARAN Z-II Piped Water Supply Scheme under ARAMBAGH Sub-Division of Hooghly Division P.H.E. Dte. |  |  | ORD/000296/2024-2025 | 3656/HUG | 13/11/2024 | 11/02/2025 | M/S BIMAL DAS AND CO. | 16.13 | 0 | 0 | 0
6 | HOOGHLY | Goghat-II | Hooghly Division | GROUND WATER BASED GARMANDARAN (Z-2) PIPED WATER SUPPLY SCHEME IN GOGHAT-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/15887 | New | Construction of 3 nos.5.4 m X 3.6 m Switch Room with Sanitary and Water Supply arrangement , Boundary Wall ,Laying rising main pipe for inter connection between Proposed T.W & Distribution at Proposed Tube Well Site of PUKURIA, GARMANDARAN Zone-I , GARMANDARAN Zone -II W/S Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. |  |  | ORD/000403/2024-2025 | 3781/HUG | 25/11/2024 | 24/01/2025 | KAJAL DEY | 55.4 | 0 | 0 | 0
7 | HOOGHLY | Goghat-II | Electrical | GROUND WATER BASED GARMANDARAN (Z-2) PIPED WATER SUPPLY SCHEME IN GOGHAT-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/15887 | New | Quotation of New Service Connection for Gar Mandaran w/s Scheme,Zone-II,PH no-III Block-Goghat-II Dist-Hooghly under Electrical division,PHe Dte.(SM/15887) Application No-5004498949 Reference Id-503815611 |  |  | BILL/02604/2024-2025 | 638 | 18/12/2024 | 18/12/2024 | WBSEDCL | 9.44 | 0 | 0 | 0
8 | HOOGHLY | Goghat-II | Hooghly Division | GROUND WATER BASED GARMANDARAN (Z-2) PIPED WATER SUPPLY SCHEME IN GOGHAT-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/15887 | New | GARMANDARAN ZONE-II Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 300 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under GOGHAT-II Block of Arambag SUb-Division under Hooghly Division, PHE Dte. [NEW SCHEME] | Assistant Engineer | Junior Engineer (Civill) | ORD/000172/2023-2024 | 1671/HUG | 08/06/2023 | 12/09/2025 | TITAS CONSTRUCTION | 476.79 | 0 | 0 | 55
9 | HOOGHLY | Goghat-II | Electrical | GROUND WATER BASED GARMANDARAN (Z-2) PIPED WATER SUPPLY SCHEME IN GOGHAT-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/15887 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Garmandaran (Zone-II) water supply scheme, T.W. No. III & IV, Block: Goghat-II, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 2 | Junior Engineer4 | ORD/000877/2023-2024 | 3450/ED | 11/08/2023 | 01/01/2026 | M.D ENTERPRISE | 21.44 | 0 | 0 | 20
10 | HOOGHLY | Goghat-II | Hooghly Division | GROUND WATER BASED GARMANDARAN (Z-2) PIPED WATER SUPPLY SCHEME IN GOGHAT-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/15887 | New | Sinking of 3 nos 300 X200 mm dia Tube Well, 210 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at Proposed Tube Well Site of PUKURIA , GARMANDARAN Zone-I , GARMANDARAN Zone-II W/S Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000251/2024-2025 | 3529/HUG | 22/10/2024 | 31/05/2025 | KHAN ENTERPRISE | 48.02 | 0 | 0 | 66
11 | HOOGHLY | Goghat-II | Hooghly Division | GROUND WATER BASED GARMANDARAN (Z-2) PIPED WATER SUPPLY SCHEME IN GOGHAT-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/15887 | New | Designing making and erection of Display Board using logo and tag line of LAND DEMARCATION OF P.H.E. Dte. to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under ARAMBAGH Sub Division under Hooghly Division PHE Dte. (1) RAGHUBATI PWSS- 2no¿s (2) GANESHBATI PWSS- 1 no¿s (3) BENGAI PWSS- 1 no¿s (4) BHURKUNDA PWSS(Z-I)- 1no¿s (5) GARMANDARAN (Z-I)- 4 no¿s, (6) GARMANDARAN PWSS (Z-II)- 4 no¿s, (7) SAMANTAKHANDA PWSS -1 no¿s | Assistant Engineer |  | ORD/002298/2024-2025 | 1148/Arg | 10/12/2024 | 10/01/2025 | TITAS CONSTRUCTION | 0.98 | 0 | 0 | 0
12 | HOOGHLY | Goghat-II | Electrical | GROUND WATER BASED GARMANDARAN (Z-2) PIPED WATER SUPPLY SCHEME IN GOGHAT-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/15887 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Garmandaran (Zone-II) water supply scheme, T.W. No. I, II, III & IV, Block: Goghat-II, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 2 | Junior Engineer4 | ORD/000029/2023-2024 | 1706/ED | 18/04/2023 | 01/07/2025 | UNITED TRADERS | 21.47 | 0 | 0 | 30
13 | HOOGHLY | Goghat-II | Hooghly Division | GROUND WATER BASED GARMANDARAN (Z-2) PIPED WATER SUPPLY SCHEME IN GOGHAT-II BLOCK UNDER HOOGHLY, HOOGHLY DISTRICT | SM/15887 | New | Sinking of 3rd tube-well by D.R. Rig method, Construction of 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement, Construction of Boundary Wall, Laying rising main pipe for inter connection between Proposed T.W & Distribution of GARMANDARAN (ZONE-II) Piped Water Supply Scheme under ARAMBAGH Sub-Division of Hooghly Division P.HE Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000760/2023-2024 | 449/HUG | 15/02/2024 | 09/07/2025 | GARHBETA - I UNEMPLOYED YOUTH ENGINEERS CO OPERATIVE | 31.69 | 0 | 0 | 90
Total | [13 empty] | 761.16 | 0 | 0