## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Singur | Hooghly Division | Sibrambati (Zone-II) Piped Water Supply Scheme, Block-Singur, District-Hooghly | SM/15888 | New | Material Requisition To Resource Division |  |  | RTOR000547/2023-2024 | 3058/21/Hug | 11/10/2023 | 11/10/2023 | Resource Division | 7.76 | 0 | 0 | 0
2 | HOOGHLY | Singur | Hooghly Division | Sibrambati (Zone-II) Piped Water Supply Scheme, Block-Singur, District-Hooghly | SM/15888 | New | Material Requisition To Resource Division |  |  | RTOR000058/2023-2024 | 1235/7/Hug | 28/04/2023 | 28/04/2023 | Resource Division | 3.7 | 0 | 0 | 0
3 | HOOGHLY | Singur | Electrical | Sibrambati (Zone-II) Piped Water Supply Scheme, Block-Singur, District-Hooghly | SM/15888 | New | Quotation Bill for New Service Connection at Shibrambati W/S. Sch. TW-III |  |  | BILL/04457/2023-2024 | 520 | 11/12/2023 | 11/12/2023 | WBSEDCL | 4.42 | 0 | 0 | 0
4 | HOOGHLY | Singur | Electrical | Sibrambati (Zone-II) Piped Water Supply Scheme, Block-Singur, District-Hooghly | SM/15888 | New | Quotation Bill for New Service Connection at Sibrambati W/S. Sch.TW-I, Z-II |  |  | BILL/04132/2023-2024 | 378 | 25/10/2023 | 25/10/2023 | WBSEDCL | 5.8 | 0 | 0 | 0
5 | HOOGHLY | Singur | Electrical | Sibrambati (Zone-II) Piped Water Supply Scheme, Block-Singur, District-Hooghly | SM/15888 | New | Quotation for new service connection at Sibrambati W/s Sch. Zone - II, T/W No. - III,[SM/15888], under Singur CCC, WBSEDCL, Ref. Id. - 503666629, Dt. - 18-06-2024, Application No. - 5004236084 |  |  | BILL/00851/2024-2025 | 247 | 24/06/2024 | 24/06/2024 | WBSEDCL | 9.51 | 0 | 0 | 0
6 | HOOGHLY | Singur | Hooghly Division | Sibrambati (Zone-II) Piped Water Supply Scheme, Block-Singur, District-Hooghly | SM/15888 | New | SIBRAMBATI ZONE-II Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 150 cum capacity RCC OHR with 20.0 mtr Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under SINGUR Block of Chandannagar Sub-Division under Hooghly Division, PHE Dte. [NEW SCHEME] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000800/2022-2023 | 937/HUG | 29/03/2023 | 24/12/2023 | M/S R.M. CONSTRUCTION | 311.17 | 0 | 0 | 100
7 | HOOGHLY | Singur | Electrical | Sibrambati (Zone-II) Piped Water Supply Scheme, Block-Singur, District-Hooghly | SM/15888 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Shibrambati water supply scheme, Zone-II, T.W. No. III, Block: Singur, District: Hooghly under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer 4 | ORD/002479/2023-2024 | 339/ED | 21/02/2024 | 21/05/2024 | DEY ENTERPRISE | 10.36 | 0 | 0 | 90
8 | HOOGHLY | Singur | Electrical | Sibrambati (Zone-II) Piped Water Supply Scheme, Block-Singur, District-Hooghly | SM/15888 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Sibrambati (Zone-II) water supply scheme, T.W. No. I & II, Block: Singur, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 2 | Junior Engineer4 | ORD/000032/2023-2024 | 1709/ED | 18/04/2023 | 01/06/2024 | GLACIER ENGINEERING CO. | 21.1 | 0 | 0 | 50
9 | HOOGHLY | Singur | Hooghly Division | Sibrambati (Zone-II) Piped Water Supply Scheme, Block-Singur, District-Hooghly | SM/15888 | New | Sinking of 3rd tube-well by D.R. Rig method, Construction of 3.6 m X 3.0m Switch Room with Sanitary and Water Supply arrangement, Construction of Boundary Wall, Laying rising main pipe for inter connection between Proposed T.W & Distribution of SHIBRAMBATI (ZONE-II) Piped Water Supply Scheme under CHANDANNAGAR Sub-Division of Hooghly Division P.HE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000750/2023-2024 | 385/HUG | 08/02/2024 | 03/02/2025 | BIMAL KUMAR HALDER | 31.64 | 0 | 0 | 100
Total | [13 empty] | 405.46 | 0 | 0