## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Singur | Hooghly Division | Sibrambati (Zone-I) Piped Water Supply Scheme, Block- Singur, District-Hooghly | SM/15889 | New | Material Requisition To Resource Division |  |  | RTOR000269/2022-2023 | 902/6/Hug | 27/03/2023 |  | Resource Division | 7.76 | 0 | 0 | 0
2 | HOOGHLY | Singur | Hooghly Division | Sibrambati (Zone-I) Piped Water Supply Scheme, Block- Singur, District-Hooghly | SM/15889 | New | Material Requisition To Resource Division |  |  | RTOR000427/2023-2024 | 3058/20/Hug | 11/10/2023 |  | Resource Division | 15.5 | 0 | 0 | 0
3 | HOOGHLY | Singur | Hooghly Division | Sibrambati (Zone-I) Piped Water Supply Scheme, Block- Singur, District-Hooghly | SM/15889 | New | Horizontal Auger boring with water jet system Including Approach Road at SIBRAMBATI ZONE-I Piped Water Supply Scheme under Chandannagar Sub-Division Of Hooghly Division P.H.E Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000590/2023-2024 | 3232/HUG | 03/11/2023 | 03/12/2023 | M/S BISWAS CONSTRUCTION | 20.63 | 10.31 | 50 | 100
4 | HOOGHLY | Singur | Electrical | Sibrambati (Zone-I) Piped Water Supply Scheme, Block- Singur, District-Hooghly | SM/15889 | New | Quotation for new service connection at Sibrambati water supply Scheme [SM/15889],Zone - I, T/W No. - I, Block - Singur, under Singur CCC, WBSEDCL, Ref. Id. - 503588850, Dt. - 11-03-2024, Application No. - 5004057590 |  |  | BILL/06274/2023-2024 | 882 | 13/03/2024 |  | WBSEDCL | 5.7 | 0 | 0 | null
5 | HOOGHLY | Singur | Electrical | Sibrambati (Zone-I) Piped Water Supply Scheme, Block- Singur, District-Hooghly | SM/15889 | New | Quotation for new service connection at Sibrambati water supply Scheme [SM/15889],Zone - I, T/W No. - I, Block - Singur, under Singur CCC, WBSEDCL, Ref. Id. - 503588850, Dt. - 11-03-2024, Application No. - 5004057590 |  |  | BILL/06274/2023-2024 | 882 | 13/03/2024 |  | WBSEDCL | 5.7 | 0 | 0 | null
6 | HOOGHLY | Singur | Hooghly Division | Sibrambati (Zone-I) Piped Water Supply Scheme, Block- Singur, District-Hooghly | SM/15889 | New | Preparation of DPR for different works for providing Functional Household Tap Connection (FHTC) of Sibrambati (Zone-I) Piped Water Supply Scheme under Singur Block, Hooghly District under Chandannagar Sub-Division, PHE Dte. (PART-A). | Assistant Engineer (Civil) |  | ORD/000792/2023-2024 | 152/Chan | 16/02/2024 | 02/03/2024 | TECHVISION | 0.84 | 0.42 | 50 | 98
7 | HOOGHLY | Singur | Hooghly Division | Sibrambati (Zone-I) Piped Water Supply Scheme, Block- Singur, District-Hooghly | SM/15889 | New | Preparation of DPR for different works for providing Functional Household Tap Connection (FHTC) of Sibrambati (Zone-I) Piped Water Supply Scheme under Singur Block, Hooghly District under Chandannagar Sub-Division, PHE Dte. (PART-C). | Assistant Engineer (Civil) |  | ORD/000797/2023-2024 | 154/Chan | 16/02/2024 | 02/03/2024 | TECHVISION | 0.96 | 0.48 | 50 | 98
8 | HOOGHLY | Singur | Hooghly Division | Sibrambati (Zone-I) Piped Water Supply Scheme, Block- Singur, District-Hooghly | SM/15889 | New | Preparation of DPR for different works for providing Functional Household Tap Connection (FHTC) of Sibrambati (Zone-I) Piped Water Supply Scheme under Singur Block, Hooghly District under Chandannagar Sub-Division, PHE Dte. (PART-B). | Assistant Engineer (Civil) |  | ORD/000794/2023-2024 | 153/Chan | 16/02/2024 | 02/03/2024 | TECHVISION | 0.73 | 0.36 | 50 | 98
9 | HOOGHLY | Singur | Hooghly Division | Sibrambati (Zone-I) Piped Water Supply Scheme, Block- Singur, District-Hooghly | SM/15889 | New | Preparation of DPR for different works for providing Functional Household Tap Connection (FHTC) of Sibrambati (Zone-I) Piped Water Supply Scheme under Singur Block, Hooghly District under Chandannagar Sub-Division, PHE Dte. (PART-D). | Assistant Engineer (Civil) |  | ORD/000798/2023-2024 | 155/Chan | 16/02/2024 | 02/03/2024 | TECHVISION | 0.78 | 0.39 | 50 | 98
10 | HOOGHLY | Singur | Electrical | Sibrambati (Zone-I) Piped Water Supply Scheme, Block- Singur, District-Hooghly | SM/15889 | New | Quotation for new service connection at Sibrambati W/S Sch., (Zone - I), T/W No. - II,[SM/15889] Block - Singur under Singur CCC, WBSEDCL, Ref. Id. - 503591781, Dt. - 12-03-2024, Application No. - 5004061900 |  |  | BILL/06469/2023-2024 | 893 | 18/03/2024 |  | WBSEDCL | 6.69 | 0 | 0 | null
11 | HOOGHLY | Singur | Electrical | Sibrambati (Zone-I) Piped Water Supply Scheme, Block- Singur, District-Hooghly | SM/15889 | New | Quotation for new service connection at Sibrambati W/S Sch., (Zone - I), T/W No. - II,[SM/15889] Block - Singur under Singur CCC, WBSEDCL, Ref. Id. - 503591781, Dt. - 12-03-2024, Application No. - 5004061900 |  |  | BILL/06469/2023-2024 | 893 | 18/03/2024 |  | WBSEDCL | 6.69 | 0 | 0 | null
12 | HOOGHLY | Singur | Hooghly Division | Sibrambati (Zone-I) Piped Water Supply Scheme, Block- Singur, District-Hooghly | SM/15889 | New | SIBRAMBATI ZONE-I Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 300 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under SINGUR Block of Chandannagar Sub-Division under Hooghly Division, PHE Dte. [NEW SCHEME] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000277/2023-2024 | 2296/HUG | 03/08/2023 | 29/04/2024 | M/S BISWAS CONSTRUCTION | 551.83 | 139.35 | 25.25 | 40
13 | HOOGHLY | Singur | Electrical | Sibrambati (Zone-I) Piped Water Supply Scheme, Block- Singur, District-Hooghly | SM/15889 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Sibrambati water supply scheme, Zone-I, T.W. No. I & II, Block: Singur, District - Hooghly under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/001359/2023-2024 | 4695/ED | 08/12/2023 | 07/03/2024 | A.K. ENTERPRISE | 22.43 | 0 | 0 | 70
Total | [13 empty] | 646.24 | 151.32 | 23.41