## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Jangipara | Hooghly Division | GOPALPUR PIPED WATER SUPPLY SCHEME BLOCK : JANGIPARA, DISTRICT : HOOGHLY. | SM/15890 | New | Material Requisition To Resource Division |  |  | RTOR000035/2023-2024 | 1236/2/Hug | 28/04/2023 |  | Resource Division | 56.85 | 0 | 0 | 0
2 | HOOGHLY | Jangipara | Electrical | GOPALPUR PIPED WATER SUPPLY SCHEME BLOCK : JANGIPARA, DISTRICT : HOOGHLY. | SM/15890 | New | upply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Gopalpur water supply scheme, Zone-I, T.W. No. I & II Block: jangipara, District- Hooghly under Electrical Division, PHE Dte. |  | Junior Engineer2 | ORD/000010/2023-2024 | 1626/ED | 11/04/2023 | 10/07/2023 | UNITED ENTERPRISE | 21.83 | 0 | 0 | 0
3 | HOOGHLY | Jangipara | Hooghly Division | GOPALPUR PIPED WATER SUPPLY SCHEME BLOCK : JANGIPARA, DISTRICT : HOOGHLY. | SM/15890 | New | Material Requisition To Resource Division |  |  | RTOR000323/2023-2024 | 1384/20/Hug | 15/05/2023 |  | Resource Division | 19.32 | 0 | 0 | 0
4 | HOOGHLY | Jangipara | Electrical | GOPALPUR PIPED WATER SUPPLY SCHEME BLOCK : JANGIPARA, DISTRICT : HOOGHLY. | SM/15890 | New | Adhoc payment to WBSEDCL against Service Connection |  |  | BILL/01125/2023-2024 | null | 28/06/2023 |  | WBSEDCL | 71.17 | 0 | 0 | 0
5 | HOOGHLY | Jangipara | Hooghly Division | GOPALPUR PIPED WATER SUPPLY SCHEME BLOCK : JANGIPARA, DISTRICT : HOOGHLY. | SM/15890 | New | Material Requisition To Resource Division |  |  | RTOR000527/2023-2024 | 3060/11/Hug | 11/10/2023 |  | Resource Division | 17.72 | 0 | 0 | 0
6 | HOOGHLY | Jangipara | Electrical | GOPALPUR PIPED WATER SUPPLY SCHEME BLOCK : JANGIPARA, DISTRICT : HOOGHLY. | SM/15890 | New | Quotation Bill for New Service Connection at Gopalpur W/S. Sch. PH-II, Z-I |  |  | BILL/04451/2023-2024 | 509 | 08/12/2023 |  | WBSEDCL | 10.63 | 0 | 0 | 0
7 | HOOGHLY | Jangipara | Electrical | GOPALPUR PIPED WATER SUPPLY SCHEME BLOCK : JANGIPARA, DISTRICT : HOOGHLY. | SM/15890 | New | Quotation Bill for New Service Connection at Gopalpur W/S. Sch. PH-II, Z-I |  |  | BILL/04451/2023-2024 | 509 | 08/12/2023 |  | WBSEDCL | 10.63 | 0 | 0 | 0
8 | HOOGHLY | Jangipara | Electrical | GOPALPUR PIPED WATER SUPPLY SCHEME BLOCK : JANGIPARA, DISTRICT : HOOGHLY. | SM/15890 | New | Quotation Bill for New Service Connection at Gopalpur W/S. Sch. PH-I, Z-I |  |  | BILL/04452/2023-2024 | 510 | 08/12/2023 |  | WBSEDCL | 4.72 | 0 | 0 | 0
9 | HOOGHLY | Jangipara | Electrical | GOPALPUR PIPED WATER SUPPLY SCHEME BLOCK : JANGIPARA, DISTRICT : HOOGHLY. | SM/15890 | New | Quotation Bill for New Service Connection at Gopalpur Piped W/S. Sch. Z-II, PH-I |  |  | BILL/04579/2023-2024 | 577 | 27/12/2023 |  | WBSEDCL | 7.27 | 0 | 0 | 0
10 | HOOGHLY | Jangipara | Hooghly Division | GOPALPUR PIPED WATER SUPPLY SCHEME BLOCK : JANGIPARA, DISTRICT : HOOGHLY. | SM/15890 | New | GOPALPUR ZONE-I Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 200 cum capacity RCC OHR with 20.0 mtr.Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under JANGIPARA Block under Serampore Sub-Division of Hooghly Division, PHE Dte. [NEW SCHEME] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000375/2023-2024 | 2496/HUG | 17/08/2023 | 13/05/2024 | J.N. CONSTRUCTION (TAPAN KUMAR DHAR) | 416.93 | 112.36 | 26.95 | 78
11 | HOOGHLY | Jangipara | Electrical | GOPALPUR PIPED WATER SUPPLY SCHEME BLOCK : JANGIPARA, DISTRICT : HOOGHLY. | SM/15890 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Gopalpur water supply scheme, Zone-I, T.W. No. III & IV, Block: jangipara, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 1 | Junior Engineer2 | ORD/000880/2023-2024 | 3453/ED | 11/08/2023 | 09/11/2023 | DAS ENTERPRISE | 21.49 | 9.33 | 43.4 | 50
12 | HOOGHLY | Jangipara | Hooghly Division | GOPALPUR PIPED WATER SUPPLY SCHEME BLOCK : JANGIPARA, DISTRICT : HOOGHLY. | SM/15890 | New | GOPALPUR ZONE-II Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 250 cum capacity RCC OHR with 20.0 mtr Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under JANGIPARA Block of Serampore Sub-Division under Hooghly Division PHE Dte. [NEW SCHEME] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000376/2023-2024 | 2497/HUG | 17/08/2023 | 13/05/2024 | J.N. CONSTRUCTION (TAPAN KUMAR DHAR) | 498.12 | 163.21 | 32.77 | 16
Total | [13 empty] | 1156.66 | 284.9 | 24.63