## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR DHARAMPUR W/S SCHEME | SM/15891 | Augmentation | Car Hire Charges Bill for official use of the Howrah Mechanical Sub-Division PHED |  |  | ORD/001026/2023-2024 | 958,HMSD | 20/04/2023 | 19/04/2024 | ARINDAM AUDDY | 5 | 0 | 0 | 50
2 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR DHARAMPUR W/S SCHEME | SM/15891 | Augmentation | Providing Functional Household Tap Connection (FHTC) under JJM within left out portion of DHARAMPUR PWSS under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer (Civil) |  | ORD/000029/2023-2024 | 1129/HUG | 19/04/2023 | 03/06/2023 | M/S SHIVAM UDYOG | 54.23 | 0 | 0 | 97
3 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR DHARAMPUR W/S SCHEME | SM/15891 | Augmentation | Hire Charges Bill for official use office of the Howrah Mechanical Sub-Division PHED |  |  | ORD/000987/2023-2024 | 958/HmSD | 20/04/2023 | 19/04/2024 | ARINDAM AUDDY | 5 | 0 | 0 | 1
4 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR DHARAMPUR W/S SCHEME | SM/15891 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000537/2023-2024 | 3059/32/Hug | 11/10/2023 | 11/10/2023 | Resource Division | 14.49 | 0 | 0 | 0
5 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR DHARAMPUR W/S SCHEME | SM/15891 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000071/2023-2024 | 1234/35/Hug | 28/04/2023 | 28/04/2023 | Resource Division | 19.68 | 0 | 0 | 0
6 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR DHARAMPUR W/S SCHEME | SM/15891 | Augmentation | Supply, delivery and installation of voltage correcting device and other allied works for DHARAMPUR w/s scheme, P.H No.- II, Dist- Hooghly under Electrical Division, PHE Dte. |  |  | BILL/00874/2022-2023 | 177 | 02/03/2023 | 02/03/2023 | JECLAT ENGINEERING CO-OPERATIVE SOCIETY LTD. | 2.72 | 0 | 0 | 0
7 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR DHARAMPUR W/S SCHEME | SM/15891 | Augmentation | Supply, delivery & installation of Automatic Chlorinator for Dharampur water supply scheme, P.H. No.- II, District - Hooghly under Electrical Division, PHE Dte. |  |  | BILL/00876/2022-2023 | 177 | 02/03/2023 | 02/03/2023 | JECLAT ENGINEERING CO-OPERATIVE SOCIETY LTD. | 0.76 | 0 | 0 | 0
8 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR DHARAMPUR W/S SCHEME | SM/15891 | Augmentation | Supply, Delivery & Installation of Submersible Pumping machinery and other Electrical/mechanical equipments etc. including allied works for Dharampur w/s scheme |  |  | BILL/00872/2022-2023 | 178 | 02/03/2023 | 02/03/2023 | H.K.DAS & CO. | 4.32 | 0 | 0 | 0
9 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR DHARAMPUR W/S SCHEME | SM/15891 | Augmentation | Quotation for new service connection at Dharampur W/S Sch. , T/W No. -I (Aug.), Block - Chinsurah-Mogra, Dist. - Hooghly |  |  | BILL/03784/2023-2024 | 282 | 13/09/2023 | 13/09/2023 | WBSEDCL | 0.64 | 0 | 0 | 0
10 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR DHARAMPUR W/S SCHEME | SM/15891 | Augmentation | Hiring of 1 (one) no. Diesel luxury Taxi on contract carriage for the Office of the Assistant Engineer, Howrah Mechanical Sub Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/001103/2023-2024 | 2829/HMSD | 30/10/2023 | 29/04/2024 | ARINDAM AUDDY | 0.86 | 0 | 0 | 15
11 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR DHARAMPUR W/S SCHEME | SM/15891 | Augmentation | Construction of 1 No. 3.6 m X 3.0 m Switch Room with Additional Plinth Height, with Sanitary and Water Supply arrangement, Construction of 2 nos. Boundary wall &Laying of C.I/D.I pipes & specials for connection of Proposed 2 nos.T.W with distribution system, FHTC of DHARAMPUR W/S Scheme under Chinsurah Sub - Division P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000087/2023-2024 | 1341/HUG | 11/05/2023 | 25/06/2023 | NOBLE ENGINEERS CO-OPERATIVE SOCIETY LTD. | 44.76 | 0 | 0 | 75
12 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR DHARAMPUR W/S SCHEME | SM/15891 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Augmentation of Dharampur water supply scheme, T.W. No. I & II, Block: Chinsura-Mogra, District - Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 2 ,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/001357/2023-2024 | 4693/ED | 08/12/2023 | 07/03/2024 | BISALAXMI ENTERPRISE | 21.99 | 0 | 0 | 49
13 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR DHARAMPUR W/S SCHEME | SM/15891 | Augmentation | Supply of Fuel for 1(one) no Diesel Luxury Taxi on contract Carriage for the Office of the assistant Engineer Howrah Mechanical Sub Division PHE Dte for the Month of March 2024. |  |  | BILL/00164/2024-2025 |  | 12/04/2024 | 12/04/2024 | JAMECO AGENCIES PRIVATE LIMITED. | 0.24 | 0 | 0 | 0
14 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR DHARAMPUR W/S SCHEME | SM/15891 | Augmentation | Quotation for new service connection at Augmentation of Dharampur W/S Sch.[SM/15891], T/W No. - II, South Simla, Block - Chinsurah-Mogra Dist. - Hooghly under Bandel CCC, WBSEDCL, Ref. Id. - 503599481, Dt. - 22-03-2024, Application No. - 5004078318 |  |  | BILL/00014/2024-2025 | 15 | 04/04/2024 | 04/04/2024 | WBSEDCL | 7.75 | 0 | 0 | 0
Total | [13 empty] | 182.45 | 0 | 0