## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Central Drilling | Development of ANIYA Piped Water Supply Scheme by installing (01) no. Tube Well including Connection with Distribution, Switch Room and other allied work to meet up the additional water demand induced after execution of FHTC. Block : Chanditala-I, Distric | SM/15898 | Augmentation | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 150 MTRS.) BY UTILISING DEPARTMENTAL RIG MACHINERIES FOR ANIYA SCHEME (P/H-3), CHANDITALA-I BLOCK UNDER HOOGHLY DISTRICT, CENTRAL DRILLING DIVISION , PHE DTE. | Driller In Charge | Junior Engineer | ORD/000032/2023-2024 | 872/CDD | 11/07/2023 | 10/08/2023 | UTTAM KUMAR CHATTERJEE | 10.73 | 10.41 | 97.04 | 100
2 | HOOGHLY |  | Hooghly Division | Development of ANIYA Piped Water Supply Scheme by installing (01) no. Tube Well including Connection with Distribution, Switch Room and other allied work to meet up the additional water demand induced after execution of FHTC. Block : Chanditala-I, Distric | SM/15898 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000311/2023-2024 | 1384/8/Hug | 16/05/2023 | 16/05/2023 | Resource Division | 1.23 | 0 | 0 | 0
3 | HOOGHLY |  | Electrical | Development of ANIYA Piped Water Supply Scheme by installing (01) no. Tube Well including Connection with Distribution, Switch Room and other allied work to meet up the additional water demand induced after execution of FHTC. Block : Chanditala-I, Distric | SM/15898 | Augmentation | Aniya water supply scheme,P H No-3 |  |  | BILL/02293/2023-2024 | 142 | 25/07/2023 | 25/07/2023 | WBSEDCL | 3.2 | 0 | 0 | 0
4 | HOOGHLY |  | Electrical | Development of ANIYA Piped Water Supply Scheme by installing (01) no. Tube Well including Connection with Distribution, Switch Room and other allied work to meet up the additional water demand induced after execution of FHTC. Block : Chanditala-I, Distric | SM/15898 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Aniya water supply scheme, T.W. No. I, Block: Chanditala-I, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 1 | Junior Engineer2 | ORD/000011/2023-2024 | 1627/ED | 11/04/2023 | 10/07/2023 | ANIK & CO. | 11.41 | 11.11 | 97.37 | 85
5 | HOOGHLY |  | Hooghly Division | Development of ANIYA Piped Water Supply Scheme by installing (01) no. Tube Well including Connection with Distribution, Switch Room and other allied work to meet up the additional water demand induced after execution of FHTC. Block : Chanditala-I, Distric | SM/15898 | Augmentation | Construction of 3.6 m X 3.0 m Switch Room with Additional Plinth Height, with Sanitary and Water Supply arrangement, Laying of C.I/D.I pipes & specials for connection of Proposed T.W. with distribution system & FHTC For Development of ANIYA W/S Scheme under Serampore Sub - Division P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000113/2023-2024 | 1442/HUG | 18/05/2023 | 17/06/2023 | M/S KAMALA ENTERPRISE | 26.42 | 14.91 | 56.42 | 80
6 | HOOGHLY |  | Central Drilling | Development of ANIYA Piped Water Supply Scheme by installing (01) no. Tube Well including Connection with Distribution, Switch Room and other allied work to meet up the additional water demand induced after execution of FHTC. Block : Chanditala-I, Distric | SM/15898 | Augmentation | Additional work for construction of tube well at Aniya PWSS TW-I, Chanditala-I Block, Hooghly District by utilizing skilled departmental crew and departmental mechaneries CDD, PHE Dte. | Driller In Charge | Junior Engineer | ORD/000197/2023-2024 | 193/CMSD-II | 26/07/2023 | 05/08/2023 | UTTAM KUMAR CHATTERJEE | 0.67 | 0.69 | 102.22 | 100
Total | [13 empty] | 53.66 | 37.12 | 69.16