## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF KOLA W/S SCHEME UNDER CHINSURAH MAGRA BLOCK | SM/15899 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000538/2023-2024 | 3059/31/Hug | 11/10/2023 | 11/10/2023 | Resource Division | 1.85 | 0 | 0 | 0
2 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF KOLA W/S SCHEME UNDER CHINSURAH MAGRA BLOCK | SM/15899 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000354/2023-2024 | 3004/19/Hug | 05/10/2023 | 05/10/2023 | Resource Division | 20.39 | 0 | 0 | 0
3 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF KOLA W/S SCHEME UNDER CHINSURAH MAGRA BLOCK | SM/15899 | Augmentation | Augmentation Kola PWSS |  |  | BILL/00497/2023-2024 | BP-2023-24-398 | 26/09/2023 | 26/09/2023 | EXECUTIVE ENGINEER, HOOGHLY HIGHWAY DIVISION NO.I P.W.(ROADS) DIRECTORATE | 4.22 | 0 | 0 | 0
4 | HOOGHLY |  | Electrical | SOURCE AUGMENTATION OF KOLA W/S SCHEME UNDER CHINSURAH MAGRA BLOCK | SM/15899 | Augmentation | "Quotation Bill for New Service Connection at Kola W/S. Sch. " |  |  | BILL/04320/2023-2024 | 440 | 23/11/2023 | 23/11/2023 | WBSEDCL | 3.17 | 0 | 0 | 0
5 | HOOGHLY |  | Electrical | SOURCE AUGMENTATION OF KOLA W/S SCHEME UNDER CHINSURAH MAGRA BLOCK | SM/15899 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Kola water supply scheme, T.W. No. I, Block: Chinsurah-Magra, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 2 | Junior Engineer4 | ORD/000018/2023-2024 | 1634/ED | 11/04/2023 | 10/07/2023 | BIJAN ENTERPRISE | 11.4 | 11.08 | 97.24 | 95
6 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF KOLA W/S SCHEME UNDER CHINSURAH MAGRA BLOCK | SM/15899 | Augmentation | Construction of 3.6 m X 3.0 m Switch Room with Additional Plinth Height, with Sanitary and Water Supply arrangement, Laying of C.I/D.I pipes & specials for connection of Proposed T.W with distribution system , FHTC of KOLA W/S Scheme under Chinsurah Sub - Division P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000080/2023-2024 | 1314/HUG | 10/05/2023 | 09/06/2023 | M/S T.K.B. CONSTRUCTION | 32.26 | 31.34 | 97.16 | 50
7 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF KOLA W/S SCHEME UNDER CHINSURAH MAGRA BLOCK | SM/15899 | Augmentation | Sinking of Six Nos. Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto180 Mtr at DHARAMPUR, BADINAN, BHASTARA, KOLA, PATNABHAIRABPUR, GURAP PWSS of CHINSURAH Sub-Division under Hooghly Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000787/2022-2023 | 882/HUG | 27/03/2023 | 11/05/2023 | AUXILIARY TUBEWELL DRILLERS | 75.1 | 13.08 | 17.42 | 65
8 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF KOLA W/S SCHEME UNDER CHINSURAH MAGRA BLOCK | SM/15899 | Augmentation | Designing, making and erection of Display Board to be placed at different work sites / departmental lands under CHINSURAH-MOGRA KOLA/AMODGHATA/CHAKBASBERIA/NALDANGA/KULIHANDA/DHARAMPUR/DIGSUI) Block of Chinsurah Sub Division under Hooghly Division PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/001962/2024-2025 | 284/CH | 20/02/2025 | 02/03/2025 | DAS ENTERPRISE (SAMIR DAS) | 3.88 | 0 | 0 | 100
9 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF KOLA W/S SCHEME UNDER CHINSURAH MAGRA BLOCK | SM/15899 | Augmentation | Restoration & repairing of village road damaged due to laying of pipeline of Kola piped water supply schemes under in JJM under Chinsurah Magra Block. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/002146/2024-2025 | 373/CH | 03/03/2025 | 10/03/2025 | VOLCANO | 0.89 | 0 | 0 | 100
Total | [13 empty] | 153.16 | 55.51 | 36.24