## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF PATNA BHAIRAVPUR W/S SCHEME UNDER POLBA DADPUR BLOCK | SM/15900 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000541/2023-2024 | 3059/28/Hug | 11/10/2023 | 11/10/2023 | Resource Division | 1.85 | 0 | 0 | 0
2 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF PATNA BHAIRAVPUR W/S SCHEME UNDER POLBA DADPUR BLOCK | SM/15900 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000356/2023-2024 | 3004/Hug | 05/10/2023 | 05/10/2023 | Resource Division | 1.5 | 0 | 0 | 0
3 | HOOGHLY |  | Electrical | SOURCE AUGMENTATION OF PATNA BHAIRAVPUR W/S SCHEME UNDER POLBA DADPUR BLOCK | SM/15900 | Augmentation | Quotation for new service connection at Patna Bhirabpur W/S Sch. T/W - I (Aug.), Dist. - Hooghly |  |  | BILL/03755/2023-2024 | 259 | 05/09/2023 | 05/09/2023 | WBSEDCL | 5.61 | 0 | 0 | 0
4 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF PATNA BHAIRAVPUR W/S SCHEME UNDER POLBA DADPUR BLOCK | SM/15900 | Augmentation | Horizontal Auger boring with water jet system including Protection Work at Patna Bhairabpur W/S Scheme under CHINSURAH Sub-Division of Hooghly Division, P.H.E. Dte., Dist. Hooghly. |  |  | ORD/000305/2024-2025 | 3676/HUG | 13/11/2024 | 13/12/2024 | SAMRAT CONSTRUCTION | 8.16 | 0 | 0 | 0
5 | HOOGHLY |  | Electrical | SOURCE AUGMENTATION OF PATNA BHAIRAVPUR W/S SCHEME UNDER POLBA DADPUR BLOCK | SM/15900 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Patna Bhairavpur water supply scheme, T.W. No. I, Block: Polba-Dadpur, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 2 | Junior Engineer4 | ORD/000020/2023-2024 | 1636/ED | 11/04/2023 | 10/07/2023 | DIPA CHHETRI | 11.5 | 11.47 | 99.77 | 90
6 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF PATNA BHAIRAVPUR W/S SCHEME UNDER POLBA DADPUR BLOCK | SM/15900 | Augmentation | Maintanance work for improvement of water supply in distribution system at Patna Bhairabpur W/S Scheme under Chinsurah Sub - Division P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000732/2023-2024 | 24/CH | 05/01/2024 | 20/01/2024 | SUNITI MAIRA | 4.47 | 0 | 0 | 50
7 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF PATNA BHAIRAVPUR W/S SCHEME UNDER POLBA DADPUR BLOCK | SM/15900 | Augmentation | Laying of pipe line and other necessary maintanance work for improvement of water supply in distribution system at Patna Bhairabpur W/S Scheme under Chinsurah Sub - Division P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000733/2023-2024 | 25/CH | 05/01/2024 | 20/01/2024 | SUNITI MAIRA | 4.67 | 4.54 | 97.02 | 50
8 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF PATNA BHAIRAVPUR W/S SCHEME UNDER POLBA DADPUR BLOCK | SM/15900 | Augmentation | Sinking of Six Nos. Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto180 Mtr at DHARAMPUR, BADINAN, BHASTARA, KOLA, PATNABHAIRABPUR, GURAP PWSS of CHINSURAH Sub-Division under Hooghly Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000787/2022-2023 | 882/HUG | 27/03/2023 | 11/05/2023 | AUXILIARY TUBEWELL DRILLERS | 75.1 | 13.08 | 17.42 | 65
9 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF PATNA BHAIRAVPUR W/S SCHEME UNDER POLBA DADPUR BLOCK | SM/15900 | Augmentation | Construction of 3.6 m X 3.0 m Switch Room with Additional Plinth Height, with Sanitary and Water Supply arrangement, Laying of C.I/D.I pipes & specials for connection of Proposed T.W with distribution system , FHTC of PATNA BHAIRABPUR W/S Scheme under Chinsurah Sub - Division P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000081/2023-2024 | 1315/HUG | 10/05/2023 | 01/12/2024 | DREAM INFRASTRUCTURE | 21.56 | 8 | 37.11 | 50
Total | [13 empty] | 134.41 | 37.09 | 27.59