## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | IMPROVEMENT OF KOLA W/S SCHEME BY LAYING OF HDPE PIPELINE BY HDD PROCESS UNDER CHINSURAH SUB DIVISION UNDER CHINSURAH MAGRA BLOCK | SM/15901 | Augmentation | Laying of HDPE Pipe by HDD Process from Spandan Electronics at Magra Ganj towards Natungram Shib Manidr via Rathtala Suriya Sangha Club at Mogra-Gurap (23 No.) Road within KOLA PWSS, under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer (Civil) |  | ORD/000038/2023-2024 | 1161/HUG | 20/04/2023 | 04/06/2023 | MAA TARA CONSTRUCTION | 96.46 | 76.91 | 79.73 | 50
2 | HOOGHLY |  | Hooghly Division | IMPROVEMENT OF KOLA W/S SCHEME BY LAYING OF HDPE PIPELINE BY HDD PROCESS UNDER CHINSURAH SUB DIVISION UNDER CHINSURAH MAGRA BLOCK | SM/15901 | Augmentation | Laying C.I/D.I pipes & specials for rising main pipe line in between T.W No. -I & II to O.H.R including Bypass arrangement and interconnection with distribution system along with the connection between T.W No. -III with distribution system for Kola W/S under Chinsurah Sub - Division P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000310/2024-2025 | 3664/HUG | 13/11/2024 | 13/12/2024 | SHREEOM ENTERPRISE | 8.97 | 4.67 | 52.06 | 70
Total | [13 empty] | 105.43 | 81.58 | 77.38