## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Arambag | Electrical | GROUND WATER BASED DAHAR KUNDU (ZONE-II) PIPED WATER SUPPLY SCHEME IN ARAMBAG BLOCK UNDER HOOGHLY DIVISION, HOOGHLY DISTRICT | SM/15913 | New | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Dahar Kundu water supply scheme, Zone-II, T.W. No.- I & II, Block: Armbag, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 2 ,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000310/2022-2023 | 1240/ED | 06/03/2023 | 01/05/2025 | ALPHA ENTERPRISE | 20.47 | 0 | 0 | 30
2 | HOOGHLY | Arambag | Hooghly Division | GROUND WATER BASED DAHAR KUNDU (ZONE-II) PIPED WATER SUPPLY SCHEME IN ARAMBAG BLOCK UNDER HOOGHLY DIVISION, HOOGHLY DISTRICT | SM/15913 | New | BALUNDI,SELALPUR, MADHABPUR, DAHARKUNDU ZONE-II Piped Water Supply Scheme with T.W, SWITCH ROOM , BOUNDARY WALL, RISING MAIN, LDS, FHTC & Construction of OHR with 20 mtr. staging height including Soil Investigation work at ARAMBAGH Block under ARAMBAGH Sub-Division Under Hooghly Division PHE Dte | Assistant Engineer | Junior Engineer (Civill) | ORD/000556/2023-2024 | 3191/HUG | 31/10/2023 | 31/10/2025 | S & P ENTERPRISE | 2296.42 | 176.39 | 7.68 | 70
3 | HOOGHLY | Arambag | Hooghly Division | GROUND WATER BASED DAHAR KUNDU (ZONE-II) PIPED WATER SUPPLY SCHEME IN ARAMBAG BLOCK UNDER HOOGHLY DIVISION, HOOGHLY DISTRICT | SM/15913 | New | Material Requisition To Resource Division |  |  | RTOR000476/2023-2024 | 3057/10/Hug | 11/10/2023 | 11/10/2023 | Resource Division | 13.55 | 0 | 0 | 0
4 | HOOGHLY | Arambag | Hooghly Division | GROUND WATER BASED DAHAR KUNDU (ZONE-II) PIPED WATER SUPPLY SCHEME IN ARAMBAG BLOCK UNDER HOOGHLY DIVISION, HOOGHLY DISTRICT | SM/15913 | New | Material Requisition To Resource Division |  |  | RTOR000044/2023-2024 | 1234/17/Hug | 28/04/2023 | 28/04/2023 | Resource Division | 42.83 | 0 | 0 | 0
5 | HOOGHLY | Arambag | Electrical | GROUND WATER BASED DAHAR KUNDU (ZONE-II) PIPED WATER SUPPLY SCHEME IN ARAMBAG BLOCK UNDER HOOGHLY DIVISION, HOOGHLY DISTRICT | SM/15913 | New | Quotation Bill for New Service Connection at Dahar Kundu W/S. Sch.TW-I, Z-II |  |  | BILL/04583/2023-2024 | 588 | 28/12/2023 | 28/12/2023 | WBSEDCL | 6.53 | 0 | 0 | 0
6 | HOOGHLY | Arambag | Electrical | GROUND WATER BASED DAHAR KUNDU (ZONE-II) PIPED WATER SUPPLY SCHEME IN ARAMBAG BLOCK UNDER HOOGHLY DIVISION, HOOGHLY DISTRICT | SM/15913 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for DAHARKUNDU PIPED W/S SCHEME, Zone - II, T.W. No. III, Block: Arambag, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000204/2024-2025 | 1160/ED | 14/06/2024 | 12/09/2024 | B.P. TRADING CORPORATION | 10.75 | 0 | 0 | 0
7 | HOOGHLY | Arambag | Hooghly Division | GROUND WATER BASED DAHAR KUNDU (ZONE-II) PIPED WATER SUPPLY SCHEME IN ARAMBAG BLOCK UNDER HOOGHLY DIVISION, HOOGHLY DISTRICT | SM/15913 | New | Designing making and erection of Display Board using logo and tag line of LAND DEMARCATION OF P.H.E. Dte. to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under ARAMBAGH Sub Division under Hooghly Division PHE Dte. (1) MAYAPUR PWSS (Z-II)- 1no¿s (2) BALUNDI PWSS - 4no¿s (3) BHALIA PWSS (Z-I)- 2 no¿s (4) BHALIA PWSS (Z-II)- 1 no¿s (5) DAHARKUNDU PWSS (Z-I)- 2 no¿s, (6) DAHARKUNDU PWSS (Z-II)- 2 no¿s, (7) GOBINDANAGAR PWSS(Z-I) ¿2 no¿s | Assistant Engineer | Junior Engineer (Civill) | ORD/002742/2024-2025 | 1150/Arg | 10/12/2024 | 10/01/2025 | DHIRENDRA ENGINEERING & CONSTRUCTION | 0.98 | 0 | 0 | 0
8 | HOOGHLY | Arambag | Electrical | GROUND WATER BASED DAHAR KUNDU (ZONE-II) PIPED WATER SUPPLY SCHEME IN ARAMBAG BLOCK UNDER HOOGHLY DIVISION, HOOGHLY DISTRICT | SM/15913 | New | Quotation of New Service Connection for Dahar Kundu w/s Scheme,Zone-II,TW No-II Block-Khanakul-II Dist-Hooghly under ED,PHE Dte (SM/15913) Application No-5004015927 Reference Id-503563368 |  |  | BILL/06064/2023-2024 | 754 | 16/02/2024 | 16/02/2024 | WBSEDCL | 16.1 | 0 | 0 | 0
Total | [13 empty] | 2407.63 | 176.39 | 7.33