## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF HANRAL Z-I PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK | SM/16119 | Augmentation | Providing Functional Household Tap Connection (FHTC) under JJM within left out portion of HARALPWSS under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer (Civil) |  | ORD/000035/2023-2024 | 1134/HUG | 19/04/2023 | 19/05/2023 | NOBLE ENGINEERS CO-OPERATIVE SOCIETY LTD. | 14.97 | 0 | 0 | 100
2 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF HANRAL Z-I PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK | SM/16119 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000279/2023-2024 | 1386/52/Hug | 15/05/2023 | 15/05/2023 | Resource Division | 1.23 | 0 | 0 | 0
3 | HOOGHLY |  | Electrical | AUGMENTATION OF HANRAL Z-I PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK | SM/16119 | Augmentation | QUOTATION FOR NEW SERVICE CONNECTION AT HANRAL W/S SCHEME, T/W NO. - III, DIST. - HOOGHLY |  |  | BILL/00762/2023-2024 | 45 | 23/05/2023 | 23/05/2023 | WBSEDCL | 10.88 | 0 | 0 | 0
4 | HOOGHLY |  | Electrical | AUGMENTATION OF HANRAL Z-I PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK | SM/16119 | Augmentation | Quotation Bill for New Service Connection at Hanral W/S. Sch. PH-III, Z-I Hooghly |  |  | BILL/00894/2022-2023 | 179 | 09/03/2023 | 09/03/2023 | WBSEDCL | 2.86 | 0 | 0 | 0
5 | HOOGHLY |  | Electrical | AUGMENTATION OF HANRAL Z-I PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK | SM/16119 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Hanral water supply scheme, Zone-I, T.W. No. III, Block: Polba Dadpur, District - Hooghly under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/001374/2022-2023 | 969/ED | 25/02/2023 | 26/05/2023 | TRIDENT ENTERPRISE | 11.08 | 0 | 0 | 90
6 | HOOGHLY |  | Electrical | AUGMENTATION OF HANRAL Z-I PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK | SM/16119 | Augmentation | Quotation for new service connection at Hanral W/S Sch., Zone -I, T/W No. - III [SM/16119] under SM/Dadpur, WBSEDCL, Ref Id. - 503657583, dt. - 25-06-2024, Application No. - 5004214131 |  |  | BILL/00969/2024-2025 | 256 | 03/07/2024 | 03/07/2024 | WBSEDCL | 3.53 | 0 | 0 | 0
7 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF HANRAL Z-I PIPED W/S SCHEME UNDER POLBA DADPUR BLOCK | SM/16119 | Augmentation | Sinking of tube-well, LDS, Rising Main, Connection with Existing FHTC, construction of switch-room & boundary wall & Repairing of Existing Switch Rooms, Boundary walls at different TW sites of both zones for Augmentation of HANRAL Piped Water Supply Scheme under POLBA DADPUR Block, District:- Hooghly | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000178/2023-2024 | 1683/HUG | 08/06/2023 | 05/12/2023 | ASIA CONSTRUCTION | 503.22 | 0 | 0 | 45
Total | [13 empty] | 547.77 | 0 | 0