## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF PATUL PIPED WATER SUPPLY SCHEME, BLOCK- KHANAKUL-I, DISTRICT-HOOGHLY | SM/16120 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000102/2023-2024 | 1263/17/Hug | 03/05/2023 | 03/05/2023 | Resource Division | 17.17 | 0 | 0 | 0
2 | HOOGHLY |  | Electrical | AUGMENTATION OF PATUL PIPED WATER SUPPLY SCHEME, BLOCK- KHANAKUL-I, DISTRICT-HOOGHLY | SM/16120 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Patul water supply scheme, T.W. No.-V, Block: Khanakul-I, District - Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 2 | Junior Engineer4 | ORD/001385/2023-2024 | 4735/ED | 15/12/2023 | 14/03/2024 | MAA KALI ENTERPRISE | 10.74 | 0 | 0 | 30
3 | HOOGHLY |  | Electrical | AUGMENTATION OF PATUL PIPED WATER SUPPLY SCHEME, BLOCK- KHANAKUL-I, DISTRICT-HOOGHLY | SM/16120 | Augmentation | Quotation Bill for New Service Connection at Patul W/S. Sch. Z-II, TW-II |  |  | BILL/04592/2023-2024 | 593 | 29/12/2023 | 29/12/2023 | WBSEDCL | 3.51 | 0 | 0 | 0
4 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF PATUL PIPED WATER SUPPLY SCHEME, BLOCK- KHANAKUL-I, DISTRICT-HOOGHLY | SM/16120 | Augmentation | Repairing of R.C.C. Elevated Reservoir of PATUL PWSS Under Arambagh Sub-Division Hooghly Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000485/2024-2025 | 4149/HUG | 26/12/2024 | 26/03/2025 | R.K. TRADERS | 10.98 | 0 | 0 | 99
5 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF PATUL PIPED WATER SUPPLY SCHEME, BLOCK- KHANAKUL-I, DISTRICT-HOOGHLY | SM/16120 | Augmentation | Designing making and erection of Display Board using logo and tag line of LAND DEMARCATION OF P.H.E. Dte. to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under ARAMBAGH Sub Division under Hooghly Division PHE Dte. (1) KHANAKUL PWSS - 6 nos (2) KRISHNANAGAR PWSS - 4nos (3) PATUL PWSS - 4nos | Assistant Engineer | Junior Engineer (Civill) | ORD/002646/2024-2025 | 810/Arg | 23/08/2024 | 22/09/2024 | HAZRA CONSTRUCTION | 0.98 | 0 | 0 | 0
6 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF PATUL PIPED WATER SUPPLY SCHEME, BLOCK- KHANAKUL-I, DISTRICT-HOOGHLY | SM/16120 | Augmentation | Construction of 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement, Boundary Wall in Proposed T.W Site, Laying rising main pipe for inter connection between T.W & Distribution For Source Augmentation of Patul Piped Water Supply Scheme under Arambagh Sub-Division of Hooghly Division P.HE Dte. within KHANAKUL-I Block. | Assistant Engineer | Junior Engineer (Civill) | ORD/000076/2023-2024 | 1310/HUG | 10/05/2023 | 14/01/2025 | MUNSHI TAJUDDIN | 11.82 | 0 | 0 | 99
7 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF PATUL PIPED WATER SUPPLY SCHEME, BLOCK- KHANAKUL-I, DISTRICT-HOOGHLY | SM/16120 | Augmentation | AUGMENTATION OF PATUL Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 200 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under KHANAKUL-I Block, District:- Hooghly [AUGMENTATION SCHEME] | Assistant Engineer | Junior Engineer (Civill) | ORD/000271/2023-2024 | 2288/HUG | 03/08/2023 | 01/05/2025 | R.K. TRADERS | 271.15 | 0 | 0 | 45
Total | [13 empty] | 326.36 | 0 | 0