## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Electrical | Source Augmentation of SABALSINGHAPUR Piped Water Supply Scheme under Khanakul-II Block | SM/16121 | Augmentation | Quotation Bill for New Service Connection at Sabalsinghapur W/S. Sch. PH-III |  |  | BILL/00893/2022-2023 | 180 | 09/03/2023 |  | WBSEDCL | 2.81 | 0 | 0 | 0
2 | HOOGHLY |  | Electrical | Source Augmentation of SABALSINGHAPUR Piped Water Supply Scheme under Khanakul-II Block | SM/16121 | Augmentation | "Quotation Bill for New Service Connection at Sabalsinghapur W/S. Sch. PH-IV Hooghly" |  |  | BILL/00895/2022-2023 | 180 | 09/03/2023 |  | WBSEDCL | 2.75 | 0 | 0 | 0
3 | HOOGHLY |  | Hooghly Division | Source Augmentation of SABALSINGHAPUR Piped Water Supply Scheme under Khanakul-II Block | SM/16121 | Augmentation | Sinking of I (one) No Big dia tube well (250 mm X 150mm) with supply of PVC Pipe and strainer and having depth upto 150 M at 3rd TW site of Sabalsinghapur W/S Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000893/2022-2023 | 1413/Hug | 12/07/2022 | 11/08/2022 | SUBHAJIT BISWAS | 7.88 | 7.32 | 92.84 | 0
4 | HOOGHLY |  | Electrical | Source Augmentation of SABALSINGHAPUR Piped Water Supply Scheme under Khanakul-II Block | SM/16121 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Sabalsinghapur water supply scheme, T.W. No. IV, Block: Khanakul-II, District - Hooghly under Electrical Division, PHE Dte. |  |  | ORD/002102/2022-2023 | 2048/ED | 01/12/2022 | 01/03/2023 | BOSE & CHATTERJEE INDUSTRIES | 10.57 | 0 | 0 | 0
5 | HOOGHLY |  | Electrical | Source Augmentation of SABALSINGHAPUR Piped Water Supply Scheme under Khanakul-II Block | SM/16121 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Sabalsinghapur water supply scheme, T.W. No. III, Block: Khanakul-II, District - Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 2 ,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000869/2023-2024 | 3442/ED | 11/08/2023 | 09/11/2023 | BISALAXMI ENTERPRISE | 10.74 | 10.52 | 97.96 | 25
6 | HOOGHLY |  | Electrical | Source Augmentation of SABALSINGHAPUR Piped Water Supply Scheme under Khanakul-II Block | SM/16121 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Sabalsinghapur water supply scheme, T.W. No. IV, Block: Khanakul-II, District - Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 2 | Junior Engineer4 | ORD/001074/2023-2024 | 4190/ED | 01/11/2023 | 30/01/2024 | D. K. ELECTRIC | 10.83 | 5.37 | 49.6 | 40
7 | HOOGHLY |  | Electrical | Source Augmentation of SABALSINGHAPUR Piped Water Supply Scheme under Khanakul-II Block | SM/16121 | Augmentation | Quotation money deposition for new service connection at Udna w/s scheme, T.W. No.-IV, Sabal Singapur pwss, Dist.-Hooghly under PHE Dte. Application No- 5004235292 Reference ID- 503666262 SM Code- 16121 |  |  | BILL/00817/2024-2025 | 221 | 18/06/2024 |  | WBSEDCL | 4.03 | 0 | 0 | null
8 | HOOGHLY |  | Electrical | Source Augmentation of SABALSINGHAPUR Piped Water Supply Scheme under Khanakul-II Block | SM/16121 | Augmentation | Quotation money deposition for new service connection at Udna w/s scheme, T.W. No.-III, Sabal Singapur pwss, Dist.-Hooghly under PHE Dte. Application No- 5004235310 Reference ID- 5004235310 SM Code- 16121 |  |  | BILL/00818/2024-2025 | 220 | 18/06/2024 |  | WBSEDCL | 5.73 | 0 | 0 | null
9 | HOOGHLY |  | Electrical | Source Augmentation of SABALSINGHAPUR Piped Water Supply Scheme under Khanakul-II Block | SM/16121 | Augmentation | Quotation money deposition for new service connection at Udna w/s scheme, T.W. No.-III, Sabal Singapur pwss, Dist.-Hooghly under PHE Dte. Application No- 5004235310 Reference ID- 5004235310 SM Code- 16121 |  |  | BILL/00818/2024-2025 | 220 | 18/06/2024 |  | WBSEDCL | 5.73 | 0 | 0 | null
10 | HOOGHLY |  | Electrical | Source Augmentation of SABALSINGHAPUR Piped Water Supply Scheme under Khanakul-II Block | SM/16121 | Augmentation | Quotation money deposition for new service connection at Udna w/s scheme, T.W. No.-II, Sabal Singapur pwss, Dist.-Hooghly under PHE Dte. Application No- 5004234490 Reference ID- 503666255 SM Code- 16121 |  |  | BILL/00819/2024-2025 | 219 | 18/06/2024 |  | WBSEDCL | 7.27 | 0 | 0 | null
11 | HOOGHLY |  | Hooghly Division | Source Augmentation of SABALSINGHAPUR Piped Water Supply Scheme under Khanakul-II Block | SM/16121 | Augmentation | Construction of 2 Nos. 3.6 m X 3.0 m Switch Room with Additional Plinth Height, with Sanitary and Water Supply arrangement, Laying of C.I/D.I pipes & specials for connection of Proposed 2 nos. T.W with distribution system, For Source Augmentation of SABALSINGHAPUR W/S Scheme under Arambagh Sub - Division P.H.E. Dte. | Assistant Engineer | Junior Engineer (Civill),Khanakul 2 Block Junior Engineer | ORD/000114/2023-2024 | 1443/HUG | 18/05/2023 | 11/06/2024 | KARALI MOHAN KHAMRUI | 31.29 | 8.99 | 28.72 | 94
Total | [13 empty] | 99.63 | 32.2 | 32.32