## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | Source Augmentation of SABALSINGHAPUR Piped Water Supply Scheme under Khanakul-II Block | SM/16121 | Augmentation | Sinking of I (one) No Big dia tube well (250 mm X 150mm) with supply of PVC Pipe and strainer and having depth upto 150 M at 3rd TW site of Sabalsinghapur W/S Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000893/2022-2023 | 1413/Hug | 12/07/2022 | 11/08/2022 | SUBHAJIT BISWAS | 7.88 | 7.32 | 92.84 | 0
2 | HOOGHLY |  | Electrical | Source Augmentation of SABALSINGHAPUR Piped Water Supply Scheme under Khanakul-II Block | SM/16121 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Sabalsinghapur water supply scheme, T.W. No. IV, Block: Khanakul-II, District - Hooghly under Electrical Division, PHE Dte. |  |  | ORD/002102/2022-2023 | 2048/ED | 01/12/2022 | 01/03/2023 | BOSE & CHATTERJEE INDUSTRIES | 10.57 | 0 | 0 | 0
3 | HOOGHLY |  | Hooghly Division | Source Augmentation of SABALSINGHAPUR Piped Water Supply Scheme under Khanakul-II Block | SM/16121 | Augmentation | Construction of 2 Nos. 3.6 m X 3.0 m Switch Room with Additional Plinth Height, with Sanitary and Water Supply arrangement, Laying of C.I/D.I pipes & specials for connection of Proposed 2 nos. T.W with distribution system, For Source Augmentation of SABALSINGHAPUR W/S Scheme under Arambagh Sub - Division P.H.E. Dte. | Assistant Engineer | Junior Engineer (Civill),Khanakul 2 Block Junior Engineer | ORD/000114/2023-2024 | 1443/HUG | 18/05/2023 | 11/06/2024 | KARALI MOHAN KHAMRUI | 31.29 | 31.26 | 99.89 | 94
4 | HOOGHLY |  | Electrical | Source Augmentation of SABALSINGHAPUR Piped Water Supply Scheme under Khanakul-II Block | SM/16121 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Sabalsinghapur water supply scheme, T.W. No. III, Block: Khanakul-II, District - Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 2 ,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000869/2023-2024 | 3442/ED | 11/08/2023 | 09/11/2023 | BISALAXMI ENTERPRISE | 10.74 | 10.66 | 99.24 | 25
5 | HOOGHLY |  | Electrical | Source Augmentation of SABALSINGHAPUR Piped Water Supply Scheme under Khanakul-II Block | SM/16121 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Sabalsinghapur water supply scheme, T.W. No. IV, Block: Khanakul-II, District - Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 2 | Junior Engineer4 | ORD/001074/2023-2024 | 4190/ED | 01/11/2023 | 30/01/2024 | D. K. ELECTRIC | 10.83 | 10.75 | 99.21 | 40
6 | HOOGHLY |  | Electrical | Source Augmentation of SABALSINGHAPUR Piped Water Supply Scheme under Khanakul-II Block | SM/16121 | Augmentation | Quotation Bill for New Service Connection at Sabalsinghapur W/S. Sch. PH-III |  |  | BILL/00893/2022-2023 | 180 | 09/03/2023 | 09/03/2023 | WBSEDCL | 2.81 | 0 | 0 | 0
7 | HOOGHLY |  | Electrical | Source Augmentation of SABALSINGHAPUR Piped Water Supply Scheme under Khanakul-II Block | SM/16121 | Augmentation | "Quotation Bill for New Service Connection at Sabalsinghapur W/S. Sch. PH-IV Hooghly" |  |  | BILL/00895/2022-2023 | 180 | 09/03/2023 | 09/03/2023 | WBSEDCL | 2.75 | 0 | 0 | 0
8 | HOOGHLY |  | Hooghly Division | Source Augmentation of SABALSINGHAPUR Piped Water Supply Scheme under Khanakul-II Block | SM/16121 | Augmentation | Protection works and other allied works at 2nd TubeWell Sites of Soaluk & Sabalsinghapur Water Supply Scheme under Arambagh Sub Division of Hooghly Division P.H.E Dte. |  |  | ORD/000473/2024-2025 | 4052/HUG | 19/12/2024 | 19/03/2025 | TANISA ENTERPRISE | 15.54 | 0 | 0 | 0
9 | HOOGHLY |  | Hooghly Division | Source Augmentation of SABALSINGHAPUR Piped Water Supply Scheme under Khanakul-II Block | SM/16121 | Augmentation | Repair and Renovation Works of R.C.C. Elevated Reservoir, Boundary Wall, Switch Room of SABALSINGHAPUR PWSS under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. |  |  | ORD/000453/2024-2025 | 4078/HUG | 19/12/2024 | 19/03/2025 | CHAKRABORTY ENTERPRISE | 14.1 | 0 | 0 | 0
10 | HOOGHLY |  | Hooghly Division | Source Augmentation of SABALSINGHAPUR Piped Water Supply Scheme under Khanakul-II Block | SM/16121 | Augmentation | Designing making and erection of Display Board using logo and tag line of LAND DEMARCATION OF P.H.E. Dte. to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under ARAMBAGH Sub Division under Hooghly Division PHE Dte. (1) SABALSINGHAPUR PWSS-4nos (2) BARADANGAL (Z-II) PWSS-2nos (3) SAIDPUR (Z-I) PWSS-4nos (4) SOALUK PWSS-4nos | Assistant Engineer | Junior Engineer (Civill) | ORD/002648/2024-2025 | 814/Arg | 23/08/2024 | 22/09/2024 | TITAS CONSTRUCTION | 0.98 | 0 | 0 | 100
11 | HOOGHLY |  | Hooghly Division | Source Augmentation of SABALSINGHAPUR Piped Water Supply Scheme under Khanakul-II Block | SM/16121 | Augmentation | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under ARAMBAGH Sub-Division under Hooghly Division PHE Dte. (i) PALASPAI PWSS (ii) SABALSINGHAPUR PWSS (iii) CHINGRA (ZONE- I) PWSS (iv) CHINGRA (ZONE- II) PWSS (v) HAYATPUR PWSS (vi) PRATAPNAGAR PWSS | Assistant Engineer | Junior Engineer (Civill) | ORD/000441/2024-2025 | 802/Arg | 23/08/2024 | 30/08/2024 | LIMRA SOCIAL WELFARE SOCIETY | 0.95 | 0 | 0 | 100
12 | HOOGHLY |  | Electrical | Source Augmentation of SABALSINGHAPUR Piped Water Supply Scheme under Khanakul-II Block | SM/16121 | Augmentation | Quotation money deposition for new service connection at Udna w/s scheme, T.W. No.-III, Sabal Singapur pwss, Dist.-Hooghly under PHE Dte. Application No- 5004235310 Reference ID- 5004235310 SM Code- 16121 |  |  | BILL/00818/2024-2025 | 220 | 18/06/2024 | 18/06/2024 | WBSEDCL | 5.73 | 0 | 0 | 0
13 | HOOGHLY |  | Electrical | Source Augmentation of SABALSINGHAPUR Piped Water Supply Scheme under Khanakul-II Block | SM/16121 | Augmentation | Quotation money deposition for new service connection at Udna w/s scheme, T.W. No.-IV, Sabal Singapur pwss, Dist.-Hooghly under PHE Dte. Application No- 5004235292 Reference ID- 503666262 SM Code- 16121 |  |  | BILL/00817/2024-2025 | 221 | 18/06/2024 | 18/06/2024 | WBSEDCL | 4.03 | 0 | 0 | 0
14 | HOOGHLY |  | Electrical | Source Augmentation of SABALSINGHAPUR Piped Water Supply Scheme under Khanakul-II Block | SM/16121 | Augmentation | Quotation money deposition for new service connection at Udna w/s scheme, T.W. No.-II, Sabal Singapur pwss, Dist.-Hooghly under PHE Dte. Application No- 5004234490 Reference ID- 503666255 SM Code- 16121 |  |  | BILL/00819/2024-2025 | 219 | 18/06/2024 | 18/06/2024 | WBSEDCL | 7.27 | 0 | 0 | 0
Total | [13 empty] | 125.48 | 59.98 | 47.8