## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Electrical | Source Augmentation of JAGATPUR Piped Water Supply Scheme under Khanakul-II Block | SM/16122 | Augmentation | Hire Charges Bill for official use office of the Assistant Engineer -I PHED |  |  | ORD/002498/2022-2023 | 203_ae1 | 27/03/2023 | 26/03/2024 | DASHRATH KUMAR PRAJAPATI | 5 | 0.39 | 7.83 | 1
2 | HOOGHLY |  | Electrical | Source Augmentation of JAGATPUR Piped Water Supply Scheme under Khanakul-II Block | SM/16122 | Augmentation | Quotation of New Service Connection for Jagatpur w/s Scheme, TW No-4 Block-Khanakul-II,Dist-Hooghly under Electrical Division, PHE Dte |  |  | BILL/03860/2023-2024 | 308 | 27/09/2023 | 27/09/2023 | WBSEDCL | 7.56 | 0 | 0 | 0
3 | HOOGHLY |  | Electrical | Source Augmentation of JAGATPUR Piped Water Supply Scheme under Khanakul-II Block | SM/16122 | Augmentation | Quotation of New Service Connection for Jagatpur w/s Scheme, TW no-5 Block-Khanakul-II,Dist-Hooghly under Electrical division,PHE Dte |  |  | BILL/03861/2023-2024 | 289 | 20/09/2023 | 20/09/2023 | WBSEDCL | 6.65 | 0 | 0 | 0
4 | HOOGHLY |  | Electrical | Source Augmentation of JAGATPUR Piped Water Supply Scheme under Khanakul-II Block | SM/16122 | Augmentation | Hire Charges Bill of V.No.- WB-04G-2822 for official use of Electrical Division PHED. |  |  | ORD/001029/2023-2024 | 591_AE-1_ED | 21/08/2023 | 28/08/2023 | DASHRATH KUMAR PRAJAPATI | 5 | 1.95 | 39.07 | 10
5 | HOOGHLY |  | Electrical | Source Augmentation of JAGATPUR Piped Water Supply Scheme under Khanakul-II Block | SM/16122 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Jagatpur water supply scheme, T.W. No. I & II, Block: Khanakul-II, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 2 | Junior Engineer4 | ORD/000030/2023-2024 | 1707/ED | 18/04/2023 | 17/07/2023 | GHOSE ENGINEERING SYNDICATE | 21.93 | 21.82 | 99.5 | 40
6 | HOOGHLY |  | Hooghly Division | Source Augmentation of JAGATPUR Piped Water Supply Scheme under Khanakul-II Block | SM/16122 | Augmentation | Construction of 2 Nos. 3.6 m X 3.0 m Switch Room with Additional Plinth Height, with Sanitary and Water Supply arrangement, Laying of C.I/D.I pipes & specials for connection of Proposed 2 nos. T.W with distribution system, For Source Augmentation of JAGATPUR W/S Scheme under Arambagh Sub - Division P.H.E. Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000115/2023-2024 | 1444/HUG | 18/05/2023 | 17/06/2023 | S.S. CONSULTANCY AND CONSTRUCTION | 31.19 | 31.18 | 99.98 | 65
7 | HOOGHLY |  | Electrical | Source Augmentation of JAGATPUR Piped Water Supply Scheme under Khanakul-II Block | SM/16122 | Augmentation | Quotation of New Service Connection for Jagatpur w/s Scheme,PH No-I Block-Khanakul-II Dist-Hooghly under Electrical Division,PHE Dte.(SM/16122) Application No-5004134007 Reference Id-503627506 |  |  | BILL/01002/2024-2025 | 262 | 03/07/2024 | 03/07/2024 | WBSEDCL | 12.35 | 0 | 0 | 0
8 | HOOGHLY |  | Hooghly Division | Source Augmentation of JAGATPUR Piped Water Supply Scheme under Khanakul-II Block | SM/16122 | Augmentation | Repair and Renovation Works of R.C.C. Elevated Reservoir, Boundary Wall, Switch Room &Construction of Internal Pathway of JAGATPUR PWSS under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000454/2024-2025 | 4077/HUG | 19/12/2024 | 17/06/2025 | DAS CONSTRUCTION | 20.22 | 0 | 0 | 100
Total | [13 empty] | 109.89 | 55.34 | 50.36